## 1st qtr (6)
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE FIRST QUARTER , CY 2019
Province, City or Municipality: Bayawan City, Negros Orietnal
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of | Remarks
[5 empty] | % of | Total Cost Incurred | Extensions, if
[5 empty] | Completion | to Date | any
Bayawan Agroforestry Project - GTZ EnRD - LGU Equity | Selected barangay in Bayawan City with classified forestland | 1700120 |  |  | 89.52% | 1521988 |  | last transaction 12/31/16
Sta. Bayabas - Common Health Fund | Bayawan City | 5326494.4 |  |  | 34.11% | 1816660.35 |  | on going
Establishment of Community-Based Instant Complementary Food Processing Center Towards Sustaining Siglang Pinoy Project of the DOST-Food & Nutrition | Barangay Nangka | 347250 |  | 2387-09-15 | 95.72% | 332394.25
Provision of Portable Water Supply -SALINTUBIG (LGU Equity & DILG) re: Improvement of Tayawan Proper Water Supply | Proper Tayawan | 2661417 | 2015-06-06 | 2019-02-28 | 100% | 2661417 |  | Turned-over to BAWAD
Provision of Portable Water Supply -SALINTUBIG (LGU Equity & DILG-BUB) re: Upgrading of Sitio Lapay, Dawis Water Supply System | Lapay, Dawis | 5203583 | 2015-06-01 | 2017-09-15 | 99% | 4288821.52 |  | Turned-over to BAWAD
LGU Equity & DILG (BUB) for the Rehabilitation of San Miguel Potable Water Supply System | Proper San Miguel | 3000000 | 2016-06-17 |  | 95% | 2701363.56 |  | Turned-over to BAWAD
LGU Equity& DILG (BUB) for the Rehabilitation of Sitio Cayaocao Potable Water Supply System | Sitio Cayaocao, Barangay Narra | 4500000 | 2016-06-17 |  | 98% | 3791101.13 |  | Turned-over to BAWAD
page 1 of 6
LGU Equity & DILG (BUB) for the Rehabilitation of Minaba Potable Water Supply System | Proper Minaba | 2000000 | 2016-06-17 | 2019-01-31 | 100% | 1671639.63 |  | Turned-over to BAWAD
LGU Equity & DILG (BUB) for the Improvements of Cansumalig Proper Water Supply System | Proper Cansumalig | 1000000 | 2016-06-17 | 2018-01-31 | 100% | 809199.16 |  | Physically Completed COC issued 7/26/18
LGU Equity & DILG (BUB) for the Rehabilitation of Proper San Isidro Potable Water Supply System | Barangay San Isidro | 750000 | 2016-03-16 | 2017-05-31 | 100% | 610799.45 |  | Physically Completed COC issued 4/3/18
LGU Equity & DILG (BUB) for the Rehabilitation of Proper Villasol Potable Water Supply System | Proper Villasol | 750000 | 2016-03-16 |  | 95% | 750000 |  | Turned-over to BAWAD
LGU Equity & DILG ( BUB ) for the Improvement of Banaybanay Water supply System | Barangay Banaybanay | 600000 | 2016-03-16 |  | 88% | 600000 |  | Turned-over to BAWAD
LGU Equity & DILG ( BUB ) for the Proposed Hanging Trunkline (Footbridge) for Sitio Damig, Kalamtukan & Sitio Baong Kalumboyan | Barangay Kalumboyan | 1500000 | 2017-08-31 | 2019-03-31 | 100% | 1177377.74 |  | on going
LGU Equity & DILG ( BUB ) for Rescue Vehicle intended to PWD's & Senior Citizen | Bayawan City | 1000000 |  |  | 100% | 995000 |  | completed
LGU Equity & DILG for the Rehabilitation of Tayawan Water System - Phase 2 | Barangay Tayawan | 3750000 |  |  | 100% | 3359134.98 |  | Turned-over to BAWAD
LGU Equity for the Renovation of Public Market | Bayawan City | 437865 |  |  | 0% | 0
Financial Assistance to Bayawan City for Various Electrification Projects from Province of Negros Oriental | Bayawan City | 100000 |  |  | 0% | 0
page 2 of 6
DBM & LGU Equity to the Rehabilitation of Pagatban Water System | Barangay Pagatban | 1780000 | 2017-08-01 | 2019-01-01 | 100% | 1686689.93 |  | Turned-over to BAWAD
MNCHN Grant | 28 Barangay | 817794.28 |  |  | 98.01% | 801486.04
Rubber Tree Reforestation Project | Bayawan City | 1500000 |  |  | 76.05% | 1140693.79
Rubber Tree Reforestation Project (Nursery Expansion) | Bry Banaybanay & Dawis | 500000 |  |  | 78.78% | 393887
DA & LGU Equity to Improvement of Organic Fertilizer Plant & Establishment of Nurseries for the provisions of chemical-free seeds to farmers using greenhouse technology | Barangay Maninihon | 2000000 |  |  | 0% | 0
DA R7 for Organic Fetilizer Production & Marketing (Construction of OFRAB Building & Installation of Electrical & Plumbing of OFPRAB Building) | Sitio Omod, Barangay Maninihon | 805110 |  |  | 35.97% | 289617.6 |  | on going
DA &LGU Equity to Extension & Rehab. of Irrigation System 3 sites (BUB-DA) | Camayaan, Cansilong & Mantapi | 300000 |  |  | 80% | 240000 |  | Implemented by NIA
DA R7 for Building & Machine for Food Processing of Fruits, Vegetables, Fish, Grains and Meat |  | 1300000 |  |  | 21.5% | 279468.52 |  | on going
DA & LGU Equity to Rehabilitation & Extension of Line Canal for Mantapi - Cansigid Irrigation System (BUB) | Mantapi - Cansigid, Banga | 8000000 | 2018-06-01 |  | 70% | 6043076.58 |  | on going
page 3 of 6
DA & LGU Equity to Mechanical Dryer with Storage Facility for Bugay, Ohot-Narra, Tayawan (BUB-DA) | Bugay, Ohot-Narra; Mantapi | 2500000 |  |  | 0% | 0
DA & LGU Equity for Small Water Impounding (BUB) | Bayawan City | 4000000 |  |  |  | 1699937.88 |  | on going
DA & LGU Equity for Upgrading of Slaughter House Double " A " | Sitio Bulibuli, Brgy. Banga | 30000000 | 2018-03-16 |  | 98% | 16967842.4 |  | on going
DOLE & LGU Equity to Rubber Products Processing Machinery (Farm Level Rubber Sheet Production) | Rural Barangays | 843500 |  |  | 98% | 821500
DOLE & LGU Equity to Hog Fattening | Lapay, Dawis | 300000 |  |  | 98.46% | 295366
DOLE & LGU Equity to Stainless Steel Equipment for Food Processing | Barangay Nangka | 120000 |  |  | 24.12% | 28940
DOLE & LGU Equity to Motorized Fishing Banca & Accessories | Barangay Suba | 502502.4 |  |  | 23.53% | 118233.04
DOLE & LGU Equity to Small Scale Farm Services (Farm Implements & Rice Mill Project) | Candalaga | 931950 |  |  | 99.09% | 923449.9
DOLE & LGU Equity to Bag Making Project | Cambolo | 345547.6 |  |  | 1.852% | 6400
DENR & LGU Equity to On-Farm Wood Lot Production & Agro Forestry Project (BUB) | Brgy Kalamtukan, Tayawan & Narra | 1500000 |  |  | 0% | 0 |  | - No funds received from DENR yet
page 4 of 6
DOE & LGU Equity to Solar Electification 5 Sitios (BUB) | Tabuan; Manduao; Kalamtukan; Banaybanay & Villasol | 3000000 |  |  | 0% | 0 |  | - No funds received from DOE yet
Supplementary Feeding (Cycle VII) | Bayawan City | 6732000 |  |  | 83.32% | 5609228
MDG-Familis-based Action for Children and their Environs in the Slums (FACES) Project of DILG | Bayawan City | 210000 |  |  | 47.78% | 100347.5
Construction of Senior Citizen Center (DSWD) | Barangay Boyco | 1000000 |  |  | 0% | 0
Construction of National Child Development Center (ECCD) | Bayawan City | 2450000 | 2017-04-16 | 2018-11-30 | 100% | 2136100.09 |  | Physically completed
Establishment of Early Child Development Center (Performance Challenged Fund) | Barangay Kalumboyan | 3400000 | 2018-02-15 | 2018-09-30 | 100% | 3393875.94 |  | Physically Completed
LGU Equity toTech 4ED Project | Bayawan City | 400000 |  |  | 0% | 0
LGU Equity to Department of Agriculture for High Valued Crops Development | Bayawan City | 656500 |  |  | 0% | 0
DA to Acquisition of Palay Reaper(cutter) and Post Harvest Facilities and Equipment for SAAD FY 2017 | Bayawan City | 1040000 |  |  | 0% | 0
page 5 of 6
DENR to National Greening Program/Comprehesive Site Development (CSD) | Bayawan City | 1583000 |  |  | 49.61% | 785250 |  | on going
DENR to Enhance National Greening Program-Seedling Production & Seedling Maintenance activities of its Rubber | Bayawan City | 2000000 |  |  | 0.96% | 19200
Completion of Tabuan Barangay Health Station | Barangay Tabuan | 500000 |  |  | 0% | 0
Completion of Minaba Barangay Health Station | Barangay Minaba | 500000 |  |  | 0% | 0
TOTAL |  | 116144633.68 |  |  |  | 70867486.98
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this documents.
CORAZON P. LIRAZAN, CPA MBA | [6 empty] | PRYDE HENRY A. TEVES
City Accountant | [6 empty] | City Mayor
page 6 of 6
cc: - DILG
- CEO
- DA
- CSWD
- Acctg.
1370213.01
Note on A3: bdtrayvilla1: