## sept 2019
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION REPORT
As of September 30, 2019
CITY OF BAYAWAN
[5 empty] | Location | Total Cost (per Budget Approp) | Target Start Date | Target Completion Date | Project Status |  | No. of Ext., if any | Remarks
1 | Project Code | Year |  | Program or Project |  |  |  |  | % of Completion | Total Cost Incurred (per Acctg) |  |  | old engas code
3 |  | CURRENT APPROPRIATION
4
5 |  | 2019 | Loan Amortization |  |  | 58000000 |  |  |  | 49166376.06
6 |  |  | Land
7 |  | 2019 |  | Lot Acquisition for Dita Relocation | Tabuan | 5000000
8 |  | 2019 |  | Lot Acquisition for Road Right of Way | Villareal | 500000
9 |  | 2019 |  | Lot Acquisition for Agricultural Development Center (Tan-ayan) | Tan-ayan | 2500000
10 |  |  | Road Networks
11 | 10710020-001-0135 | 2019 |  | Wayang Access Road Development | Nangka | 20000000 | 2019-02-16 | 2019-12-30 | 45% | 7070295.1
12 | 10710020-002-0088 | 2019 |  | Construction of Ondol-Napit-an FMR | Bayawan City | 20000000 | 2019-03-01 |  |  | 6516616.5 |  | Pending: RROW Issues not yet resolved
13 | 10710020-001-0136 | 2019 |  | Concreting of Access Road from National Highway to Palongpong Agricultural Development Center | Bayawan City | 9000000 | 2019-04-01 | 2019-12-31 | 83% | 876579.47 |  |  |  | target completion
14 | 10710020-001-0134 | 2019 |  | Improvement of Road Leading to Danapa Inland Aquaculture Facility | Nangka | 2000000 | 2019-03-16 | 2019-12-31 | 92% | 589052.76 |  |  |  | target completion
15 | 10710020-001-0137 | 2019 |  | Concreting of Perimeter Road at BCWMEC | Maninihon | 2000000 | 2019-06-01 | 2019-12-31 | 93% | 320183.4 |  |  |  | NO EXPENSE YET?
16 | 10710020-001-0139 | 2019 |  | Concreting of Urban Roads with Drainage System (Gomez St.) | Poblacion | 3000000 | 07/16/19 | 2019-12-31 | 25% | 468172.85 |  |  |  | NO EXPENSE YET?
17 |  | 2019 |  | Improvement of Maninihon-Cansumalig-San Isidro FMR |  | 2387650.49
18 |  |  | Flood Control Systems
19 | 10710020-007-0030 | 2019 |  | Construction of Drainage Canal at Magsulay Agricultural Development Center | Narra | 400000 | 2019-06-01 | 2019-12-31 | 40% | 165391.25 |  |  |  | date
21 | 10710020-007-0029 | 2019 |  | Concreting of Drainage Canals at Barangay Proper, San Isidro | Bayawan City | 400000 | 2019-06-01 | 08/31/19 | 100% | 331852.13 |  |  |  | complete but exp is low
22 |  |  | Water Supply Systems
23 | 0 | 2019 |  | Construction & Installation of Water Supply Systems for Barangays Malabugas, San Roque, Minaba, San Miguel and Tayawan | Various Brgys | 11000000
24 |  |  | Power Supply Systems
25 | 0 | 2019 |  | Electrification Project at Purok Ipil-Ipil, San Roque | San Roque | 600000
26 |  |  | Other Infrastructures Assets
27 |  |  | School Buildings
28 | 10710030-002-0028 | 2019 |  | Construction of Day Care Center, Brgy San Miguel | Bayawan City | 400000 | 07/16/19 | 09/30/19 | 100% | 120858.3 |  |  |  | complete but no expenses
29 |  |  | Markets
30 | 10710030-004-0006 | 2019 |  | Construction of Public Market Stalls in Omod, Maninihon (Phase 1) | Bayawan City | 1678571.43 | 2019-06-16 | 2019-12-31 | 40% | 873960.08 |  |  |  | target completion date
31 |  |  | Other Structures
32 | 10710030-030-0198 | 2019 |  | Completion of Lapay Multi-Purpose Pavement | Dawis | 360000 | 2019-06-01 | 08/31/19 | 100% | 174859.65 |  |  |  | complete but no expenses
33 | 10710010-002-0011 | 2019 |  | Construction of Concrete Fence of Minaba Elementary School | Minaba | 500000 | 05/31/19 | 2019-12-31 | 90% | 95315.24 |  |  |  | 90% no expense, target date
34 | 10710010-002-0013 | 2019 |  | Construction of Concrete Fence of Canabuan Elementary School | Minaba | 500000 | 2019-06-01 | 2019-12-31 | 90% | 160496.92 |  |  |  | 90% no expense, target date
35 | 10710010-002-0012 | 2019 |  | Construction of Concrete Fence of Minaba High School | Minaba | 678571.43 | 2019-06-01 | 2019-12-31 | 90% | 105687.86 |  |  |  | 90% no expense, target date
36 | 10710030-030-0211 | 2019 |  | Construction of Barangay Multi-Purpose Building, Nangka | Nangka | 1678571.43 |  |  |  | 395897.8
37 | 10710030-030-0209 | 2019 |  | Construction of 2-Storey Multi-Purpose Building, Barangay Poblacion | Poblacion | 1678571.43 |  |  |  | 0
38 | 10710010-002-0015 | 2019 |  | Construction of Concrete Fence of Bolirocon Elementary School, San Isidro | Bolirocon, San Isidro | 278571.43 |  |  |  | 81666.4
39 | 0 | 2019 |  | Construction of Multi-Purpose Building, Barangay San Isidro (Phase 3) | San Roque | 1000000 |  |  |  | 0
40 | 10710010-002-0010 | 2019 |  | Construction of Perimeter Fence at San Roque Elementary School | San Roque | 578571.43 | 2019-06-01 | 2019-12-31 | 80% | 112400.2 |  |  |  | 80% low expense, target date
41 | 0 | 2019 |  | Construction of Barangay Multi-Purpose Building, Tinago (Phase 3) | Tinago | 1678571.43 |  |  |  | 0
42 | 0 | 2019 |  | Establishment of Agricultural Research Center |  | 10877134.99 |  |  |  | 0
43 |  |  |  | Purchase of Construction & Heavy Equipment:
44 |  |  |  | 1 unit Bulldozer |  | 15000000 |  |  |  | 0 |  |  |  | PR in process
45 |  |  |  | 1 unit Backhoe |  | 12000000 |  |  |  | 0
46 |  |  |  | 1 unit Trailer Mounted DW100-T Drilling Rig with Accessories |  | 3594500 |  |  |  | 0 |  |  |  | for 2020
47 |  |  |  | 2 units 6-Wheeler Dump Truck |  | 4400000 |  |  |  | 0 |  |  |  | for 2020
48 |  |  | Other Transportation Equipment
49 |  | 2019 |  | Purchase of Garbage Compactor Truck |  | 5000000 |  |  |  | 0
50 |  | 2019 |  | Purchase of Vacuum Declogger Truck |  | 2000000 |  |  |  | 0 |  |  |  | PR in process
51 |  |  | Breeding Stocks
52 |  | 2019 |  | Purchase of Livestock Breeding Stocks |  | 2000000 |  |  |  | 0
53 |  |  | TOTAL DF - CURRENT APPROPRIATION |  |  | 202669285.49 |  |  |  | 67625661.97
54
55
56 |  | CONTINUING APPROPRIATION
57
60 | ngas 2 |  | Environmental Sanitation Program: |  |  | 0
61 |  | 2004 |  | 1. Sanitary Landfill (Land Acquisition) 2004 | Maninihon | 1000000 |  |  |  | 8311
62 |  | 2001 |  | 2. Sanitary Landfill - Dumpsite Acquisition | Maninihon | 500000 |  |  |  | 0 |  |  | no obligation
63 |  | 2011 |  | Renovation of BDH Canteen | BDH, Ubos | 114000 | 2011-06-01 | 2012-12-31 | 100% | 80418 |  |  | 264-004-11-10-G0021
64 | 10710020-006-0003 | 2011 |  | Const. of Hanging Bridge at Sitio Tiki, Kalumboyan (Phase 3) | Kalumboyan | 700000 | 2011-07-01 |  | 37% | 546410.34 |  | project heavily damaged by typhoon - discontinued | 266-003-11-05-G0009 | project discontinued, what happens to balance
65 | 10710030-005-0002 | 2012 |  | Construction of Slaughterhouse | Suba | 10000000 | 2016-09-16 | 2018-03-31 | 100% | 7818835.46 |  |  | 264-003-1603-G0021
66 | *10710030-030-0023 | 2012 |  | Improvement of Bayawan City Boulevard (Landscaping fronting GK Village) | Villareal | 535115.83 | 2013-08-01 | 2014-03-15 | 100% | 495907.52 |  |  | 264-009-13-04-G0429
67 | *10710030-030-0021 | 2013 |  | Construction of Sports Center and Children's Playground, Phase 3 | Suba | 3000000 | 2013-03-18 | 2015-05-30 | 100% | 2668470.08 |  |  | 264-009-13-03-G0424
68 | *10710030-030-0024 | 2013 |  | Construction of Covered Court at BCsTEC, Phase II | Cabcabon, Banga | 3008100 | 2013-10-01 | 2017-06-30 | 100% | 2783489.42 |  |  | 264-009-13-07-G0437/267-004-13-06-G0003
69 | 10710030-030-0025 | 2013 |  | Rehabilitation of GK Septic Tanks | Villareal | 3104400 | 2013-11-18 |  |  | 77968.68 |  | Pending: sub-standard Fiber Glass septic Tank delivered by supplier not accepted by LGU | 264-009-13-09-G0445
70 | *10710020-002-0036 | 2013 |  | Improvement of Water System for 21 Rural Barangays | Bayawan City | 568710 | 2016-07-01 | 2017-07-31 | 100% | 468013.78 |  |  | 269-001-1511-G0039
71 | *10710020-007-0002 | 2013 |  | Construction of Drainage Canal with Cover Along City Streets | Bayawan City | 606779.6 | 2014-06-02 | 2014-11-30 | 100% | 544360.59 |  |  | 271-002-14-05-G0027
72 | 0 | 2013 |  | Fabrication of Distillation Chamber for Essential Oil Production | Banga | 150000 |  |  |  | 0
73 | *10710020-001-0011 | 2014 |  | Construction of Bayawan City Boulevard/Phase 2 | Bayawan City | 1000000 | 2014-08-16 | 2014-10-30 | 100% | 936750.81 |  |  | 266-001-14-05-g0313
74 | *10710030-030-0031 | 2014 |  | Const. of Motorpool Building, Phase 1, Cabcabon | Cabcabon, Banga | 8483700 | 2015-07-06 | 09/31/17 | 100% | 7911686.98 |  |  | 264-009-14-10-e14-475
75 |  |  | Construction & Heavy Equipment
76 | per saaob | 2014 |  | Major Repair - Construction & Heavy Equipment | Motorpool Area | 10000000 | 2014-06-11 |  | 22.43% | 2242763
77 |  |  | Roads, Highways & Bridges |  |  | 0
78 | 10710020-001-0039 | 2014 |  | Road Surfacing from Sitio Binanigan to Sitio Guintana-an, Brgy. Tayawan, Phase 1 | Tayawan | 500000 | 2016-03-16 |  | 75% | 173183.68 |  | Temporary stopped; (need to look other quarry source, road not yet passable, no Backhoe available) | 266-001-1603-G0360
79 |  |  | Artesian Wells, Reservoir, Pumping Stations & Conduits |  |  | 0
80 | *10710020-002-0025 | 2014 |  | Construction of Water System-Crusher Kalumboyan |  | 212800 | 2015-06-01 | 2016-06-30 | 100% | 182355.32 |  |  | 269-001-14-07-G0036
81 |  |  | Other Structures
82 | 10710030-030-0058 | 2015 |  | Construction of Evacuation Center, Brgy. San Miguel | San Miguel | 800000 | 2016-02-01 |  | 95% | 602620.16 |  | Temporary stopped | 264-009-1510-G0520
83 | *10710030-030-0059 | 2015 |  | Construction of Portable Toilet | Bayawan City | 770000 | 2016-01-15 | 2018-03-31 | 100% | 542396.04 |  |  | 264-009-1601-G0524
84 | 10710010-002-0003 | 2015 |  | Const. of GK Village Perimeter Fence | Villareal | 2000000 | 2016-10-01 | 2019-11-30 | 94% | 1716184.88 |  |  | 264-009-1601-G0526 | target date of completion
85 |  |  | Construction & Heavy Equipment
86 | no obligation | 2015 |  | Purchase of Various Heavy Equipment |  | 3476406.99 |  |  |  | 0
87 |  |  | Roads, Highways & Bridges
88 | *10710020-001-0019 | 2015 |  | Reblocking of Concrete Pavement at Villareal-Cansumalig-San Isidro FMR, Phase 2 | Bayawan City | 500000 | 2015-06-01 | 2015-06-30 | 100% | 457677.34 |  |  | 266-001-1504-G0335
89 | 10710020-001-0013 | 2015 |  | Construction of Gomez Street Extension | Bayawan City | 3000000 | 2016-03-16 | 2018-06-30 | 100% | 1148517.88 |  |  | 266-001-1502-g0319
90 | *10710020-001-0016 | 2015 |  | Concreting of Road Shoulder of National Highway Fronting BNHS, | Bayawan City | 3000000 | 2016-02-09 | 2017-01-15 | 100% | 2935348.39 |  |  | 266-001-1502-g0326
91 | *10710020-001-0017 | 2015 |  | Construction of Access Road at Bayawan East, | Bayawan City | 2053659.56 | 2015-04-01 | 2016-03-15 | 100% | 1967337.73 |  |  | 266-001-1504-g0330
92 | 10710020-001-0040 | 2015 |  | Road Surfacing of Sitio Hag-um and Sitio Mambunot, Brgy. Tayawan, Phase 1 | Tayawan, Bayawan City | 500000 | 2016-03-16 |  | 30% | 189523.51 |  | Temporary stopped; (need to look other quarry source, road not yet passable, no Backhoe available) | 266-001-1603-G0361
93 | *10710020-001-0022 | 2015 |  | Rehabilitation of FMR at Sitio Tubod, Brgy. Tabuan | Tubod, Tabuan | 100000 | 2015-10-01 | 2016-03-15 | 100% | 56654.12 |  |  | 266-001-1509-G0343
94 | *10710020-001-0021 | 2015 |  | Rehabilitation of Pulangyuta-Lapay FMR | Bayawan City | 2014400 | 2015-09-16 | 2017-03-31 | 100% | 2008455.26 |  |  | 266-001-1509-g0338
95 |  |  | Artesian Wells, Reservoir, Pumping Stations & Conduits
96 | 10710020-002-0037 | 2015 |  | Water System Development @ Sitio Camague to Cabiguhan, Brgy Banaybanay | Banaybanay | 303389.8 | 2017-02-16 |  | 50% | 206913.03 |  | Pending: Declared site has no water source; Materials completely delivered | 269-001-1603-G0039
97 |  |  | Hospital & Health Centers
98 | 10710030-003-0001 | 2016 |  | Rehabilitation of Health Center & Const. of Lying-in Facility, Brgy. Poblacion, Phase 2 | Poblacion | 500000 | 2016-09-16 | 2017-06-30 | 100% | 320188.77 |  |  | 264-004-1603-G0031
99 |  |  | Electrification, Power & Energy Structures
100 | *10710030-006-0010 | 2016 |  | Installation of Electrical System (Sitio Napit-an, Brgy Maninihon & Zamora Streets, Brgy. Suba) - | Suba | 1500000 | 2016-11-15 | 2018-08-31 | 100% | 1439250.62 |  |  | 264-005-1611-G0058
101 | *264-005-1606-G0056 | 2016 |  | Purchase of Transforments & Primary Metering @ New Gov't. Center | Banga | 2545000 | 2016-11-24 | 2016-11-29 | 100% | 2540000
102 | *10710030-006-0009 | 2016 |  | Installation of Secondary Line Feeder @ New Gov't. Center | Banga | 800000 | 2016-02-13 | 2018-07-15 | 100% | 669519.56 |  |  | 264-005-1606-G0055
103 | 10710020-001-0044 | 2016 |  | Establishment of Street Lighting Facilities - 2016 | Var. Brgys. | 400000 |  |  |  | 314630 |  |  | 266-004-1603-g0055
104 | *10710020-001-0065 | 2016 |  | Installation of Street Lightings at Brgy Proper, Villasol | Villasol | 140000 | 2017-10-02 | 2017-10-30 | 100% | 132852.6 |  |  | 266-004-1607-G0056
105 |  |  | Other Structures
106 | 10710030-002-0010 | 2016 |  | Construction of Day Care Centers in Nangka and Napit-an/Rehabilitation of Day Care Centers in Minaba, Narra, Purok 4 Tayawan | Nangka, Napit-an, Minaba, Narra, Tayawan | 2000000 | 2017-06-01 |  | 51.7% | 1428868.03 |  | Pending: No lot available | 264-009-1607-G0553
107 | *10710030-030-0079 | 2016 |  | Improvement of CICL Center Faciltities | Banga | 975000 | 2017-11-16 | 2019-03-31 | 100% | 764122.65 |  |  | 264-009-1607-g0548
108 | *10710030-030-0081 | 2016 |  | Completion of Paglaum Center at Cabcabon | Cabcabon | 500000 | 2016-10-16 | 2018-05-31 | 100% | 352817.03 |  |  | 264-009-1607-g0550
109 | *10710030-030-0069 | 2016 |  | Completion of Women's Multi-purpose Center | Boyco | 1000000 | 2016-12-01 | 2018-11-30 | 100% | 783751.69 |  |  | 264-009-1603-G0533
110 | 10710030-030-0078 | 2016 |  | Construction of Women's Detention Cell | Banga | 400000 | 2019-07-29 | 2019-10-30 |  | 211222.56 |  |  | 264-009-1607-g0547
111 | 10710030-030-0067 | 2016 |  | Construction of Women's Facilities in Evacuation Center | Var. Brgys | 200000 | 2019-07-22 | 2019-08-22 |  | 158078.43 |  |  | 264-009-1603-G0538
112 | *10710030-002-0009 | 2016 |  | Construction of Day Care Center at Brgy. Proper, Brgy,. San Miguel | San Miguel | 500000 | 2016-08-16 | 2017-05-31 | 100% | 440367.22 |  |  | 264-002-1603-G0078
113 | 10710030-030-0073 | 2016 |  | Const. of Bleachers & CRs @ Existing Gyms for evacuation (Tinago, Boyco, Suba,Poblacion, Banga, Malabugas, Villareal, BNHS) | Various Brgys | 6000000 | 2019-07-30 | 07/31/19 | 100% | 5105050.96 |  |  | 264-009-1603-G0540
114 |  |  |  | a. Tinago |  |  |  |  | 100%
115 |  |  |  | b. Boyco |  |  |  |  | 100%
116 |  |  |  | c. Suba |  |  |  |  | 100%
117 |  |  |  | d. Poblacion |  |  |  |  | 100%
118 |  |  |  | e. Banga |  |  |  |  | 100%
119 |  |  |  | f. Malabugas |  |  |  |  | 100%
120 |  |  |  | g.Villareal |  |  |  |  | 100%
121 |  |  |  | h. BNHS |  |  |  |  | 100%
122 | 10710030-030-0076 | 2016 |  | Improvement of Agricultural Dev. Ctr. (ADC), Cansumalig, Phase 2 | Cansumalig | 400000 | 2017-06-01 | 2018-06-30 | 100% | 348687.17 |  |  | 264-009-1606-G0544
123 | *10710030-030-0074 | 2016 |  | Const. of Comfort Rooms in 13 Evacuation Ctrs. | Var Brgys | 1054174.83 | 2019-04-30 | 2018-02-28 | 100% | 1056488.39 |  |  | 264-009-1604-G0541
124 |  |  |  | a. Banga Central School |  |  |  |  | 100%
125 |  |  |  | b. BCSTEC Elementary & Highschool |  |  |  |  | 100%
126 |  |  |  | c. Malabugas Highschool |  |  |  |  | 100%
127 |  |  |  | d. Nangka Elementary School |  |  |  |  | 100%
128 |  |  |  | e. Guisocon Elementary School |  |  |  |  | 100%
129 |  |  |  | f. Atilano Cabangal Memorial Highschool |  |  |  |  | 100%
130 |  |  |  | g. Tavera Elementary School |  |  |  |  | 100%
131 |  |  |  | h. Dean Felix Gaudiel Memorial Elementary School |  |  |  |  | 100%
132 |  |  |  | i. H. Bido Jordan Elementary School |  |  |  |  | 100%
133 |  |  |  | j. Bayawan National Highschool |  |  |  |  | 100%
134 |  |  |  | k. Maninihon Elementary & Highschool |  |  |  |  | 100%
135 |  |  |  | l. H. Bido Jordan Highschool School |  |  |  |  | 100%
136 |  |  |  | m. SLGTMES |  |  |  |  | 100%
137 | *10710030-030-0072 | 2016 |  | Improvement of Covered Court/Evacuation Ctr., Bry. Banga | Banga | 500000 | 2016-10-16 | 2017-06-30 | 100% | 435324.88 |  |  | 264-009-1603-G0536
138 | 10710030-030-0071 | 2016 |  | Const. of Evacuation Ctr., Brgy. San Roque | San Roque | 500000 | 2017-06-16 | 2019-06-30 | 100% | 361521.48 |  |  | 264-009-1603-G0535
139 | *10710030-030-0070 | 2016 |  | Const. of Covered Court/Evacuation Ctr., Bry. Suba | Suba | 500000 | 2016-12-16 | 2017-05-31 | 100% | 454964.53 |  |  | 264-009-1603-G0534
140 | *10710030-030-0082 | 2016 |  | Const. of Multi-Purpose Bldg. for Evacuation Ctr., Brgy Villareal | Villareal | 500000 | 2017-05-01 | 2018-11-30 | 100% | 431575.23 |  |  | 264-009-1608-G0557
141 | *10710020-002-0043 | 2016 |  | Const. of Rain Collector at Brgy. San Isidro | San Isidro | 150000 | 2017-12-16 | 2018-05-31 | 100% | 137210.67
142 | 0 | 2016 |  | Fish Farm Development Program |  | 900000 |  |  |  | 0
143 | *10710030-030-0084 | 2016 |  | Establishment of Youth Development Center |  | 5000000 | 2017-06-15 | 2018-09-01 | 100% | 4000896.6 |  |  | 264-009-1701-G0560
144 | 10710030-003-0009 | 2016 |  | Renovation of the Integrated Business Center(IBC) Building | Villareal | 8000000 | 2018-04-27 |  | 96% | 6223227.42 |  | Recommended for termination of contract
145 | 10710030-030-0086 | 2016 |  | Pilot Livestock Silage Stocking Project |  | 2000000 |  |  |  | 1391084 |  |  | 264-009-1703-G0564
146 | 0 | 2016 |  | LGU Counterpart for the Construction of Sports Complex |  | 15000000 |  |  |  | 0
147 | *10710030-004-0005 | 2016 |  | Establishment of Bayawan Farmers' Market in Dumaguete |  | 5000000 | 2018-02-05 | 2018-10-31 | 100% | 4994489.13 |  |  | 264-009-1708-g0577
148 |  |  | Agricultural, Fishery & Forestry Equipment
149 | per saaob | 2016 |  | Purchase of Agricultural & Forestry Equipment and Implements |  | 8800000 | 2018-01-02 | 2018-12-31 | 100% | 8400000
150 |  |  | Technical & Scientific equipment
151 | no obligation |  |  | Purchase of Digital Weighing Scale |  | 250000 |  |  |  | 0
152 |  |  | Roads,Highways & Bridges
153 | *10710020-001-0031 | 2016 |  | Improvement of Nangka-Narra FMR | Bayawan City | 5000000 | 2016-06-16 | 2017-08-31 | 100% | 4454951.93 |  |  | 266-001-1601-G0353
154 | *10710020-001-0041 | 2016 |  | Improvement of Maninihon-Cansumalig-San Isidro FMR | Bayawan City | 5000000 | 2016-06-16 | 2017-09-15 | 100% | 4802539.95 |  |  | 266-001-1603-G0362
155 | *10710020-001-0053 | 2016 |  | Reblocking of Concrete Pavement at Villareal-Cansumalig-San Isidro FMR, Phase 3 | Bayawan City | 500000 | 2017-03-01 | 2017-07-31 | 100% | 470136.11 |  |  | 266-001-1606-G0374
156 | *10710020-001-0043 | 2016 |  | Reblocking of Concrete Pavement Nangka- Narra FMR | Bayawan City | 500000 | 2017-02-16 | 2017-06-30 | 100% | 472475.09 |  |  | 266-001-1603-G0364
157 | *10710020-001-0062 | 2016 |  | Reblocking of Concrete Pavement with Slope Protection at Malabugas-San Roque Route | Bayawan City | 500000 | 2017-05-01 | 2017-10-31 | 100% | 459598.82 |  |  | 266-001-1607-G0383
158 | *10710020-001-0052 | 2016 |  | Reblocking of Concrete Pavement with Slope Protection at Tabuan-Banay-banay Route | Bayawan City | 500000 | 2017-05-01 | 2017-10-31 | 100% | 463537.29 |  |  | 266-001-1606-G0373
159 | *10710020-001-0049 | 2016 |  | Concreting of Road Approaching Upper Baican Box Culvert with Slope Protection | Bugay | 1000000 | 2016-10-16 | 2017-06-30 | 100% | 974648.99 |  |  | 266-001-1606-G0370
160 | *10710020-001-0048 | 2016 |  | Concreting of Road Approaching Nayabaan Box Culvert with Slope Protection | Bugay | 1000000 | 2016-09-16 | 2017-07-15 | 100% | 908111.85 |  |  | 266-001-1606-G0369
161 | *10710020-001-0063 | 2016 |  | Concreting of Road Approaching Cagayon Box Culvert with Slope Protection | Banaybanay | 1000000 | 2017-01-01 | 2017-10-31 | 100% | 905886.26 |  |  | 266-001-1607-G0384
162 | *10710020-001-0061 | 2016 |  | Concreting of Road Approaching Cabigohan Box Culvert with Slope Protection | Dawis | 1000000 | 2017-05-01 | 2017-10-15 | 100% | 930476.68 |  |  | 266-001-1607-G0382
163 | 10710020-030-0001 | 2016 |  | Installation of Guardrails at Kalumboyan Bridge Approaches | Kalumboyan | 2000000 | 2017-08-01 | 2018-06-30 | 100% | 1737337.87 |  |  | 266-003-1608-G0022
164 | *10710020-006-0008 | 2016 |  | Const. Tiki Footbridge, Phase 2 Brgy. Kalumboyan | Kalumboyan | 700000 | 2017-04-16 | 2018-02-28 | 100% | 685551.67 |  |  | 266-003-1602-G0018
165 | 10710020-001-0025 | 2016 |  | Const. of Urban Roads (Gomez to Kabankalan Road) | City Proper | 8000000 | 2017-06-01 | 2018-12-31 | 100% | 5854241.79 |  |  | 266-001-1512-G0347
166 | 10710020-001-0032 | 2016 |  | Rehab of FMR at So. Pag-awitan, Ali-is | Ali-is | 500000 | 2018-05-16 | 2018-12-31 | 100% | 296371.2 |  |  | 0
167 | 10710020-001-0036 | 2016 |  | Road Opening at Sitio Palasanon, Cansinacao, Guintalasan Mangharaw & Guinhamogan, Brgy Cansumalig | Cansumalig | 500000 | 2018-02-16 |  | 50% | 114051.44 |  | Temporary Stopped: Road not passable anymore & No Available Heavy Equipment | 266-001-1602-G0358
168 | 10710020-001-0033 | 2016 |  | Road Rehabilitation at so. Camague, Brgy Dawis | Villareal | 500000 |  |  |  | 82591.46 |  | Pending: No available H.E. and Road not yet passable | 266-001-1602-G0355
169 | 10710020-001-0035 | 2016 |  | Road surfacing at Manduao-Bucao, Brgy Manduao | Manduao | 500000 | 2016-03-16 |  | 5% | 167283.93 |  | Temporarily stopped, road not yet passable. | 266-001-1602-G0357
170 | *10710020-006-0009 | 2016 |  | Const. of Steel Bridge Connecting So. Malampa to So. Tab-ang, Brgy Pagatban | Pagatban | 500000 | 2017-06-16 | 2018-01-31 | 100% | 360828.1 |  |  | 266-003-1607-G0020
171 | *10710020-001-0060 | 2016 |  | Const. or Road from Gov't. Ctr. To sitio Buli-buli/Phase 2 | Banga | 2000000 | 2017-01-01 | 11-31-17 | 100% | 1670978.21 |  |  | 266-001-1607-G0381
172 | 10710020-001-0064 | 2016 |  | Improvement of Road Along Bayawan CIP Main Canal | Bayawan City | 190000 |  |  |  | 90000 |  |  | 266-001-1607-G0385 | with expense no date and completion
173 | *10710020-006-0010 | 2016 |  | Const. of Footbridge at Sitio Lower Baican, Brgy Villasol | Baican, Villasol | 220000 | 2018-02-01 | 2018-06-30 | 100% | 189061.91 |  |  | 266-003-1607-G0021
174 |  |  | Artesian Wells, Reservoir, Pumping Stations & Conduits
175 | 10710020-002-0041 | 2016 |  | Rehabilitation of San Isidro Water Supply System | Villareal | 350000 |  |  |  | 189138.38 |  |  | 269-001-1612-g0043 | with expense no date and completion
176 | *10710030-030-0085 | 2016 |  | Const. of Water Tank & Pipeline at Tabuan Brgy Proper | Tabuan | 500000 | 2017-05-01 | 2018-05-31 | 99.5% | 424113.31 |  |  | 264-009-1702-G0561
177 | 10710020-002-0039 | 2016 |  | Construction of Tayawan Water System | Tayawan | 300000 | 2017-06-01 |  | 95% | 255424.64 |  | Temporary Stopped: RCPC for water source cannot be delivered on site road not passable | 269-001-1608-G0041
178 |  |  | Irrigation, Canals & Laterals
179 | *10710020-003-0004 | 2016 |  | Rehabilitation of Bayawan Communal Irrigation System | Pagatban | 500000 | 2016-08-16 | 2016-12-31 | 100% | 458455.32 |  |  | 270-001-1607-G0015
180 | 10710020-003-0005 | 2016 |  | Const. of Small Scale Irrigation Project at Sitio Magsulay | Narra | 1000000 |  |  |  | 959792.77 |  |  | 270-001-1701-G0017 | with expense no date and completion
181 |  |  | Flood Controls
182 | *10710020-007-0010 | 2016 |  | Construction of Drainage City Streets - Zamora, Teologio Sts, Subd Area | Zamora, Teologio & Subd Area | 3000000 | 2017-01-01 | 2017-09-15 | 100% | 2461029.39 |  |  | 271-002-1607-G0038
183 | *10710020-005-0008 | 2016 |  | Rehabilitation of River Bank Protection at Sitio Ebuan | Nangka | 2000000 | 2017-03-16 | 2018-12-31 | 100% | 1451778.7 |  |  | 272-002-1702-G0033
184 | *10710020-004-0011 | 2016 |  | Const. of Box Culvert in So. Candalaga, Brgy Nangka | Nangka | 500000 | 2017-03-16 | 2017-06-30 | 100% | 381385.53 |  |  | 271-001-1607-G0052
185 | *10710020-002-0042 | 2016 |  | Construction of Spring Box at Upper Talao, San Isidro | San Isidro | 500000 | 2018-04-15 | 2019-03-31 | 100% | 253922.18 |  |  | 269-002-1607-G0032
186 | *10710020-004-0016 | 2016 |  | Const. of 1 unit Single Box Culvert Phase 1 at So, Magsakang, brgy Tayawan | Tayawan | 500000 | 2018-01-16 | 2018-05-15 | 100% | 410379.87 |  |  | 271-001-1706-G0057
187 | *10710020-007-0011 | 2016 |  | Const. of Drainage Canal at along Burgos St. & AlongBollos St. Brgy Ubos | Ubos | 500000 | 2017-02-01 | 2017-06-30 | 100% | 442668.24 |  |  | 271-002-1607-G0036
188 |  |  | Waterways, Aqueducts, Seawalls, RiverWalls & Others
189 | *10710020-005-0007 | 2016 |  | Rehabilitation of Riverbank @ Brgy. Nangka | Nangka | 1000000 | 2018-05-16 | 2018-12-31 | 100% | 1013905.35 |  |  | 272-002-1609-G0032
105 |  |  | Other Structures
190 |  | 2017 |  | Establishment of Montessori-Type Early Child Care Development Centers | Various Brgys | [7 empty] | 264-002-1711-g0081/G0082
191 | 10710030-002-0011 | 2017 |  | a. Establishment of Montessori-Type Early Child Care Development Centers Phase 2 | Boyco | 2289000 | 2018-12-16 | 2019-12-15 | 98% | 1062624.16
192 | 10710030-002-0014 | 2017 |  | b. Establishment of Montessori-Type Early Child Care Development Centers | Poblacion | 1211000 | 2018-01-01 | 2018-11-30 | 100% | 699088.03 |  |  | 264-002-1711-g0081/G0082
193 | 10710010-001-0003 | 2017 |  | Development of Danapa Eco Park | Nangka | 18000000 | 2016-06-12 |  | 98% | 16778685.58 |  | pending: subject for termination | 264-009-1705-G0566
194 | 10710020-030-0003 | 2017 |  | Development of Narra Water Park | Narra | 16000000 | 2017-09-12 | 2018-09-30 | 100% | 15993892.48 |  |  | 269-002-1704-G0035
195 | 10710020-009-0003 | 2017 |  | Development of Tabuan People's Park | Tabuan | 2000000 |  |  |  | 1396904.13 |  |  | 0
196 | *10710030-030-0128/0129/0130 | 2017 |  | Construction of Coastal Park Comfort Rooms | Coastal Road | 4500000 | 2018-02-15 | 2018-05-27 | 100% | 4497336 |  |  | 264-009-1710-G0592/G0593/g0594
197 | 264-009-1711-G0600 | 2017 |  | Construction of Children's Playground with Facilities, Ali-is | Ali-is | 500000 |  |  |  | 0
198 | 10710030-003-0016 | 2017 |  | Improvement of Barangay Health Center Lying-In Clinic, Brgy. Malabugas | Malabugas | 678571.43 |  |  |  | 0 |  |  | 0
199 | 264-004-1711-G0033 | 2017 |  | Improvement of Barangay Health Center & Lying-in Clinic, Brgy. Manduao | Manduao | 100000 |  |  |  | 0
200 | 10710030-030-0132 | 2017 |  | Construction of Covered Court and Evacuation Center, Brgy. Pagatban | Pagatban | 1728571.43 |  |  |  | 0 |  |  | 264-009-1712-g0609
201 | 10710030-030-0135 | 2017 |  | Improvement of Evacuation Center and Multi-Purpose Building, Brgy. Poblacion | Poblacion | 878571.43 |  |  |  | 0 |  |  | 264-009-1712-g0612
202 | 10710030-002-0019 | 2017 |  | Construction of New Day Care Center at Brgy. Poblacion | Poblacion | 800000 |  |  |  | 0 |  |  | 264-002-1712-g0083
203 | 10710030-003-0015 | 2017 |  | Construction of Lying-In Clinic, Brgy. San Isidro | San Isidro | 1178571.43 | 2019-01-24 | 2019-11-30 | 98% | 590297.46 |  |  | 0 | target completion date
204 | 10710030-003-0006 | 2017 |  | Improvemen of Health Center and Lying-in Clinic, Brgy.San Roque | San Roque | 1678571.43 |  |  |  | 0 |  |  | 264-004-1712-g0035
205 | 0 | 2017 |  | Improvement of Barangay Health Center, Brgy. Tinago | Tinago | 600000 |  |  |  | 0 |  |  | 0
206 | 10710030-030-0131 | 2017 |  | Construction of Children's Playground with Facilities, Brgy. Villareal | Villareal | 500000 |  |  |  | 0 |  |  | 264-009-1712-g0608
207 | 0 | 2017 |  | Construction of Multi-Purpose Center for Senior Citizens, Brgy. Villasol | Bayawan City | 50000 |  |  |  | 0 |  |  | 0
208 | 10710030-003-0005 | 2017 |  | Improvement of Barangay Health Center, Brgy. San Jose | San Jose | 60000 |  |  |  | 0 |  |  | 264-004-1712-g0034
209 | 10710030-003-0007 | 2017 |  | Renovation of Barangay Health Center at Brgy. Tayawan | Tayawan | 150000 |  |  |  | 0 |  |  | 264-004-1712-g0036
210 | 10710030-002-0020 | 2017 |  | Renovation of Day Care Center, Brgy. Tayawan | Tayawan | 100000 |  |  |  | 0 |  |  | 264-002-1712-g0084
211 | 10710030-030-0049 | 2017 |  | Construction of Pigpens |  | 400000 |  |  |  | 0
212 | 0 | 2017 |  | Construction of 2 Units Small Scale Rubber Processing Plant with Shed |  | 300000 |  |  |  | 0 |  |  | 0
213 | budget data | 2017 |  | Purchase of Breeding Stocks | Bayawan City | 1944000
214 | 0 | 2017 |  | Improvement of Brgy. Dawis Livestock Auction Market | Dawis | 150000 |  |  |  | 0 |  |  | 0
215 | *10710030-030-0091 | 2017 |  | Fabrication of Portable Batching Plant |  | 500000 | 2017-10-16 | 2018-05-31 | 100% | 325671.05 |  |  | 264-009-1707-G0576
216 | *10710030-001-0004 | 2017 |  | Construction of CEO Multi-Purpose Building | Cabcabon | 2000000 | 2017-04-16 | 2019-04-30 | 100% | 1744342.36 |  |  | 264-009-1705-G0567
217 | 10710030-030-0088 | 2017 |  | Construction of Motorpool Building at Cabcabon | Cabcabon | 8000000 | 2017-05-16 | 2019-12-15 | 99.5% | 6067226.56 |  |  | 264-009-1706-g0569
218 | no obligation | 2017 |  | Lot Acquisition |  | 500000 |  |  |  | 0
219 | 0 | 2017 |  | Establishment of Livestock Auction Market |  | 2000000 |  |  |  | 0 |  |  | 0
220 | 0 | 2017 |  | Improvement of Public Market Water System | Bayawan City | 500000 |  |  |  | 0 |  |  | 0
221 | *10710020-001-0076 | 2017 |  | Construction of Slope Protection at Narra-Duyanduyan FMR, Sito Duyan-duyan, Brgy. Narra | Bayawan City | 1000000 | 2017-10-16 | 2018-05-31 | 100% | 895097.05 |  |  | 266-001-1708-g0396
222 | 10710020-008-0006 | 2017 |  | Flood Control Project at Brgy. Malabugas, Phase 2 | Malabugas | 1500000 | 2017-09-01 | 2018-06-30 | 100% | 1331896.08 |  |  | 271-002-1709-G0048
223 | 10710020-007-0022 | 2017 |  | Construction of Drainage at Cabugcabugan Creek, Brgy. Poblacion, Phase 4 | Poblacion | 1356746.77 | 2017-11-16 |  | 25% | 1197855.77 |  | Pending Consultation with BMAKBI and Mr. Eldie Tinapao (Vallacar) | 271-002-1711-g0050
224 | 10710020-005-0010 | 2017 |  | Construction of Riverbank Protection at Camayaan Creek,Brgy. Malabugas | Malabugas | 1000000 | 2018-01-16 | 2018-10-16 | 100% | 898258.82 |  |  | 272-002-1708-G0035
225 | no obligation | 2017 |  | Purchase of Various Agricultural Equipment | Bayawan City | 4000000
226 | 10710030-030-0101 | 2017 |  | Construction of Multi-Purpose Pavement at Brgy. Ali-is | Ali-is | 580000 | 2017-12-16 | 2018-06-30 | 100% | 549090.35 |  |  | 264-009-1708-G0587
152 |  |  | Roads,Highways & Bridges
227 | 10710020-006-0012 | 2017 |  | Construction of Flat Slab Bridge at Brgy. Proper, Banaybanay | Banaybanay | 600000 | 2018-01-16 | 2018-09-30 | 100% | 583108.44 |  |  | 266-003-1708-G0025
228 | 0 | 2017 |  | Improvement of FMR at Sitio Cangcawit, Banaybanay | Banaybanay | 1078571.43 |  |  |  | 0 |  |  | 0
229 | 10710030-030-0189 | 2017 |  | Improvement of Covered Court & Evacuation Center, Brgy. Banga | Banga | 500000 | 2019-03-16 | 2019-10-30 | 60% | 330449.03 |  |  | 0
230 | *10710020-001-0079 | 2017 |  | Improvement of FMR at Sitio Cansig-id, Brgy. Banga | Banga | 500000 | 2017-12-01 | 2018-01-31 | 100% | 455034 |  |  | 266-001-1708-g0401
231 | 0 | 2017 |  | Improvement of FMR from Brgy. Proper to Sitio Aya, Brgy. Bugay | Bugay | 839286.43 |  |  |  | 0 |  |  | 0
232 | 0 | 2017 |  | Improvement of FMR from Brgy Proper to Sitio Canlantang,Brgy. Bugay | Bugay | 839285 |  |  |  | 0 |  |  | 0
233 | 10710030-030-0090 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Guintalasan, Brgy. Cansumalig | Cansumalig | 559523.81 |  |  |  | 293822.16 |  |  | 264-009-1707-G0574
234 | *10710030-030-0093 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Guinhamogan, Brgy. Cansumalig | Cansumalig | 559523.81 | 2018-04-18 | 2018-07-31 | 100% | 519399.55 |  |  | 264-009-1708-g0579
235 | 10710030-030-0099 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Punong, Brgy. Cansumalig | Cansumalig | 559523.81 | 2018-03-16 | 2019-08-31 | 100% | 505035.42 |  |  | 264-009-1708-G0582
236 | 264-009-1711-g0597 | 2017 |  | Construction of Satellite Farmers' Market, Brgy. Dawis | Dawis | 1000000 |  |  |  | 0
237 | 264-009-1711-g0595 | 2017 |  | Improvement of Multi-Purpose Building at Brgy. Dawis | Dawis | 678571.43 |  |  |  | 0
238 | 10710020-001-0115 | 2017 |  | Improvement of FMR at Brgy. Dawis | Dawis | 150000 | 2018-06-01 | 2019-02-22 | 100% | 146687.65 |  |  | 266-001-1708-G0394
239 | 10710020-001-0081 | 2017 |  | Improvement of Road from Barangay Proper to Kalamtukan Elementary School, Brgy. Kalamtukan | Kalamtukan | 1178571.43 | 2017-10-16 | 2018-06-15 | 100% | 1083384.59 |  |  | 266-001-1708-G0405
240 | 10710030-030-0100 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Cogon, Brgy. Kalamtukan | Kalamtukan | 500000 | 2018-01-16 | 2018-06-30 | 100% | 471707.38 |  |  | 264-009-1708-g0583
241 | 0 | 2017 |  | Improvement of FMR at Brgy. Proper, Manduao | Manduao | 500000 |  |  |  | 0 |  | Road not yet passable | 0
242 | 10710020-002-0047 | 2017 |  | Construction of Water System at Proper Manduao | Manduao | 678571.43 |  | 2019-09-30 | 99.8% | 407627.54 |  |  | 269-001-1708-G0047 | Turn-over to BAWAD
243 | 10710030-030-0089 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Bocaw, Manduao | Manduao | 500000 | 2019-01-01 | 2019-07-31 | 100% | 461324.64 |  |  | 264-009-1707-G0575
244 | 10710020-002-0052 | 2017 |  | Water System Development Project at Sitio Upper Camandagan, Brgy. Maninihon | Maninihon | 1000000 |  |  |  | 647344.67 |  |  | 269-001-1711-g0052 | Turn-over to BAWAD
245 | 264-009-1712-g0606 | 2017 |  | Improvement of Multi-Purpose Gymnasium and Evacuation Center, Brgy. Maninihon | Maninihon | 678571.43 | 2019-01-25 | 2019-11-30 | 99% | 0 |  | Subject for evaluation of as built plan and estimates
246 | *10710020-001-0114 | 2017 |  | Improvement of FMR at Brgy. Minaba | Minaba | 678571.43 | 2018-05-16 | 2019-01-31 | 100% | 532636.79 |  |  | 0
247 | 10710020-001-0075 | 2017 |  | Improvement of FMR at Sitio Kasla, Brgy. Nangka | Nangka | 1000000 | 2017-12-01 | 2018-07-31 | 100% | 889470.06 |  |  | 266-001-1708-g0402
248 | 0 | 2017 |  | Establishment of Barangay Water Refilling Station, Brgy. Nangka | Nangka | 678571.43 |  |  |  | 0 |  |  | 0
249 | 10710020-001-0085 | 2017 |  | Improvement of FMR at Sitios Terong, Palongpong, Canggabi and Cadal-ugan, Brgy. Narra | Narra | 1000000 | 2018-05-16 |  | 20% | 246842 |  | Temporarily stopped: Road not yet passable | 0
250 | 10710020-001-0072 | 2017 |  | Road Opening at Brgy. Narra Proper | Narra | 678571.43 | 2018-06-16 | 2019-12-31 | 80% | 301799.59 |  | Pending: No Heavy Equipment available | 266-001-1708-g0398
251 | *10710020-002-0053 | 2017 |  | Installation of Water System at Brgy. Poblacion | Poblacion | 70000 | 2018-03-01 | 2018-03-15 | 100% | 28933.33 |  |  | 0
252 | 0 | 2017 |  | Construction of Barangay Public Market, Brgy. San Jose | San Jose | 1678571.43 |  |  |  | 0 |  |  | 0
253 | 0 | 2017 |  | Construction of Cloning Chamber at San Roque BADC | San Roque | 50000 |  |  |  | 0 |  |  | 0
254 | 10710030-030-0134 | 2017 |  | Improvement of Covered Court for Evacuation Center, Brgy Suba | Suba | 1678571.43 | [6 empty] | 264-009-1712-g0611
255 | 10710020-006-0013 | 2017 |  | Improvement of Flat Slab Bridge at Sitio Magsakang, Brgy Tayawan | Tayawan | 500000 | 2019-02-16 | 2019-10-31 | 99% | 321785.57 |  |  | 266-003-1704-G0023
256 | 10710020-001-0074 | 2017 |  | Improvement of Binanigan-Guintanaan FMR, Tayawan | Tayawan | 678571.43 |  |  |  | 24776.18 |  |  | 266-001-1708-g0403
257 | 10710020-001-0073 | 2017 |  | Improvement of Binanigan-Napo FMR, Brgy. Tayawan | Tayawan | 500000 |  |  |  | 205271.33 |  |  | 266-001-1708-g0404
258 | 264-009-1711-g0602 | 2017 |  | Improvement of Multi-Purpose Building, Brgy. Tinago | Tinago | 1128571.43 |  |  |  | 168535.72
259 | 10710020-007-0017 | 2017 |  | Concreting of Drainage Canal Cover Along National Highway, Brgy. Villareal | Villareal | 678571.43 | 2017-11-16 | 2019-12-31 | 90% | 491510.65 |  | Pending: transfer of location, Barangay & SP resolution on process | 271-002-1708-G0044
260 | 10710020-006-0014 | 2017 |  | Construction of Flat Slab Bridge Connecting Barangay Proper to Purok Malinong, Brgy. Villasol | Villasol | 1078571.43 | 2018-02-15 | 2019-04-30 | 100% | 1023638.83 |  |  | 266-003-1708-G0026
261 | *10710030-030-0098 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Manghakayhakay, Brgy. Villasol | Villasol | 600000 | 2017-12-16 | 2018-03-31 | 100% | 560025.05 |  |  | 264-009-1708-G0586
262 | 10710020-002-0050 | 2017 |  | Improvement/Rehabilitation of Water Systems for Various Barangays | Various Brgys | 934500 |  |  |  | 575402.78 |  |  | 269-001-1711-g0050 | Turn-over to BAWAD
263 | 10710030-030-0195 | 2017 |  | Installation of Water Refilling Stations at Various Barangays | Various Brgys | 2200000 | 2019-01-21 |  | 48% | 1054599.9 |  | Pending: Building is not yet ready
264 | 10710030-030-0094 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Bolo, Brgy. Villasol | Villasol | 600000 | 2018-02-16 | 2018-06-30 | 100% | 563177.77 |  |  | 264-009-1708-g0580
265 | 264-009-1712-g0605 | 2017 |  | Construction of Multi-Purpose Building in Barangay Tayawan | Tayawan | 900000
266 | 0 | 2017 |  | Construction of Multi-Purpose Building in Barangay San Jose | San Jose | 900000 |  |  |  | 0 |  |  | 0
267 | *10710030-006-0018 | 2017 |  | Electrification Project for Various Barangays | Various Brgys | 10000 | 2018-06-01 | 2018-06-15 | 100% | 9060.49 |  |  | 0
268 | *10710020-007-0018 | 2017 |  | Construction of Drainage Canal at Cansumalig High School | Cansumalig | 150000 | 2017-12-16 | 2018-03-30 | 100% | 126833.17 |  |  | 271-002-1708-G0045
269 | 10710010-002-0004 | 2017 |  | Construction of Perimeter Fence of Multi-Purpose Building, Brgy. San Miguel | San Miguel | 100000 | [6 empty] | 264-009-1712-g0610
270 | 10710020-002-0086 | 2017 |  | Improvement of Water Systems of Guintanaan Tayawan | Tayawan | 100000 |  |  |  | 3058 |  |  | 0 | Turn-over to BAWAD
271 | 10710020-002-0046 | 2017 |  | Improvement of Water Systems at Manduao | Manduao | 110000 |  |  |  | 16811.66 |  |  | 269-001-1708-g0046 | Turn-over to BAWAD
272 | 0 | 2017 |  | Installation of Solar-Driven Water System for Catumbalan, Minaba | Minaba | 100000 |  |  |  | 0 |  |  | 0 | Turn-over to BAWAD
273 | 10710030-006-0015 | 2017 |  | Installation of Solar-Driven Water System for Oban-Oban, Brgy. Kalumboyan | Kalumboyan | 50000 |  |  |  | 13835.24 |  |  | 264-005-1711-g0062 | Turn-over to BAWAD
274 | 0 | 2017 |  | Installation of Solar-Driven Water Systems for Napo, Brgy. Tayawan | Tayawan | 50000 |  |  |  | 0 |  |  | 0 | Turn-over to BAWAD
275 | 0 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Upper Manlubid, Ali-is | Ali-is | 50000 |  |  |  | 0 |  |  | 0
276 | *10710030-030-0095 | 2017 |  | Construction of Multi-Purpose Pavement at Inner Canabuan, Minaba | Minaba | 300000 | 2018-02-16 | 2018-06-30 | 100% | 286328.7 |  |  | 264-009-1708-G0581
277 | 269-001-1712-g0052 | 2017 |  | Improvement of Water System at Sitio Pag-awitan, Brgy. Ali-is | Ali-is | 50000 |  |  |  | 35325 |  |  |  | Turn-over to BAWAD
278 | 10710020-002-0089 | 2017 |  | Rehabilitation and Improvement of Water System at Brgy. Banaybanay | Banaybanay | 220000 |  |  |  | 111151.8 |  |  | 0 | Turn-over to BAWAD
279 | 10710030-004-0004 | 2017 |  | Improvement of Barangay Public Market, Brgy. Malabugas | Malabugas | 50000 |  |  |  | 0 |  |  | 264-003-1712-g0022
280 | 10710030-006-0016 | 2017 |  | Installation of Electrical System in Sitio Buli-buli, Brgy. Banga | Banga | 60000 | 2019-02-01 | 2019-02-28 | 100% | 43514.9 |  |  | 264-005-1711-g0063
281 | 0 | 2017 |  | Installation of Electrical System in Brgy. Kalamtukan | Kalamtukan | 60000 |  |  |  | 60000 |  |  | 0
282 | 10710030-006-0014 | 2017 |  | Installation of Electrical System in Brgy. Kalumboyan | Kalumboyan | 70000 | 2019-06-16 | 2019-07-31 | 100% | 54252.49 |  |  | 264-005-1708-G0061
283 | 269-001-1801-g0057 | 2017 |  | Improvement of Water System, Brgy. San Roque | San Roque | 70000 |  |  |  | 47394 |  |  |  | Turn-over to BAWAD
284 | *10710020-002-0054 | 2017 |  | Improvement of Water System, Brgy. Ubos | Ubos | 145000 | 2018-06-01 | 2018-06-15 | 100% | 136216.2 |  |  | 0
285 | 0 | 2017 |  | Improvement of Water System at Brgy. Villasol | Villasol | 70000 |  |  |  | 62346 |  |  | 0 | Turn-over to BAWAD
286 | 10710030-030-0096 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Ponong, Brgy. Villasol | Villasol | 100000 |  |  |  | 62715.89 |  | Pending: Road not yet passable | 264-009-1708-G0584
287 | *10710030-006-0012 | 2017 |  | Installation of Electrical System at Sitio Malampa, Brgy. Pagatban | Pagatban | 50000 | 2018-06-01 | 2018-06-30 | 100% | 44857.31 |  |  | 264-005-1708-G0059
288 | 0 | 2017 |  | Improvement of FMR at Brgy. Banaybanay | Banaybanay | 100000 |  |  |  | 0 |  |  | 0
289 | *10710030-006-0013 | 2017 |  | Installation of Electrical System in Brgy. Malabugas | Malabugas | 50000 | 2018-03-16 | 2018-04-30 | 100% | 46024.73 |  |  | 264-005-1708-G0060
290 | 10710020-002-0051 | 2017 |  | Improvement of Canabuan Water System, Brgy. Minaba | Minaba | 200000 |  |  |  | 62827.91 |  |  | 269-001-1711-g0051
291 | *10710020-001-0080 | 2017 |  | Slope Protection at Barangay Proper, San Isidro | San Isidro | 50000 | 2017-11-16 | 2018-01-31 | 100% | 48807.67 |  |  | 266-001-1708-G0395
292 | 264-009-1711-g0596 | 2017 |  | Improvement of Barangay Multi-Purpose Hall, Brgy. Ali-is | Ali-is | 200000 |  |  |  | 0
293 | 10710030-030-0097 | 2017 |  | Construction of Multi-Purpose Pavement at Purok 2, Brgy. Kalamtukan | Kalamtukan | 250000 | 2018-01-16 | 2018-06-30 | 100% | 224233.82 |  |  | 264-009-1708-G0585
294 | *10710020-001-0071 | 2017 |  | Installation of Street Lights at Purok 4, Cansilong, Brgy. Malabugas | Malabugas | 100000 | 2018-03-16 | 2018-05-31 | 100% | 90521.66 |  |  | 266-004-1708-G0057
295 | 10710020-001-0078 | 2017 |  | Improvement of FMR at Sitio Napit-an, Brgy. Maninihon | Maninihon | 220000 | 2018-04-01 | 2018-07-31 | 100% | 189414.53 |  |  | 266-001-1708-g0400
296 | 0 | 2017 |  | Improvement of Water System, Brgy. Minaba | Minaba | 110000 |  |  |  | 93457 |  |  | 0
297 | 10710020-001-0082 | 2017 |  | Improvement of FMR at Sitio Ondol, Brgy. Nangka | Nangka | 100000 | 2018-04-01 | 2018-08-31 | 100% | 95011 |  |  | 266-001-1709-G0406
298 | 0 | 2017 |  | Installation of Electrical System for Purok Ipil-Ipil, Brgy. San Roque | San Roque | 200000 |  |  |  | 0 |  |  | 0
299 | *10710020-001-0077 | 2017 |  | Road Improvement at Brgy. Ubos | Ubos | 170000 | 2018-01-01 | 2018-02-15 | 100% | 148018.03 |  |  | 266-001-1708-g0397
300 | *10710020-030-0002 | 2017 |  | Construction of Pathway to Banay-Banay Proper | Banay-Banay | 100000 | 2017-10-16 | 2018-02-28 | 100% | 89325.07 |  |  | 266-001-1708-g0399
301 | 0 | 2017 |  | Construction of Alternative Learning System (ALS) Building, Brgy. Kalumboyan | Kalumboyan | 200000 |  |  |  | 0 |  |  | 0
302 | 10710020-001-0084 | 2017 |  | Road Opening from National Highway to Purok 1 Pasil, Brgy. Malabugas | Malabugas | 150000 |  |  |  | 70424.49 |  | No ROW | 266-001-1711-g0409
303 | 10710020-002-0048 | 2017 |  | Installation of Deep Well at Atilano Cabangal High School, Brgy. Nangka | Nangka | 250000 |  |  |  | 10606.87 |  | Pending: re-PR magsaysay type deepwell not available anymore in the market | 269-001-1707-g0045
304 | 10710020-002-0081 | 2017 |  | Installation of Water System at Brgy. Pagatban | Pagatban | 50000 | 2018-03-16 | 2019-06-30 | 100% | 41977.04 |  |  | 269-001-1801-g0058
305 | 10710020-001-0083 | 2017 |  | Improvement of FMR at Sitio San Ramon, Brgy. Poblacion | Poblacion | 150000 | 2018-04-01 | 2018-08-31 | 100% | 143423.48 |  |  | 266-001-1709-G0407
306 | *10710020-002-0045 | 2017 |  | Improvement of Water System at Purok Dol-Dol, Brgy. San Roque | San Roque | 100000 | 2017-11-16 | 2018-01-31 | 100% | 69781.89 |  |  | 269-001-1707-g0044
307 | *10710020-007-0016 | 2017 |  | Construction of Concrete Covered Canals, Brgy. Tinago | Tinago | 50000 | 2017-10-01 | 2017-10-31 | 100% | 46908.05 |  |  | 271-002-1708-G0043
308 | *10710020-007-0019 | 2017 |  | Construction of Concrete Covered Canals, Brgy. Ubos | Ubos | 100000 | 2017-10-16 | 2017-11-30 | 100% | 84467.6 |  |  | 271-002-1708-G0046
309 | 264-009-1712-g0607 | 2017 |  | Improvement of Multi-Purpose Gym & Evacuation Center, Brgy. San Isidro | San Isidro | 495000 |  |  |  | 0
310 | *10710030-030-0092 | 2017 |  | Construction of Multi-Purpose Pavement, Brgy. Dawis | Dawis | 340000 | 2017-11-01 | 2018-02-28 | 100% | 326849.92 |  |  | 264-009-1708-g0578
311 | *10710020-007-0015 | 2017 |  | Construction of Concrete Covered Canal, Brgy. Suba | Suba | 400000 | 2017-08-16 | 2018-01-31 | 100% | 360021.69 |  |  | 271-002-1708-G0042
312 | 264-009-1712-g0604 | 2017 |  | Construction of Multi-Purpose Building at Relocation Site, Brgy. San Miguel | San Miguel | 500000
313 | 10710020-001-0070 | 2017 |  | Rehabilitation of Farm to Market Road from Sitio Bosque to Tavera, Barangay Nangka | Nangka | 1000000 |  |  |  | 439057.6 |  |  | 266-001-1706-g0393
314 | 10710030-030-0193 | 2017 |  | Construction of CICL at BADC Magsulay, Barangay Narra | Narra | 1000000 | 2018-09-10 |  | 37% | 1000000 |  | Temporarily stopped: Suspended due site location | 0
315 | budget data | 2017 |  | Purchase of Livestock Breeding Stocks |  | 533460 |  |  | 100% | 515555.56
316 | no obligation | 2017 |  | Purchase of Lot(Road Right of Way for Various Road Projects) |  | 2980124.07 |  |  |  | 0
317 | 0 | 2017 |  | Const. of Livelihood Center for Women at Brgy Villasol Proper |  | 100000 |  |  |  | 0 |  |  | 0
318 | 10710030-030-0104 | 2017 |  | Construction of Multi-purpose Pavement at Sitio Kaayahan (Phase 1) |  | 100000 |  |  |  | 62571.46 |  |  | 264-009-1710-G0591
319 | *10710030-030-0103 | 2017 |  | Completion of Multi-purpose Pavement at Sitio Tangistangisan |  | 330000 | 2018-02-01 | 2018-06-30 | 100% | 306358.29 |  |  | 264-009-1709-G0590
320 | *10710020-007-0020 | 2017 |  | Construction of Concrete Covered Canal at Zamora St. Brgy Suba |  | 173060.9 | 2017-08-16 | 2018-01-31 | 100% | 170642.5 |  |  | 271-002-1709-G0049
321 | *10710020-007-0021 | 2017 |  | Construction of Concrete Canal Cover Along Rizat St. Brgy Tinago |  | 1000000 | 2017-11-16 | 2018-03-31 | 100% | 678776.75 |  |  | 271-002-1709-G0047
322 |  |  | Water Supply Systems
323 | 10710020-002-0082 | 2017 |  | Development of Water System at Sitio Tavera, Nangka |  | 5700000 |  |  | 28.3% | 2367310.55 |  |  | 269-001-1709-G0049 | Turn-over to BAWAD
324 | *10710020-002-0087 | 2017 |  | Improvement of Cabatangan-Tavera Water System |  | 154784.58 | 2019-01-16 | 2019-03-31 | 100% | 133057.22
325 |  |  | Parks, Plazas & Monuments
326 | 0 | 2017 |  | Improvement of Sports Center and Children's Playground, Boulevard |  | 1000000 |  |  |  | 0 |  |  | 0
327 |  |  | School Buildings
328 | 10710030-002-0018 | 2017 |  | Establishment of Early Child Development Center |  | 2300000 | 2018-03-31 | 2019-12-15 | 99.79% | 2106628.3 |  |  | 264-009-1709-g0589/264-002-1711-g0080/81/82
330 |  |  | Other Structures
331 | no obligation | 2017 |  | Construction of Workshop Area for Bayawan City Technology & Livelihood Development Center (BCTLDC) |  | 3000000 |  |  |  | 0
332 |  | 2017 | Purchase of Workshop Tools and Equipment for BCTLDC:
333 |  | 2017 |  | Furniture & Fixtures
334 |  | 2017 |  | 3 units Exhaust Fan |  | 4500 |  |  | 100% | 4500
335 |  | 2017 |  | 3 units Industrial Fan |  | 19656 |  |  | 100% | 19656
336 |  | 2017 |  | 4 units White Board with Movable Stand |  | 11000 |  |  | 100% | 11000
337 |  | 2017 |  | 3 units White Board (4x8x3/4) |  | 9900 |  |  | 100% | 9900
338 |  | 2017 |  | Machinery |  |  |  |  | 100%
339 |  | 2017 |  | 18 units Arc Welding Machine AC/DC & Acc |  | 698040 |  |  | 100% | 698040
340 |  | 2017 |  | Communication Equipment |  |  |  |  | 100%
341 |  | 2017 |  | 1 unit LCD projector |  | 26000 |  |  | 100% | 22995
342 |  | 2017 |  | Disaster Response & Rescue Equipment |  |  |  |  | 100%
343 |  | 2017 |  | 4 units Fire Extinguishers |  | 12364 |  |  | 100% | 12364
344 |  | 2017 |  | Military, Police & Security Equipment |  |  |  |  | 100%
345 |  | 2017 |  | 1 Set Security Equipment Access Control (CCTV) |  | 29845 |  |  | 100% | 29845
346 |  | 2017 |  | Other Machinery & Equipment |  |  |  |  | 100%
347 |  | 2017 |  | 6 units Work Bench w/ Bench Vice on 4 Corners |  | 204000 |  |  | 100% | 204000
348 |  | 2017 |  | 25 sets Combination Spanner (6mm to 24 mm) |  | 80000 |  |  | 100% | 80000
349 |  | 2017 |  | 12 units Blow Torch |  | 18000 |  |  | 100% | 18000
350 |  | 2017 |  | 12 units Clamp on Meter |  | 36000 |  |  | 100% | 36000
351 |  | 2017 |  | 6 units Portable Electric Drill |  | 30000 |  |  | 100% | 30000
352 |  | 2017 |  | 6 units Portable Planer |  | 51600 |  |  | 100% | 51600
353 |  | 2017 |  | 6 units Portable Circular Saw |  | 47220 |  |  | 100% | 47220
354 |  | 2017 |  | 25 pcs Welding Positioners |  | 96250 |  |  | 100% | 96250
355 |  | 2017 |  | 6 units Electrode Oven |  | 24000 |  |  | 100% | 24000
356 |  | 2017 |  | 25 units Portable Disc Grinder |  | 78750 |  |  | 100% | 78750
357 |  | 2017 |  | 6 units Pipe Threader 1/2-2" |  | 343200 |  |  | 100% | 343200
358 |  | 2017 |  | 6 units Pipe Bender |  | 26400 |  |  | 100% | 26400
359 |  | 2017 |  | 6 units Heat Gun 1200 watts |  | 18900 |  |  | 100% | 18900
360 |  | 2017 |  | 6 units Bolt Cutter |  | 7680 |  |  | 100% | 7680
361 |  | 2017 |  | 12 pcs Box Wrench |  | 58800 |  |  | 100% | 58800
362 |  | 2017 |  | 12 pcs Wire Splicer |  | 25320 |  |  | 100% | 25320
363 |  | 2017 |  | 12 pcs Wire Stripper |  | 25320 |  |  | 100% | 25320
364 |  | 2017 |  | 12 units Electric Drill |  | 58800 |  |  | 100% | 58800
365 |  | 2017 |  | 12 units Portable Grinder |  | 52500 |  |  | 100% | 52500
366 |  | 2017 |  | 6 units Pipe Cutter (1/2"-1") |  | 31590 |  |  | 100% | 31590
367 |  | 2017 |  | 3 units Manual Pipe Threader (1/2", 3/4", 1") |  | 33705 |  |  | 100% | 33705
368 |  | 2017 |  | 3 units Fusion Machine (20mm-32mm) |  | 34020 |  |  | 100% | 34020
369 |  | 2017 |  | 4 units Electric Grinder (4") |  | 20520 |  |  | 100% | 20520
370 |  | 2017 |  | 12 units Angle Grinder |  | 61560 |  |  | 100% | 61560
371 |  | 2017 |  | 2 units Labelling Machine |  | 2200 |  |  | 100% | 2200
372 |  | 2017 |  | 6 units Insulation Resistance Tester |  | 9900 |  |  | 100% | 9900
373 |  | 2017 |  | 6 units Earth Resistance Tester |  | 13200 |  |  | 100% | 13200
374 |  | 2017 |  | 4 units Pedestal/Bench Grinding Machine |  | 9400 |  |  | 100% | 9400
375 |  | 2017 |  | 10 units Panel Board with 70 amp main & 4 |  | 34450 |  |  | 100% | 34450
376 |  | 2017 |  | 25 pcs Electrician Pliers |  | 66250 |  |  | 100% | 66250
377 |  | 2017 |  | Other Property, Plant & Equipment
378 |  | 2017 |  | 3 units Wheelbarrow |  | 6600 |  |  | 100% | 6000
379 |  | 2017 |  | 6 sets Oxy-Acetylene/Oxy-LPG Cutting Outfit |  | 72000 |  |  | 100% | 72000
380 |  | 2017 |  | 6 units Plastic Drum (200 liters) |  | 10560 |  |  | 100% | 10560
382 |  |  | Power Supply System
383 |  | 2017 |  | Purchase of 50 KVA Transformer for BCTLDC |  | 500000 |  |  |  | 0
384 |  |  | Hospital and Health Centers
385 |  | 2017 |  | Construction of City Health Office Building |  | 1000000
386 |  | 2018 | Loan Amortization |  |  | 9809031.89 |  |  |  | 0
6 |  |  | Land
387 |  | 2018 |  | Lot Acquisition for Development Projects |  | 1754285.71 |  |  |  | 0
388 |  | 2018 |  | Purchase of Lot for Multi-Purpose Hall at Sitio Cambulo. Banga | Banga | 600000 |  |  |  | 0
152 |  |  | Roads,Highways & Bridges
389 | 10710020-001-0112 | 2018 |  | Widening of Malabugas-San Roque Road |  | 3500000 | 2019-09-01 | 2019-12-31 | 30% | 931407.77
390 | 10710020-001-0095 | 2018 |  | Concreting of Road Approaching Lapay Box Culvert with Slope Protection, Dawis | Bayawan Creek, Dawis | 1000000 | 2018-04-01 | 2018-08-31 | 100% | 746162.76
391 | 10710020-001-0094 | 2018 |  | Concreting of Road Approaching Candalaga Box Culvert with Slope Protection, Nangka | Nangka | 1000000 | 2018-04-01 | 2018-11-30 | 100% | 870445.24
392 | 10710020-001-0098 | 2018 |  | Concreting of Road Approaching Pusi-on Box Culvert with Slope Protection, Maninihon | Maninihon | 1000000 | 2018-04-01 | 2019-02-28 | 100% | 851903.96
393 | 10710020-001-0093 | 2018 |  | Concreting of Road Approaching Camandagan Box Culvert with Slope Protection, Maninihon | Maninihon | 1000000 | 2018-04-01 | 2018-09-30 | 100% | 787342.62
394 | 10710020-001-0091 | 2018 |  | Concreting of Road Approaching Balao Box Culvert with Slope Protection, San Miguel | San Miguel | 1000000 | 2018-04-01 | 2018-10-30 | 100% | 828417.41
395 | 10710020-001-0096 | 2018 |  | Concreting of Road Approaching Magsakang Box Culvert with Slope Protection, Tayawan | Tayawan | 1000000 | 2018-04-01 | 2019-07-31 | 100% | 851245.15
396 | 10710020-006-0016 | 2018 |  | Completion of Magsakang Flat Slab Bridge, Tayawan | Tayawan | 1000000 | 2018-04-01 | 2019-04-30 | 100% | 954259.8
397 | 10710020-001-0097 | 2018 |  | Concreting of Road Approaching Pamuat Box Culvert with Slope Protection, San Isidro | San Isidro | 1000000 | 2018-04-01 | 2019-06-30 | 100% | 928312.72
398 | 10710020-001-0092 | 2018 |  | Concreting of Road Approaching Binanigan Box Culvert with Slope Protection, Tayawan | Tayawan | 1000000 | 2018-04-01 | 2018-09-30 | 100% | 760523.42
399 | *10710020-001-0086 | 2018 |  | Concreting of Road at Purok 7, Barangay Tinago | Tinago | 2000000 | 2018-02-16 | 2018-08-31 | 100% | 1714331.49
400 | 10710020-001-0088 | 2018 |  | Concreting of Dawis-Lapay FMR | Bayawan City | 5500000 | 2018-04-01 | 2019-07-31 | 100% | 4536505.09
401 | 10710020-001-0087 | 2018 |  | Concreting of Banga-San Roque-Minaba-San Miguel-Tayawan FMR | Bayawan City | 5872000 | 2018-04-01 | 2019-06-30 | 100% | 5221497.1
402 | 10710020-001-0090 | 2018 |  | Concreting of Nangka-Narra FMR | Bayawan City | 5500000 | 2018-04-01 | 2019-05-31 | 100% | 4586263.85
403 | 10710020-001-0105 | 2018 |  | Concreting of Tabuan- Banaybanay-Lapay-Bugay-San Jose-Manduao FMR | Bayawan City | 28340000 | 2018-05-29 |  | 96.5% | 21144768.47
404 | 10710020-001-0103 | 2018 |  | Concreting of Road from Sitio Balastro to Sitio Candulion to Pulangyuta, Barangay Kalamtukan | Kalamtukan | 10500000 | 2018-08-01 | 2019-08-31 | 95% | 6516585.43
405 | 10710020-001-0104 | 2018 |  | Concreting of Road with Drainage Canal at Upper Napit-an, Maninihon | Maninihon | 300000 | 2018-04-01 | 2018-07-31 | 100% | 173965.88
406 | 10710020-001-0102 | 2018 |  | Concreting of Road from Highway Intersection to Minaba Elem. School, Brgy. Minaba | Bayawan City | 1000000 | 2018-04-01 | 2018-09-30 | 100% | 701735.4
407 | 10710020-001-0099 | 2018 |  | Concreting of Road at Sitio Kasla, Brgy. Nangka | Nangka | 850000 | 2018-04-01 | 2018-09-30 | 100% | 653409.03
408 | 10710020-006-0020 | 2018 |  | Construction of Flat Slab Bridge at Sitio Terong, Narra | Narra | 600000 | 2018-04-01 | 2019-06-30 | 100% | 520886.82
409 | 10710020-001-0107 | 2018 |  | Road Concreting from Proper Narra to Purok III, Brgy. Narra | Narra | 500000 | 2018-04-01 | 2018-10-16 | 100% | 394052.4
410 | 10710020-001-0089 | 2018 |  | Concreting of FMR from National Highway to Sitio Lapacon, Brgy. Pagatban | Bayawan City | 500000 | 2018-04-01 | 2018-08-31 | 100% | 394562.39
411 | 10710020-001-0100 | 2018 |  | Concreting of Road at Sitio Upper Pamu-at, San Isidro | San Isidro | 500000 | 2018-04-01 |  | 92.5% | 266044 |  | Temporarily Stopped: Road not yet passable; Materials delivered - 100%
412 | 10710020-001-0101 | 2018 |  | Concreting of Road at Upper Talao, San Isidro | San Isidro | 600000 | 2018-10-01 | 2019-03-31 | 100% | 514849.54
413 | 10710020-001-0108 | 2018 |  | Road Shouldering Along Zamora St., Brgy. Ubos | Ubos | 500000 | 2018-06-16 | 2018-11-30 | 100% | 428565.85
414 | 10710020-001-0110 | 2018 |  | Road Surfacing from Barangay Proper to Sitio Gawgaw to Sitio Aya, Brgy. Bugay | Bugay | 839286.43 | 2019-03-01 |  | 12% | 214010.55 |  | Pending: road not yet passable
415 | 10710020-001-0111 | 2018 |  | Road Surfacing from Barangay Proper to Sitio Mambuy-og to Sitio Canlantang, Brgy. Bugay | Bugay | 839285 | 2019-04-01 | 2019-12-31 | 92% | 337109.44
416 | 10710020-001-0109 | 2018 |  | Road Surfacing from Barangay Cansumalig | Cansumalig | 1078571.43 |  |  |  | 118966.57 |  | Pending: Road not yet passable
417 | 10710020-007-0026 | 2018 |  | Construction of Drainage Canal from Upper Napit-an to Lower Napit-an, Brgy. Maninihon | Maninihon | 650000 | 2018-06-01 | 2018-09-30 | 100% | 544106.01
418 | 10710020-004-0017 | 2018 |  | Installation of Cylindrical Culvert with Riprap at Proper Narra | Narra | 578571.43 | 2018-06-16 | 2019-08-31 | 100% | 495318.65
419 | 10710020-007-0025 | 2018 |  | Covering of Drainage Canals along Gomez St., Brgy. Ubos | Ubos | 1078571.43 |  |  |  | 542372.16 |  |  |  | GSO
420 | 0 | 2018 |  | Construction of Small Scale Irrigation Projects (SSIP): | Bayawan City
421 | 10710020-003-0007 | 2018 |  | a. Purok Mangga, Brgy. Manduao | Manduao | 800000 |  |  |  | 569072.95
422 | 10710020-003-0008 | 2018 |  | b. Sitio Dita, Brgy. Tabuan | Tabuan | 800000 |  |  |  | 299129.89
423 | 10710020-003-0009 | 2018 |  | c. Upper Canlinte, Brgy Ali-is | Ali-is | 800000 |  |  |  | 380721.33
424 | 10710020-003-0010 | 2018 |  | Rehabilitation of Irrigation Canal at Brgy. Tabuan | Tabuan | 915000 | 2019-03-01 |  | 95% | 765127.66 |  |  |  | Turn-over to BAWAD
322 |  |  | Water Supply Systems
425 | 10710020-002-0057 | 2018 |  | Water System Development at Bugay Proper | Bugay | 500000 |  |  |  | 148710.4 |  |  |  | Turn-over to BAWAD
426 | 10710020-002-0056 | 2018 |  | Development of Water System at Brgy. Villareal | Villareal | 1000000 |  |  |  | 327600 |  |  |  | Turn-over to BAWAD
427 | 10710020-001-0113 | 2018 |  | Installation of Street Lighting from Purok 1 to Purok IV, Brgy. Tayawan | Tayawan | 500000 |  |  |  | 144025.62
428 | 10710020-009-0001 | 2018 |  | Improvement of Barangay Plaza and Children's Park, Tayawan | Tayawan | 500000 |  |  |  | 24636.1
330 |  |  | Other Structures
429 | 0 | 2018 |  | Establishment of Early Child Care Dev't Centers: | Bayawan City
430 | 10710030-002-0021 | 2018 |  | a. Brgy. Villareal | Villareal | 5000000 |  |  |  | 20850.19
431 | 10710030-002-0022 | 2018 |  | b. Brgy. Malabugas | Malabugas | 5000000 | 2018-06-21 |  | 95% | 4436517.58
432 | 10710030-002-0023 | 2018 |  | Construction of Day Care Center at Sitio Mantapi, Nangka | Nangka | 578571.43 |  |  |  | 324562.46 |  |  |  | GSO
433 | 0 | 2018 |  | Improvement of Barangay Health Center & Lying-In Clinic, Brgy. Malabugas | Malabugas | 1000000 |  |  |  | 0
434 | 10710030-003-0008 | 2018 |  | Construction of Health Center at Sitio Mantapi, Nangka | Nangka | 500000 |  |  |  | 110023.07 |  |  |  | GSO
435 | 0 | 2018 |  | Construction of Barangay Public Market, Ali-is (Phase 1) | Bayawan City | 1000000 |  |  |  | 0
436 | 10710030-005-0001 | 2018 |  | Completion of Minaba Mini Slaughterhouse Phase III | Minaba | 500000 | 2018-10-16 | 2019-07-31 | 100% | 419375.96
437 |  | 2018 |  | Construction of Rainwater Harvesting Systems for Nurseries:
438 | 10710020-002-0075 | 2018 |  | a. Brgy. San Miguel | San Miguel | 250000 | 2018-10-01 | 2018-11-30 | 100% | 193602.58
439 | 10710020-002-0076 | 2018 |  | b. Brgy. Tayawan | Tayawan | 250000 | 2018-10-16 | 2019-05-31 | 100% | 190464.82
440 | 10710020-002-0077 | 2018 |  | c. Brgy. Cansumalig | Cansumalig | 250000 | 2018-10-16 | 2019-06-30 | 100% | 166198.33
441 | 10710020-002-0078 | 2018 |  | d. Brgy. Manduao | Manduao | 250000 |  |  |  | 90276.74
442 | 10710020-002-0079 | 2018 |  | e. Brgy. Kalamtukan | Kalamtukan | 250000 |  |  |  | 116439.5
443 | 10710030-030-0138 | 2018 |  | Construction of Bleachers at Barangay Evacuation Center, Ali-is | Ali-is | 678571.43 | 2018-04-01 | 2019-04-30 | 100% | 555739.56
444 | 10710030-030-0146 | 2018 |  | Improvement of Barangay Multi-Purpose Building, Banaybanay | Banaybanay | 1000000 |  |  |  | 0 |  |  |  | CONTRACT
445 | 10710030-030-0150 | 2018 |  | Improvement of Barangay Multi-Purpose Hall, Brgy. Boyco | Boyco | 1678571.43 |  |  |  | 0 |  |  |  | CONTRACT
446 | 10710030-030-0144 | 2018 |  | Construction of Barangay Multi-Purpose Building, Cansumalig | Cansumalig | 1300000 | 2019-07-16 |  | 25% | 737028.54
447 | 10710030-002-0024 | 2018 |  | Construction of Feeding Center at Damig Elementary School, Brgy. Kalamtukan | Kalamtukan | 778571.43 |  |  |  | 0 |  |  |  | CONTRACT
448 | 10710030-030-0147 | 2018 |  | Improvement of Barangay Multi-Purpose Building, Maninihon | Maninihon | 1000000 |  |  |  | 140346.6 |  |  |  | CONTRACT
449 | 10710030-030-0155 | 2018 |  | Construction of Multi-Purpose Pavement at Sitio Mantapi, Nangka | Mantapi, Nangka | 600000 | 2018-07-01 | 2018-12-31 | 100% | 546309.58
450 | 10710030-030-0148 | 2018 |  | Construction of Barangay Multi-Purpose Building, Narra | Narra | 1000000 |  |  |  | 0
451 | 10710010-002-0005 | 2018 |  | Construction of Concrete Perimeter Fence of Covered Court and Evacuation Center, Brgy. Pagatban | Pagatban | 100000 | 2018-07-01 | 2018-08-31 | 100% | 86496.06
452 | 10710030-030-0145 | 2018 |  | Construction of Multi-Purpose Building, Brgy. San Isidro (Phase 2) | San Isidro | 1078571.43 | 2019-08-01 |  | 25% | 479335.65
453 | 10710030-030-0137 | 2018 |  | Construction of Children and Women's Crisis Center, Brgy. Suba | Suba | 600000 |  |  |  | 0
454 | 10710030-030-0153 | 2018 |  | Improvement of Multi-Purpose Hall, Brgy. Suba | Suba | 578571.43 |  |  |  | 0
455 | 10710030-030-0149 | 2018 |  | Construction of Multi-Purpose Hall, Brgy. Tinago | Tinago | 2278571.43 |  |  |  | 0
456 | 10710030-030-0159 | 2018 |  | Construction of Fish Processing Center @ Brgy. Suba | Suba | 2500000 | 2019-04-01 | 2019-12-31 | 80% | 1918428.71 |  |  |  | GSO
457 | 10710030-030-0152 | 2018 |  | Improvement of Multi-Purpose Hall, Banga | Banga | 2078571.43 |  |  |  | 0
458 | 10710030-030-0161 | 2018 |  | Major Repair of Narra Barangay Agricultural Development Center (BADC) | Narra | 520000 |  |  |  | 304815.17 |  |  |  | GSO
459 | 10710030-030-0160 | 2018 |  | Major Repair of Manduao Barangay Agricultural Development Center (BADC) | Manduao | 290000 |  |  |  | 179168.68 |  |  |  | GSO
460 | 10710030-030-0151 | 2018 |  | Improvement of Barangay Multi-Purpose Hall, Manduao | Manduao | 600000 |  |  |  | 440893.31
461 | no obligation | 2018 |  | Purchase of Boom Truck | Bayawan City | 1600000 |  |  |  | 0
462 |  | 2018 |  | Purchase of 1 Unit Backhoe for Barangay Tayawan | Tayawan | 1678571.43 |  |  |  | 0
463 |  | 2018 |  | Purchase of Garbage Compactor Truck | Bayawan City | 1500000 |  |  |  | 0
464 | 10701010-001-0129 | 2018 |  | Purchase of Lot for Agricultural Research Center | Maninihon | 16000000 |  |  | 100% | 15710989
465 | 0 | 2018 |  | Establishment of Agricultural Research Center | Maninihon | 6895568.71 |  |  |  | 0
466 | 10710020-001-0125 | 2018 |  | Improvement of Bugay-San Jose-Manduao FMR | Bayawan City | 3000000 | 2018-10-15 | 2019-01-06 | 100% | 2959185.3
467 | 10710020-001-0127 | 2018 |  | Concreting of Urban Roads with Drainage System (GomeZ St.) | Poblacion | 12885436.16 | 2019-01-16 |  | 85% | 7856967.44
468 |  | TOTAL EDF CONTINUING APPROPRIATION |  |  |  | 485745064.02 |  |  |  | 296186115.63
469 |  | TOTAL EDF - CURRENT & CONTINUING APPROPRIATION |  |  |  | 688414349.51 |  |  |  | 363811777.6
|  |  |  | CORAZON P. LIRAZAN, CPA | [5 empty] | HON. PRYDE HENRY A. TEVES
|  |  |  | City Accountant | [5 empty] | City Mayor
Reverted:
26 | reverted SB10 | 2019 |  | Establishment of Cotton Ginnery and Spinning Center |  | 10000000
27 | reverted SB10 | 2019 |  | Site Improvement of Bayawan City Waste Management & Ecology Center |  | 9300000
Note on G28: MARY DECEE B. RIZADA: 16m reverted sb11
Note on M40: MARY DECEE B. RIZADA: On-Going: We cannot predict 100% completion due to the recent procurement process of materials
Note on M41: MARY DECEE B. RIZADA: On-Going: We cannot predict 100% completion due to the recent procurement process of materials
Note on M42: MARY DECEE B. RIZADA: On-Going: We cannot predict 100% completion due to the recent procurement process of materials
Note on M47: MARY DECEE B. RIZADA: On-Going: We cannot predict 100% completion due to the recent procurement process of materials
Note on M70: MARY DECEE B. RIZADA: deposit for expropriation case regarding adjacent lots for sanitary landfill (2007)
Note on M85: MARY DECEE B. RIZADA: obligation per SAAOB
Note on M95: MARY DECEE B. RIZADA: waiting for Fabrication of steel fence
Note on M111: MARY DECEE B. RIZADA: Physically Completed, For COC issuance
Note on M160: MARY DECEE B. RIZADA: Ford Tractor, Phils. PIS 100-17-05-0049
Note on M251: MARY DECEE B. RIZADA: why not yet started
Note on M264: MARY DECEE B. RIZADA: Temporary stopped: Road not yet passable
Note on M265: MARY DECEE B. RIZADA: Temporarily Stopped: No Heavy Equipment available
Note on M274: MARY DECEE B. RIZADA: Pending: Due to transfer of site location and Barangay & SP resolution on process
Note on M282: MARY DECEE B. RIZADA: Physically Completed, obligation per SAAOB
Note on M483: MARY DECEE B. RIZADA: Site-Napit-an, Brgy. Maninihon; TD No. 2016-04-0013-02364;

## Sheet1
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION REPORT
As of Spetember 30, 2019
CITY OF BAYAWAN
|  |  |  | Location | Total Cost (per Budget Approp) | Target Start Date | Target Completion Date | Project Status |  | No. of Ext., if any | Remarks
1 | Project Code | Year | Program or Project |  |  |  |  | % of Completion | Total Cost Incurred (per Acctg) |  |  | old engas code
2
3 |  | 20% ECONOMIC DEVELOPMENT FUND - CURRENT APPROPRIATION
4
5 |  | 2019 | Loan Amortization |  | 58000000 |  |  |  | 49166376.06
6 |  |  | Land
7 |  | 2019 | Lot Acquisition for Dita Relocation |  | 5000000
8 |  | 2019 | Lot Acquisition for Road Right of Way (Villreal) |  | 500000
9 |  | 2019 | Lot Acquisition for Agricultural Development Center (Tan-ayan) |  | 2500000
10 |  |  | Road Networks
11 | 10710020-001-0135 | 2019 | Wayang Access Road Development | Brgy. Nangka, Bayawan City | 20000000 | 2019-02-16 | 2019-12-30 | 45% | 7070295.1
12 | 10710020-002-0088 | 2019 | Construction of Ondol-Napit-an FMR | Bayawan City | 20000000 | 2019-03-01 |  |  | 6516616.5 |  | Pending: RROW Issues not yet resolved
13 | 10710020-001-0136 | 2019 | Concreting of Access Road from National Highway to Palongpong Agricultural Development Center | Bayawan City | 9000000 | 2019-04-01 | 2019-12-31 | 83% | 876579.47 |  |  |  | target completion
14 | 10710020-001-0134 | 2019 | Improvement of Road Leading to Danapa Inland Aquaculture Facility | Brgy. Nangka, Bayawan City | 2000000 | 2019-03-16 | 2019-12-31 | 92% | 589052.76 |  |  |  | target completion
15 | 10710020-001-0137 | 2019 | Concreting of Perimeter Road at BCWMEC | Brgy. Maninihon, Bayawan City | 2000000 | 2019-06-01 | 2019-12-31 | 93% | 320183.4 |  |  |  | NO EXPENSE YET?
16 | 10710020-001-0139 | 2019 | Concreting of Urban Roads with Drainage System (Gomez St.) | Brgy. Poblacion, Bayawan City | 3000000 | 07/16/19 | 2019-12-31 | 25% | 468172.85 |  |  |  | NO EXPENSE YET?
17 |  | 2019 | Improvement of Maninihon-Cansumalig-San Isidro FMR |  | 2387650.49
18 |  |  | Flood Control Systems
19 | 10710020-007-0030 | 2019 | Construction of Drainage Canal at Magsulay Agricultural Development Center | Brgy. Narra, Bayawan City | 400000 |  |  | 40% | 165391.25 |  |  |  | date
20
21 | 10710020-007-0029 | 2019 | Concreting of Drainage Canals at Barangay Proper, San Isidro | Bayawan City | 400000 | 2019-06-01 | 08/31/19 | 100% | 331852.13 |  |  |  | complete but exp is low
22 |  |  | Water Supply Systems
23 | 0 | 2019 | Construction & Installation of Water Supply Systems for Barangays Malabugas, San Roque, Minaba, San Miguel and Tayawan | Various Brgys | 11000000
24 |  |  | Power Supply Systems
25 | 0 | 2019 | Electrification Project at Purok Ipil-Ipil, San Roque | San Roque | 600000
26 |  |  | Other Infrastructures Assets
27 |  |  | School Buildings
28 | 10710030-002-0028 | 2019 | Construction of Day Care Center, Barangay San Miguel | Bayawan City | 400000 | 07/16/19 | 09/30/19 | 100% | 120858.3 |  |  |  | complete but no expenses
29 |  |  | Markets
30 | 10710030-004-0006 | 2019 | Construction of Public Market Stalls in Omod, Maninihon (Phase 1) | Bayawan City | 1678571.43 | 2019-06-16 | 2019-12-31 | 40% | 873960.08 |  |  |  | target completion date
31 |  |  | Other Structures
32 | 10710030-030-0198 | 2019 | Completion of Lapay Multi-Purpose Pavement | Brgy. Dawis, Bayawan City | 360000 | 2019-06-01 | 08/31/19 | 100% | 174859.65 |  |  |  | complete but no expenses
33 | 10710010-002-0011 | 2019 | Construction of Concrete Fence of Minaba Elementary School | Brgy. Minaba, Bayawan City | 500000 | 05/31/19 | 2019-12-31 | 90% | 95315.24 |  |  |  | 90% no expense, target date
34 | 10710010-002-0013 | 2019 | Construction of Concrete Fence of Canabuan Elementary School | Brgy. Minaba, Bayawan City | 500000 | 2019-06-01 | 2019-12-31 | 90% | 160496.92 |  |  |  | 90% no expense, target date
35 | 10710010-002-0012 | 2019 | Construction of Concrete Fence of Minaba High School | Brgy. Minaba, Bayawan City | 678571.43 | 2019-06-01 | 2019-12-31 | 90% | 105687.86 |  |  |  | 90% no expense, target date
36 | 10710030-030-0211 | 2019 | Construction of Barangay Multi-Purpose Building, Nangka | Bayawan City | 1678571.43 |  |  |  | 395897.8
37 | 10710030-030-0209 | 2019 | Construction of 2-Storey Multi-Purpose Building, Barangay Poblacion | Bayawan City | 1678571.43 |  |  |  | 0
38 | 10710010-002-0015 | 2019 | Construction of Concrete Fence of Bolirocon Elementary School, San Isidro | Bolirocon, Brgy. San Isidro, Bayawan City | 278571.43 |  |  |  | 81666.4
39 | 0 | 2019 | Construction of Multi-Purpose Building, Barangay San Isidro (Phase 3) | Brgy. San Roque, Bayawan City | 1000000 |  |  |  | 0
40 | 10710010-002-0010 | 2019 | Construction of Perimeter Fence at San Roque Elementary School | Brgy. San Roque, Bayawan City | 578571.43 | 2019-06-01 | 2019-12-31 | 80% | 112400.2 |  |  |  | 80% low expense, target date
41 | 0 | 2019 | Construction of Barangay Multi-Purpose Building, Tinago (Phase 3) |  | 1678571.43 |  |  |  | 0
42 | 0 | 2019 | Establishment of Agricultural Research Center |  | 10877134.99 |  |  |  | 0
43 |  |  | Purchase of Construction & Heavy Equipment:
44 |  |  | 1 unit Bulldozer |  | 15000000 |  |  |  | 0 |  |  |  | PR in process
45 |  |  | 1 unit Backhoe |  | 12000000 |  |  |  | 0
46 |  |  | 1 unit Trailer Mounted DW100-T Drilling Rig with Accessories |  | 3594500 |  |  |  | 0 |  |  |  | for 2020
47 |  |  | 2 units 6-Wheeler Dump Truck |  | 4400000 |  |  |  | 0 |  |  |  | for 2020
48 |  |  | Other Transportation Equipment
49 |  | 2019 | Purchase of Garbage Compactor Truck |  | 5000000 |  |  |  | 0
50 |  | 2019 | Purchase of Vacuum Declogger Truck |  | 2000000 |  |  |  | 0 |  |  |  | PR in process
51 |  |  | Breeding Stocks
52 |  | 2019 | Purchase of Livestock Breeding Stocks |  | 2000000 |  |  |  | 0
53 |  |  | TOTAL EDF - CURRENT APPROPRIATION |  | 202669285.49 |  |  |  | 67625661.97
54
55
56 |  | 20% ECONOMIC DEVELOPMENT FUND - CONTINUING APPROPRIATION
57
58 |  |  | CAPITAL OUTLAY
59 |  |  | 3918 - Purchase, Construction and Improvement of Government Facilities
60 | ngas 2 |  | Environmental Sanitation Program: |  | 0
61 |  | 2004 | 1. Sanitary Landfill (Land Acquisition) 2004 | Maninihon | 1000000 |  |  |  | 8311
62 |  | 2001 | 2. Sanitary Landfill - Dumpsite Acquisition 2001 | Maninihon | 500000 |  |  |  | 0 |  |  | no obligation
63 |  | 2011 | Renovation of BDH Canteen | BDH, Ubos | 114000 | 2011-06-01 | 2012-12-31 | 100% | 80418 |  |  | 264-004-11-10-G0021
64 | 10710020-006-0003 | 2011 | Const. of Hanging Bridge at Sitio Tiki, Kalumboyan (Phase 3) | Kalumboyan | 700000 | 2011-07-01 |  | 37% | 546410.34 |  | heavily damaged by typhoon | 266-003-11-05-G0009 | project discontinued, what happens to balance
65 | 10710030-005-0002 | 2012 | Construction of Slaughterhouse | Suba | 10000000 | 2016-09-16 | 2018-03-31 | 100% | 7818835.46 |  |  | 264-003-1603-G0021
66 | *10710030-030-0023 | 2012 | Improvement of Bayawan City Boulevard (Landscaping fronting GK Village) | Villareal | 535115.83 | 2013-08-01 | 2014-03-15 | 100% | 495907.52 |  |  | 264-009-13-04-G0429
67 | *10710030-030-0021 | 2013 | Construction of Sports Center and Children's Playground, Phase 3 | Suba | 3000000 | 2013-03-18 | 2015-05-30 | 100% | 2668470.08 |  |  | 264-009-13-03-G0424
68 | *10710030-030-0024 | 2013 | Construction of Covered Court at BCsTEC, Phase II | Cabcabon, Banga | 3008100 | 2013-10-01 | 2017-06-30 | 100% | 2783489.42 |  |  | 264-009-13-07-G0437/267-004-13-06-G0003
69 | 10710030-030-0025 | 2013 | Rehabilitation of GK Septic Tanks | Villareal | 3104400 | 2013-11-18 |  |  | 77968.68 |  | Pending: sub-standard Fiber Glass septic Tank delivered by supplier not accepted by LGU | 264-009-13-09-G0445
70 | *10710020-002-0036 | 2013 | Improvement of Water System for 21 Rural Barangays | Bayawan City | 568710 | 2016-07-01 | 2017-07-31 | 100% | 468013.78 |  |  | 269-001-1511-G0039
71 | *10710020-007-0002 | 2013 | Construction of Drainage Canal with Cover Along City Streets | Bayawan City | 606779.6 | 2014-06-02 | 2014-11-30 | 100% | 544360.59 |  |  | 271-002-14-05-G0027
72 | 0 | 2013 | Fabrication of Distillation Chamber for Essential Oil Production | Banga | 150000 |  |  |  | 0
73 | *10710020-001-0011 | 2014 | Construction of Bayawan City Boulevard / Phase 2 | Bayawan City | 1000000 | 2014-08-16 | 2014-10-30 | 100% | 936750.81 |  |  | 266-001-14-05-g0313
74 | *10710030-030-0031 | 2014 | Const. of Motorpool Building, Phase 1, Cabcabon | Cabcabon, Banga | 8483700 | 2015-07-06 | 09/31/17 | 100% | 7911686.98 |  |  | 264-009-14-10-e14-475
75 |  |  | Construction & Heavy Equipment
76 | per saaob | 2014 | Major Repair - Construction & Heavy Equipment | Motorpool Area | 10000000 | 2014-06-11 |  | 22.43% | 2242763
77 |  |  | Roads, Highways & Bridges |  | 0
78 | 10710020-001-0039 | 2014 | Road Surfacing from Sitio Binanigan to Sitio Guintana-an, Brgy. Tayawan, Phase 1 | Tayawan | 500000 | 2016-03-16 |  | 75% | 173183.68 |  | Temporary stopped; (need to look other quarry source, road not yet passable, Lack of Backhoe available) | 266-001-1603-G0360
79 |  |  | Artesian Wells, Reservoir, Pumping Stations & Conduits |  | 0
80 | *10710020-002-0025 | 2014 | Construction of Water System-Crusher Kalumboyan | Kalumboyan | 212800 | 2015-06-01 | 2016-06-30 | 100% | 182355.32 |  |  | 269-001-14-07-G0036
81 |  |  | Other Structures
82 | 10710030-030-0058 | 2015 | Construction of Evacuation Center, Brgy. San Miguel | San Miguel | 800000 | 2016-02-01 |  | 95% | 602620.16 |  | Temporary stopped; Materials delivered- 63%;for delivery-8%; re-canvas -29% [G.I. PIPE, 50mmØ - waived] | 264-009-1510-G0520
83 | *10710030-030-0059 | 2015 | Construction of Portable Toilet | Bayawan City | 770000 | 2016-01-15 | 2018-03-31 | 100% | 542396.04 |  |  | 264-009-1601-G0524
84 | 10710010-002-0003 | 2015 | Const. of GK Village Perimeter Fence | Villareal | 2000000 | 2016-10-01 | 2019-11-30 | 94% | 1716184.88 |  | Fabrication of steel fence | 264-009-1601-G0526 | target date of completion
85 |  |  | Construction & Heavy Equipment
86 | no obligation | 2015 | Purchase of Various Heavy Equipment |  | 3476406.99 |  |  |  | 0
87 |  |  | Roads, Highways & Bridges
88 | *10710020-001-0019 | 2015 | Reblocking of Concrete Pavement at Villareal-Cansumalig-San Isidro FMR, Phase 2 | Bayawan City | 500000 | 2015-06-01 | 2015-06-30 | 100% | 457677.34 |  |  | 266-001-1504-G0335
89 | 10710020-001-0013 | 2015 | Construction of Gomez Street Extension | Bayawan City | 3000000 | 2016-03-16 | 2018-06-30 | 100% | 1148517.88 |  |  | 266-001-1502-g0319
90 | *10710020-001-0016 | 2015 | Concreting of Road Shoulder of National Highway Fronting BNHS, | Bayawan City | 3000000 | 2016-02-09 | 2017-01-15 | 100% | 2935348.39 |  |  | 266-001-1502-g0326
91 | *10710020-001-0017 | 2015 | Construction of Access Road at Bayawan East, | Bayawan City | 2053659.56 | 2015-04-01 | 2016-03-15 | 100% | 1967337.73 |  |  | 266-001-1504-g0330
92 | 10710020-001-0040 | 2015 | Road Surfacing of Sitio Hag-um and Sitio Mambunot, Brgy. Tayawan, Phase 1 | Tayawan, Bayawan City | 500000 | 2016-03-16 |  | 30% | 189523.51 |  | Temporary stopped; (need to look other quarry source, road not yet passable, Lack of Backhoe available) | 266-001-1603-G0361
93 | *10710020-001-0022 | 2015 | Rehabilitation of FMR at Sitio Tubod, Brgy. Tabuan | Tubod, Tabuan | 100000 | 2015-10-01 | 2016-03-15 | 100% | 56654.12 |  |  | 266-001-1509-G0343
94 | *10710020-001-0021 | 2015 | Rehabilitation of Pulangyuta-Lapay FMR | Bayawan City | 2014400 | 2015-09-16 | 2017-03-31 | 100% | 2008455.26 |  |  | 266-001-1509-g0338
95 |  |  | Artesian Wells, Reservoir, Pumping Stations & Conduits
96 | 10710020-002-0037 | 2015 | Water System Development @ Sitio Camague to Cabiguhan, Brgy Banaybanay | Banaybanay | 303389.8 | 2017-02-16 |  | 50% | 206913.03 |  | Pending: Declared site has no water source; Materials completely delivered | 269-001-1603-G0039
97 |  |  | Hospital & Health Centers
98 | 10710030-003-0001 | 2016 | Rehabilitation of Health Center & Const. of Lying-in Facility, Brgy. Poblacion, Phase 2 | Poblacion | 500000 | 2016-09-16 | 2017-06-30 | 100% | 320188.77 |  |  | 264-004-1603-G0031
99 |  |  | Electrification, Power & Energy Structures
100 | *10710030-006-0010 | 2016 | Installation of Electrical System (Sitio Napit-an, Brgy Maninihon & Zamora Streets, Brgy. Suba) - | Suba | 1500000 | 2016-11-15 | 2018-08-31 | 100% | 1439250.62 |  |  | 264-005-1611-G0058
101 | *264-005-1606-G0056 | 2016 | Purchase of Transforments & Primary Metering @ New Gov't. Center | Banga | 2545000 | 2016-11-24 | 2016-11-29 | 100% | 2540000
102 | *10710030-006-0009 | 2016 | Installation of Secondary Line Feeder @ New Gov't. Center | Banga | 800000 | 2016-02-13 | 2018-07-15 | 100% | 669519.56 |  |  | 264-005-1606-G0055
103 | 10710020-001-0044 | 2016 | Establishment of Street Lighting Facilities - 2016 | Var. Brgys. | 400000 |  |  |  | 314630 |  |  | 266-004-1603-g0055
104 | *10710020-001-0065 | 2016 | Installation of Street Lightings at Brgy Proper, Villasol | Villasol | 140000 | 2017-10-02 | 2017-10-30 | 100% | 132852.6 |  |  | 266-004-1607-G0056
105 |  |  | Other Structures
106 | 10710030-002-0010 | 2016 | Construction of Day Care Centers in Nangka and Napit-an/Rehabilitation of Day Care Centers in Minaba, Narra, Purok 4 Tayawan | Nangka, Napit-an, Minaba, Narra, Tayawan | 2000000 | 2017-06-01 |  | 51.7% | 1428868.03 |  | Pending: No lot available | 264-009-1607-G0553
107 | *10710030-030-0079 | 2016 | Improvement of CICL Center Faciltities | Banga | 975000 | 2017-11-16 | 2019-03-31 | 100% | 764122.65 |  |  | 264-009-1607-g0548
108 | *10710030-030-0081 | 2016 | Completion of Paglaum Center at Cabcabon | Cabcabon | 500000 | 2016-10-16 | 2018-05-31 | 100% | 352817.03 |  |  | 264-009-1607-g0550
109 | *10710030-030-0069 | 2016 | Completion of Women's Multi-purpose Center | Boyco | 1000000 | 2016-12-01 | 2018-11-30 | 100% | 783751.69 |  |  | 264-009-1603-G0533
110 | 10710030-030-0078 | 2016 | Construction of Women's Detention Cell | Banga | 400000 | 2019-07-29 | 2019-10-30 |  | 211222.56 |  |  | 264-009-1607-g0547
111 | 10710030-030-0067 | 2016 | Construction of Women's Facilities in Evacuation Center | Var. Brgys | 200000 | 2019-07-22 | 2019-08-22 |  | 158078.43 |  |  | 264-009-1603-G0538
112 | *10710030-002-0009 | 2016 | Construction of Day Care Center at Brgy. Proper, Brgy,. San Miguel | San Miguel | 500000 | 2016-08-16 | 2017-05-31 | 100% | 440367.22 |  |  | 264-002-1603-G0078
113 | 10710030-030-0073 | 2016 | Const. of Bleachers & CRs @ Existing Gyms for evacuation (Tinago, Boyco, Suba,Poblacion, Banga, Malabugas, Villareal, BNHS) | Various Brgys | 6000000 | 2019-07-30 | 07/31/19 | 100% | 5105050.96 |  |  | 264-009-1603-G0540
114 |  |  | a. Tinago |  |  |  |  | 100%
115 |  |  | b. Boyco |  |  |  |  | 100%
116 |  |  | c. Suba |  |  |  |  | 100%
117 |  |  | d. Poblacion |  |  |  |  | 100%
118 |  |  | e. Banga |  |  |  |  | 100%
119 |  |  | f. Malabugas |  |  |  |  | 100%
120 |  |  | g.Villareal |  |  |  |  | 100%
121 |  |  | h. BNHS |  |  |  |  | 100%
122 | 10710030-030-0076 | 2016 | Improvement of Agricultural Dev. Ctr. (ADC), Cansumalig, Phase 2 | Cansumalig | 400000 | 2017-06-01 | 2018-06-30 | 100% | 348687.17 |  |  | 264-009-1606-G0544
123 | *10710030-030-0074 | 2016 | Const. of Comfort Rooms in 13 Evacuation Ctrs. | Var Brgys | 1054174.83 | 2019-04-30 | 2018-02-28 | 100% | 1056488.39 |  |  | 264-009-1604-G0541
124 |  |  | a. Banga Central School |  |  |  |  | 100%
125 |  |  | b. BCSTEC Elementary & Highschool |  |  |  |  | 100%
126 |  |  | c. Malabugas Highschool |  |  |  |  | 100%
127 |  |  | d. Nangka Elementary School |  |  |  |  | 100%
128 |  |  | e. Guisocon Elementary School |  |  |  |  | 100%
129 |  |  | f. Atilano Cabangal Memorial Highschool |  |  |  |  | 100%
130 |  |  | g. Tavera Elementary School |  |  |  |  | 100%
131 |  |  | h. Dean Felix Gaudiel Memorial Elementary School |  |  |  |  | 100%
132 |  |  | i. H. Bido Jordan Elementary School |  |  |  |  | 100%
133 |  |  | j. Bayawan National Highschool |  |  |  |  | 100%
134 |  |  | k. Maninihon Elementary & Highschool |  |  |  |  | 100%
135 |  |  | l. H. Bido Jordan Highschool School |  |  |  |  | 100%
136 |  |  | m. SLGTMES |  |  |  |  | 100%
137 | *10710030-030-0072 | 2016 | Improvement of Covered Court/Evacuation Ctr., Bry. Banga | Banga | 500000 | 2016-10-16 | 2017-06-30 | 100% | 435324.88 |  |  | 264-009-1603-G0536
138 | 10710030-030-0071 | 2016 | Const. of Evacuation Ctr., Brgy. San Roque | San Roque | 500000 | 2017-06-16 | 2019-06-30 | 100% | 361521.48 |  |  | 264-009-1603-G0535
139 | *10710030-030-0070 | 2016 | Const. of Covered Court/Evacuation Ctr., Bry. Suba | Suba | 500000 | 2016-12-16 | 2017-05-31 | 100% | 454964.53 |  |  | 264-009-1603-G0534
140 | *10710030-030-0082 | 2016 | Const. of Multi-Purpose Bldg. for Evacuation Ctr., Brgy Villareal | Villareal | 500000 | 2017-05-01 | 2018-11-30 | 100% | 431575.23 |  |  | 264-009-1608-G0557
141 | *10710020-002-0043 | 2016 | Const. of Rain Collector at Brgy. San Isidro | San Isidro | 150000 | 2017-12-16 | 2018-05-31 | 100% | 137210.67
142 | 0 | 2016 | Fish Farm Development Program |  | 900000 |  |  |  | 0
143 | *10710030-030-0084 | 2016 | Establishment of Youth Development Center |  | 5000000 | 2017-06-15 | 2018-09-01 | 100% | 4000896.6 |  |  | 264-009-1701-G0560
144 | 10710030-003-0009 | 2016 | Renovation of the Integrated Business Center(IBC) Building | Villareal | 8000000 | 2018-04-27 |  | 96% | 6223227.42 |  | Recommended for termination of contract
145 | 10710030-030-0086 | 2016 | Pilot Livestock Silage Stocking Project |  | 2000000 |  |  |  | 1391084 |  |  | 264-009-1703-G0564
146 | 0 | 2016 | LGU Counterpart for the Construction of Sports Complex |  | 15000000 |  |  |  | 0
147 | *10710030-004-0005 | 2016 | Establishment of Bayawan Farmers' Market in Dumaguete |  | 5000000 | 2018-02-05 | 2018-10-31 | 100% | 4994489.13 |  |  | 264-009-1708-g0577
148 |  |  | Agricultural, Fishery & Forestry Equipment
149 | per saaob | 2016 | Purchase of Agricultural & Forestry Equipment and Implements |  | 8800000 | 2018-01-02 | 2018-12-31 | 100% | 8400000
150 |  |  | Technical & Scientific equipment
151 | no obligation |  | Purchase of Digital Weighing Scale |  | 250000 |  |  |  | 0
152 |  |  | Roads,Highways & Bridges
153 | *10710020-001-0031 | 2016 | Improvement of Nangka-Narra FMR | Bayawan City | 5000000 | 2016-06-16 | 2017-08-31 | 100% | 4454951.93 |  |  | 266-001-1601-G0353
154 | *10710020-001-0041 | 2016 | Improvement of Maninihon-Cansumalig-San Isidro FMR | Bayawan City | 5000000 | 2016-06-16 | 2017-09-15 | 100% | 4802539.95 |  |  | 266-001-1603-G0362
155 | *10710020-001-0053 | 2016 | Reblocking of Concrete Pavement at Villareal-Cansumalig-San Isidro FMR, Phase 3 | Bayawan City | 500000 | 2017-03-01 | 2017-07-31 | 100% | 470136.11 |  |  | 266-001-1606-G0374
156 | *10710020-001-0043 | 2016 | Reblocking of Concrete Pavement Nangka- Narra FMR | Bayawan City | 500000 | 2017-02-16 | 2017-06-30 | 100% | 472475.09 |  |  | 266-001-1603-G0364
157 | *10710020-001-0062 | 2016 | Reblocking of Concrete Pavement with Slope Protection at Malabugas-San Roque Route | Bayawan City | 500000 | 2017-05-01 | 2017-10-31 | 100% | 459598.82 |  |  | 266-001-1607-G0383
158 | *10710020-001-0052 | 2016 | Reblocking of Concrete Pavement with Slope Protection at Tabuan-Banay-banay Route | Bayawan City | 500000 | 2017-05-01 | 2017-10-31 | 100% | 463537.29 |  |  | 266-001-1606-G0373
159 | *10710020-001-0049 | 2016 | Concreting of Road Approaching Upper Baican Box Culvert with Slope Protection | Bugay | 1000000 | 2016-10-16 | 2017-06-30 | 100% | 974648.99 |  |  | 266-001-1606-G0370
160 | *10710020-001-0048 | 2016 | Concreting of Road Approaching Nayabaan Box Culvert with Slope Protection | Bugay | 1000000 | 2016-09-16 | 2017-07-15 | 100% | 908111.85 |  |  | 266-001-1606-G0369
161 | *10710020-001-0063 | 2016 | Concreting of Road Approaching Cagayon Box Culvert with Slope Protection | Banaybanay | 1000000 | 2017-01-01 | 2017-10-31 | 100% | 905886.26 |  |  | 266-001-1607-G0384
162 | *10710020-001-0061 | 2016 | Concreting of Road Approaching Cabigohan Box Culvert with Slope Protection | Dawis | 1000000 | 2017-05-01 | 2017-10-15 | 100% | 930476.68 |  |  | 266-001-1607-G0382
163 | 10710020-030-0001 | 2016 | Installation of Guardrails at Kalumboyan Bridge Approaches | Kalumboyan | 2000000 | 2017-08-01 | 2018-06-30 | 100% | 1737337.87 |  |  | 266-003-1608-G0022
164 | *10710020-006-0008 | 2016 | Const. Tiki Footbridge, Phase 2 Brgy. Kalumboyan | Kalumboyan | 700000 | 2017-04-16 | 2018-02-28 | 100% | 685551.67 |  |  | 266-003-1602-G0018
165 | 10710020-001-0025 | 2016 | Const. of Urban Roads (Gomez to Kabankalan Road) | City Proper | 8000000 | 2017-06-01 | 2018-12-31 | 100% | 5854241.79 |  |  | 266-001-1512-G0347
166 | 10710020-001-0032 | 2016 | Rehab of FMR at So. Pag-awitan, Ali-is | Ali-is | 500000 | 2018-05-16 | 2018-12-31 | 100% | 296371.2 |  |  | 0
167 | 10710020-001-0036 | 2016 | Road Opening at Sitio Palasanon, Cansinacao, Guintalasan Mangharaw & Guinhamogan, Brgy Cansumalig | Cansumalig | 500000 | 2018-02-16 |  | 50% | 114051.44 |  | Temporary Stopped: Road not passable anymore & No Available Heavy Equipment | 266-001-1602-G0358
168 | 10710020-001-0033 | 2016 | Road Rehabilitation at so. Camague, Brgy Dawis | Villareal | 500000 |  |  |  | 82591.46 |  | Pending: No available H.E. and Road not yet passable; Materials Completely Delivered | 266-001-1602-G0355
169 | 10710020-001-0035 | 2016 | Road surfacing at Manduao-Bucao, Brgy Manduao | Manduao | 500000 | 2016-03-16 |  | 5% | 167283.93 |  | Temporarily stopped, road not yet passable. | 266-001-1602-G0357
170 | *10710020-006-0009 | 2016 | Const. of Steel Bridge Connecting So. Malampa to So. Tab-ang, Brgy Pagatban | Pagatban | 500000 | 2017-06-16 | 2018-01-31 | 100% | 360828.1 |  |  | 266-003-1607-G0020
171 | *10710020-001-0060 | 2016 | Const. or Road from Gov't. Ctr. To sitio Buli-buli/Phase 2 | Banga | 2000000 | 2017-01-01 | 11-31-17 | 100% | 1670978.21 |  |  | 266-001-1607-G0381
172 | 10710020-001-0064 | 2016 | Improvement of Road Along Bayawan CIP Main Canal | Bayawan City | 190000 |  |  |  | 90000 |  |  | 266-001-1607-G0385 | with expense no date and completion
173 | *10710020-006-0010 | 2016 | Const. of Footbridge at Sitio Lower Baican, Brgy Villasol | Baican, Villasol | 220000 | 2018-02-01 | 2018-06-30 | 100% | 189061.91 |  |  | 266-003-1607-G0021
174 |  |  | Artesian Wells, Reservoir, Pumping Stations & Conduits
175 | 10710020-002-0041 | 2016 | Rehabilitation of San Isidro Water Supply System | Villareal | 350000 |  |  |  | 189138.38 |  |  | 269-001-1612-g0043 | with expense no date and completion
176 | *10710030-030-0085 | 2016 | Const. of Water Tank & Pipeline at Tabuan Brgy Proper | Tabuan | 500000 | 2017-05-01 | 2018-05-31 | 99.5% | 424113.31 |  |  | 264-009-1702-G0561
177 | 10710020-002-0039 | 2016 | Construction of Tayawan Water System | Tayawan | 300000 | 2017-06-01 |  | 95% | 255424.64 |  | Temporary Stopped: RCPC for water source cannot be delivered on site road not passable | 269-001-1608-G0041
178 |  |  | Irrigation, Canals & Laterals
179 | *10710020-003-0004 | 2016 | Rehabilitation of Bayawan Communal Irrigation System | Pagatban | 500000 | 2016-08-16 | 2016-12-31 | 100% | 458455.32 |  |  | 270-001-1607-G0015
180 | 10710020-003-0005 | 2016 | Const. of Small Scale Irrigation Project at Sitio Magsulay, Narra | Narra | 1000000 |  |  |  | 959792.77 |  |  | 270-001-1701-G0017 | with expense no date and completion
181 |  |  | Flood Controls
182 | *10710020-007-0010 | 2016 | Construction of Drainage City Streets - Zamora, Teologio Sts, Subd Area | Zamora, Teologio & Subd Area | 3000000 | 2017-01-01 | 2017-09-15 | 100% | 2461029.39 |  |  | 271-002-1607-G0038
183 | *10710020-005-0008 | 2016 | Rehabilitation of River Bank Protection at Sitio Ebuan, Nangka | Nangka | 2000000 | 2017-03-16 | 2018-12-31 | 100% | 1451778.7 |  |  | 272-002-1702-G0033
184 | *10710020-004-0011 | 2016 | Const. of Box Culvert in So. Candalaga, Brgy Nangka | Nangka | 500000 | 2017-03-16 | 2017-06-30 | 100% | 381385.53 |  |  | 271-001-1607-G0052
185 | *10710020-002-0042 | 2016 | Construction of Spring Box at Upper Talao, Brgy San Isidro | San Isidro | 500000 | 2018-04-15 | 2019-03-31 | 100% | 253922.18 |  |  | 269-002-1607-G0032
186 | *10710020-004-0016 | 2016 | Const. of 1 unit Single Box Culvert Phase 1 at So, Magsakang, brgy Tayawan | Tayawan | 500000 | 2018-01-16 | 2018-05-15 | 100% | 410379.87 |  |  | 271-001-1706-G0057
187 | *10710020-007-0011 | 2016 | Const. of Drainage Canal at along Burgos St. & AlongBollos St. Brgy Ubos | Ubos | 500000 | 2017-02-01 | 2017-06-30 | 100% | 442668.24 |  |  | 271-002-1607-G0036
188 |  |  | Waterways, Aqueducts, Seawalls, RiverWalls & Others
189 | *10710020-005-0007 | 2016 | Rehabilitation of Riverbank @ Brgy. Nangka | Nangka | 1000000 | 2018-05-16 | 2018-12-31 | 100% | 1013905.35 |  |  | 272-002-1609-G0032
190 |  | 2017 | Establishment of Montessori-Type Early Child Care Development Centers | Various Brgys | [7 empty] | 264-002-1711-g0081/G0082
191 | 10710030-002-0011 | 2017 | a. Establishment of Montessori-Type Early Child Care Development Centers Phase 2 | Brgy. Boyco | 2289000 | 2018-12-16 | 2019-12-15 | 98% | 1062624.16
192 | 10710030-002-0014 | 2017 | b. Establishment of Montessori-Type Early Child Care Development Centers | Brgy. Poblacion, Bayawan City | 1211000 | 2018-01-01 | 2018-11-30 | 100% | 699088.03 |  |  | 264-002-1711-g0081/G0082
193 | 10710010-001-0003 | 2017 | Development of Danapa Eco Park | Nangka | 18000000 | 2016-06-12 |  | 98% | 16778685.58 |  | pending: subject for termination | 264-009-1705-G0566
194 | 10710020-030-0003 | 2017 | Development of Narra Water Park | Narra | 16000000 | 2017-09-12 | 2018-09-30 | 100% | 15993892.48 |  |  | 269-002-1704-G0035
195 | 10710020-009-0003 | 2017 | Development of Tabuan People's Park | Tabuan | 2000000 |  |  |  | 1396904.13 |  |  | 0
196 | *10710030-030-0128/0129/0130 | 2017 | Construction of Coastal Park Comfort Rooms |  | 4500000 | 2018-02-15 | 2018-05-27 | 100% | 4497336 |  |  | 264-009-1710-G0592/G0593/g0594
197 | 264-009-1711-G0600 | 2017 | Construction of Children's Playground with Facilities, Ali-is | Ali-is | 500000 |  |  |  | 0
198 | 10710030-003-0016 | 2017 | Improvement of Barangay Health Center Lying-In Clinic, Brgy. Malabugas | Malabugas | 678571.43 |  |  |  | 0 |  |  | 0
199 | 264-004-1711-G0033 | 2017 | Improvement of Barangay Health Center & Lying-in Clinic, Brgy. Manduao | Manduao | 100000 |  |  |  | 0
200 | 10710030-030-0132 | 2017 | Construction of Covered Court and Evacuation Center, Brgy. Pagatban | Pagatban | 1728571.43 |  |  |  | 0 |  |  | 264-009-1712-g0609
201 | 10710030-030-0135 | 2017 | Improvement of Evacuation Center and Multi-Purpose Building, Brgy. Poblacion | Poblacion | 878571.43 |  |  |  | 0 |  |  | 264-009-1712-g0612
202 | 10710030-002-0019 | 2017 | Construction of New Day Care Center at Brgy. Poblacion | Poblacion | 800000 |  |  |  | 0 |  |  | 264-002-1712-g0083
203 | 10710030-003-0015 | 2017 | Construction of Lying-In Clinic, Brgy. San Isidro | San Isidro | 1178571.43 | 2019-01-24 | 2019-11-30 | 98% | 590297.46 |  |  | 0 | target completion date
204 | 10710030-003-0006 | 2017 | Improvemen of Health Center and Lying-in Clinic, Brgy.San Roque | San Roque | 1678571.43 |  |  |  | 0 |  |  | 264-004-1712-g0035
205 | 0 | 2017 | Improvement of Barangay Health Center, Brgy. Tinago | Tinago | 600000 |  |  |  | 0 |  |  | 0
206 | 10710030-030-0131 | 2017 | Construction of Children's Playground with Facilities, Brgy. Villareal | Villareal | 500000 |  |  |  | 0 |  |  | 264-009-1712-g0608
207 | 0 | 2017 | Construction of Multi-Purpose Center for Senior Citizens, Brgy. Villasol | Bayawan City | 50000 |  |  |  | 0 |  |  | 0
208 | 10710030-003-0005 | 2017 | Improvement of Barangay Health Center, Brgy. San Jose | San Jose | 60000 |  |  |  | 0 |  |  | 264-004-1712-g0034
209 | 10710030-003-0007 | 2017 | Renovation of Barangay Health Center at Brgy. Tayawan | Tayawan | 150000 |  |  |  | 0 |  |  | 264-004-1712-g0036
210 | 10710030-002-0020 | 2017 | Renovation of Day Care Center, Brgy. Tayawan | Tayawan | 100000 |  |  |  | 0 |  |  | 264-002-1712-g0084
211 | 10710030-030-0049 | 2017 | Construction of Pigpens |  | 400000 |  |  |  | 0
212 | 0 | 2017 | Construction of 2 Units Small Scale Rubber Processing Plant with Shed |  | 300000 |  |  |  | 0 |  |  | 0
213 | budget data | 2017 | Purchase of Breeding Stocks | Bayawan City | 1944000
214 | 0 | 2017 | Improvement of Brgy. Dawis Livestock Auction Market | Dawis | 150000 |  |  |  | 0 |  |  | 0
215 | *10710030-030-0091 | 2017 | Fabrication of Portable Batching Plant |  | 500000 | 2017-10-16 | 2018-05-31 | 100% | 325671.05 |  |  | 264-009-1707-G0576
216 | *10710030-001-0004 | 2017 | Construction of CEO Multi-Purpose Building | Cabcabon | 2000000 | 2017-04-16 | 2019-04-30 | 100% | 1744342.36 |  |  | 264-009-1705-G0567
217 | 10710030-030-0088 | 2017 | Construction of Motorpool Building at Cabcabon | Cabcabon | 8000000 | 2017-05-16 | 2019-12-15 | 99.5% | 6067226.56 |  |  | 264-009-1706-g0569
218 | no obligation | 2017 | Lot Acquisition |  | 500000 |  |  |  | 0
219 | 0 | 2017 | Establishment of Livestock Auction Market |  | 2000000 |  |  |  | 0 |  |  | 0
220 | 0 | 2017 | Improvement of Public Market Water System | Bayawan City | 500000 |  |  |  | 0 |  |  | 0
221 | *10710020-001-0076 | 2017 | Construction of Slope Protection at Narra-Duyanduyan FMR, Sito Duyan-duyan, Brgy. Narra | Bayawan City | 1000000 | 2017-10-16 | 2018-05-31 | 100% | 895097.05 |  |  | 266-001-1708-g0396
222 | 10710020-008-0006 | 2017 | Flood Control Project at Brgy. Malabugas, Phase 2 | Malabugas | 1500000 | 2017-09-01 | 2018-06-30 | 100% | 1331896.08 |  |  | 271-002-1709-G0048
223 | 10710020-007-0022 | 2017 | Construction of Drainage at Cabugcabugan Creek, Brgy. Poblacion, Phase 4 | Poblacion | 1356746.77 | 2017-11-16 |  | 25% | 1197855.77 |  | Pending Consultation with BMAKBI and Mr. Eldie Tinapao (Vallacar) | 271-002-1711-g0050
224 | 10710020-005-0010 | 2017 | Construction of Riverbank Protection at Camayaan Creek,Brgy. Malabugas | Malabugas | 1000000 | 2018-01-16 | 2018-10-16 | 100% | 898258.82 |  |  | 272-002-1708-G0035
225 | no obligation | 2017 | Purchase of Various Agricultural Equipment | Bayawan City | 4000000
226 | 10710030-030-0101 | 2017 | Construction of Multi-Purpose Pavement at Brgy. Ali-is | Ali-is | 580000 | 2017-12-16 | 2018-06-30 | 100% | 549090.35 |  |  | 264-009-1708-G0587
227 | 10710020-006-0012 | 2017 | Construction of Flat Slab Bridge at Brgy. Proper, Banaybanay | Banaybanay | 600000 | 2018-01-16 | 2018-09-30 | 100% | 583108.44 |  |  | 266-003-1708-G0025
228 | 0 | 2017 | Improvement of FMR at Sitio Cangcawit, Banaybanay | Banaybanay | 1078571.43 |  |  |  | 0 |  |  | 0
229 | 10710030-030-0189 | 2017 | Improvement of Covered Court & Evacuation Center, Brgy. Banga | Banga | 500000 | 2019-03-16 | 2019-10-30 | 60% | 330449.03 |  |  | 0
230 | *10710020-001-0079 | 2017 | Improvement of FMR at Sitio Cansig-id, Brgy. Banga | Banga | 500000 | 2017-12-01 | 2018-01-31 | 100% | 455034 |  |  | 266-001-1708-g0401
231 | 0 | 2017 | Improvement of FMR from Brgy. Proper to Sitio Aya, Brgy. Bugay | Bugay | 839286.43 |  |  |  | 0 |  |  | 0
232 | 0 | 2017 | Improvement of FMR from Brgy Proper to Sitio Canlantang,Brgy. Bugay | Bugay | 839285 |  |  |  | 0 |  |  | 0
233 | 10710030-030-0090 | 2017 | Construction of Multi-Purpose Pavement at Sitio Guintalasan, Brgy. Cansumalig | Cansumalig | 559523.81 |  |  |  | 293822.16 |  |  | 264-009-1707-G0574
234 | *10710030-030-0093 | 2017 | Construction of Multi-Purpose Pavement at Sitio Guinhamogan, Brgy. Cansumalig | Cansumalig | 559523.81 | 2018-04-18 | 2018-07-31 | 100% | 519399.55 |  |  | 264-009-1708-g0579
235 | 10710030-030-0099 | 2017 | Construction of Multi-Purpose Pavement at Sitio Punong, Brgy. Cansumalig | Cansumalig | 559523.81 | 2018-03-16 | 2019-08-31 | 100% | 505035.42 |  |  | 264-009-1708-G0582
236 | 264-009-1711-g0597 | 2017 | Construction of Satellite Farmers' Market, Brgy. Dawis | Dawis | 1000000 |  |  |  | 0
237 | 264-009-1711-g0595 | 2017 | Improvement of Multi-Purpose Building at Brgy. Dawis | Dawis | 678571.43 |  |  |  | 0
238 | 10710020-001-0115 | 2017 | Improvement of FMR at Brgy. Dawis | Dawis | 150000 | 2018-06-01 | 2019-02-22 | 100% | 146687.65 |  |  | 266-001-1708-G0394
239 | 10710020-001-0081 | 2017 | Improvement of Road from Barangay Proper to Kalamtukan Elementary School, Brgy. Kalamtukan | Kalamtukan | 1178571.43 | 2017-10-16 | 2018-06-15 | 100% | 1083384.59 |  |  | 266-001-1708-G0405
240 | 10710030-030-0100 | 2017 | Construction of Multi-Purpose Pavement at Sitio Cogon, Brgy. Kalamtukan | Kalamtukan | 500000 | 2018-01-16 | 2018-06-30 | 100% | 471707.38 |  |  | 264-009-1708-g0583
241 | 0 | 2017 | Improvement of FMR at Brgy. Proper, Manduao | Manduao | 500000 |  |  |  | 0 |  | Pending: Road not yet passable | 0
242 | 10710020-002-0047 | 2017 | Construction of Water System at Proper Manduao | Manduao | 678571.43 |  | 2019-09-30 | 99.8% | 407627.54 |  | Turn-over to BAWAD | 269-001-1708-G0047
243 | 10710030-030-0089 | 2017 | Construction of Multi-Purpose Pavement at Sitio Bocaw, Manduao | Manduao | 500000 | 2019-01-01 | 2019-07-31 | 100% | 461324.64 |  |  | 264-009-1707-G0575
244 | 10710020-002-0052 | 2017 | Water System Development Project at Sitio Upper Camandagan, Brgy. Maninihon | Maninihon | 1000000 |  |  |  | 647344.67 |  | Turn-over to BAWAD | 269-001-1711-g0052
245 | 264-009-1712-g0606 | 2017 | Improvement of Multi-Purpose Gymnasium and Evacuation Center, Brgy. Maninihon | Maninihon | 678571.43 | 2019-01-25 | 2019-11-30 | 99% | 0 |  | Subject for evaluation of as built plan and estimates
246 | *10710020-001-0114 | 2017 | Improvement of FMR at Brgy. Minaba | Minaba | 678571.43 | 2018-05-16 | 2019-01-31 | 100% | 532636.79 |  |  | 0
247 | 10710020-001-0075 | 2017 | Improvement of FMR at Sitio Kasla, Brgy. Nangka | Nangka | 1000000 | 2017-12-01 | 2018-07-31 | 100% | 889470.06 |  |  | 266-001-1708-g0402
248 | 0 | 2017 | Establishment of Barangay Water Refilling Station, Brgy. Nangka | Nangka | 678571.43 |  |  |  | 0 |  |  | 0
249 | 10710020-001-0085 | 2017 | Improvement of FMR at Sitios Terong, Palongpong, Canggabi and Cadal-ugan, Brgy. Narra | Narra | 1000000 | 2018-05-16 |  | 20% | 246842 |  | Temporarily stopped: Road not yet passable | 0
250 | 10710020-001-0072 | 2017 | Road Opening at Brgy. Narra Proper | Narra | 678571.43 | 2018-06-16 | 2019-12-31 | 80% | 301799.59 |  | Pending: No Heavy Equipment available | 266-001-1708-g0398
251 | *10710020-002-0053 | 2017 | Installation of Water System at Brgy. Poblacion | Poblacion | 70000 | 2018-03-01 | 2018-03-15 | 100% | 28933.33 |  |  | 0
252 | 0 | 2017 | Construction of Barangay Public Market, Brgy. San Jose | San Jose | 1678571.43 |  |  |  | 0 |  |  | 0
253 | 0 | 2017 | Construction of Cloning Chamber at San Roque BADC | San Roque | 50000 |  |  |  | 0 |  |  | 0
254 | 10710030-030-0134 | 2017 | Improvement of Covered Court for Evacuation Center, Brgy Suba | Suba | 1678571.43 | [6 empty] | 264-009-1712-g0611
255 | 10710020-006-0013 | 2017 | Improvement of Flat Slab Bridge at Sitio Magsakang, Brgy Tayawan | Tayawan | 500000 | 2019-02-16 | 2019-10-31 | 99% | 321785.57 |  |  | 266-003-1704-G0023
256 | 10710020-001-0074 | 2017 | Improvement of Binanigan-Guintanaan FMR, Tayawan | Tayawan | 678571.43 |  |  |  | 24776.18 |  |  | 266-001-1708-g0403
257 | 10710020-001-0073 | 2017 | Improvement of Binanigan-Napo FMR, Brgy. Tayawan | Tayawan | 500000 |  |  |  | 205271.33 |  |  | 266-001-1708-g0404
258 | 264-009-1711-g0602 | 2017 | Improvement of Multi-Purpose Building, Brgy. Tinago | Tinago | 1128571.43 |  |  |  | 168535.72
259 | 10710020-007-0017 | 2017 | Concreting of Drainage Canal Cover Along National Highway, Brgy. Villareal | Villareal | 678571.43 | 2017-11-16 | 2019-12-31 | 90% | 491510.65 |  | Pending: Due to transfer of site location, Barangay & SP resolution on process | 271-002-1708-G0044
260 | 10710020-006-0014 | 2017 | Construction of Flat Slab Bridge Connecting Barangay Proper to Purok Malinong, Brgy. Villasol | Villasol | 1078571.43 | 2018-02-15 | 2019-04-30 | 100% | 1023638.83 |  |  | 266-003-1708-G0026
261 | *10710030-030-0098 | 2017 | Construction of Multi-Purpose Pavement at Sitio Manghakayhakay, Brgy. Villasol | Villasol | 600000 | 2017-12-16 | 2018-03-31 | 100% | 560025.05 |  |  | 264-009-1708-G0586
262 | 10710020-002-0050 | 2017 | Improvement/Rehabilitation of Water Systems for Various Barangays | Various Brgys | 934500 |  |  |  | 575402.78 |  | Turn-over to BAWAD | 269-001-1711-g0050
263 | 10710030-030-0195 | 2017 | Installation of Water Refilling Stations at Various Barangays | Various Brgys | 2200000 | 2019-01-21 |  | 48% | 1054599.9 |  | Pending: Building is not yet ready
264 | 10710030-030-0094 | 2017 | Construction of Multi-Purpose Pavement at Sitio Bolo, Brgy. Villasol | Villasol | 600000 | 2018-02-16 | 2018-06-30 | 100% | 563177.77 |  |  | 264-009-1708-g0580
265 | 264-009-1712-g0605 | 2017 | Construction of Multi-Purpose Building in Barangay Tayawan | Tayawan | 900000
266 | 0 | 2017 | Construction of Multi-Purpose Building in Barangay San Jose | San Jose | 900000 |  |  |  | 0 |  |  | 0
267 | *10710030-006-0018 | 2017 | Electrification Project for Various Barangays | Various Brgys | 10000 | 2018-06-01 | 2018-06-15 | 100% | 9060.49 |  |  | 0
268 | *10710020-007-0018 | 2017 | Construction of Drainage Canal at Cansumalig High School | Cansumalig | 150000 | 2017-12-16 | 2018-03-30 | 100% | 126833.17 |  |  | 271-002-1708-G0045
269 | 10710010-002-0004 | 2017 | Construction of Perimeter Fence of Multi-Purpose Building, Brgy. San Miguel | San Miguel | 100000 | [6 empty] | 264-009-1712-g0610
270 | 10710020-002-0086 | 2017 | Improvement of Water Systems of Guintanaan Tayawan | Tayawan | 100000 |  |  |  | 3058 |  | Turn-over to BAWAD | 0
271 | 10710020-002-0046 | 2017 | Improvement of Water Systems at Manduao | Manduao | 110000 |  |  |  | 16811.66 |  | Turn-over to BAWAD | 269-001-1708-g0046
272 | 0 | 2017 | Installation of Solar-Driven Water System for Catumbalan, Minaba | Minaba | 100000 |  |  |  | 0 |  | Turn-over to BAWAD | 0
273 | 10710030-006-0015 | 2017 | Installation of Solar-Driven Water System for Oban-Oban, Brgy. Kalumboyan | Kalumboyan | 50000 |  |  |  | 13835.24 |  | Turn-over to BAWAD | 264-005-1711-g0062
274 | 0 | 2017 | Installation of Solar-Driven Water Systems for Napo, Brgy. Tayawan | Tayawan | 50000 |  |  |  | 0 |  | Turn-over to BAWAD | 0
275 | 0 | 2017 | Construction of Multi-Purpose Pavement at Sitio Upper Manlubid, Ali-is | Ali-is | 50000 |  |  |  | 0 |  |  | 0
276 | *10710030-030-0095 | 2017 | Construction of Multi-Purpose Pavement at Inner Canabuan, Minaba | Minaba | 300000 | 2018-02-16 | 2018-06-30 | 100% | 286328.7 |  |  | 264-009-1708-G0581
277 | 269-001-1712-g0052 | 2017 | Improvement of Water System at Sitio Pag-awitan, Brgy. Ali-is | Ali-is | 50000 |  |  |  | 35325 |  | Turn-over to BAWAD
278 | 10710020-002-0089 | 2017 | Rehabilitation and Improvement of Water System at Brgy. Banaybanay | Banaybanay | 220000 |  |  |  | 111151.8 |  | Turn-over to BAWAD | 0
279 | 10710030-004-0004 | 2017 | Improvement of Barangay Public Market, Brgy. Malabugas | Malabugas | 50000 |  |  |  | 0 |  |  | 264-003-1712-g0022
280 | 10710030-006-0016 | 2017 | Installation of Electrical System in Sitio Buli-buli, Brgy. Banga | Banga | 60000 | 2019-02-01 | 2019-02-28 | 100% | 43514.9 |  |  | 264-005-1711-g0063
281 | 0 | 2017 | Installation of Electrical System in Brgy. Kalamtukan | Kalamtukan | 60000 |  |  |  | 60000 |  |  | 0
282 | 10710030-006-0014 | 2017 | Installation of Electrical System in Brgy. Kalumboyan | Kalumboyan | 70000 | 2019-06-16 | 2019-07-31 | 100% | 54252.49 |  |  | 264-005-1708-G0061
283 | 269-001-1801-g0057 | 2017 | Improvement of Water System, Brgy. San Roque | San Roque | 70000 |  |  |  | 47394 |  | Turn-over to BAWAD
284 | *10710020-002-0054 | 2017 | Improvement of Water System, Brgy. Ubos | Ubos | 145000 | 2018-06-01 | 2018-06-15 | 100% | 136216.2 |  |  | 0
285 | 0 | 2017 | Improvement of Water System at Brgy. Villasol | Villasol | 70000 |  |  |  | 62346 |  | Turn-over to BAWAD | 0
286 | 10710030-030-0096 | 2017 | Construction of Multi-Purpose Pavement at Sitio Ponong, Brgy. Villasol | Villasol | 100000 |  |  |  | 62715.89 |  | Pending: Road not yet passable | 264-009-1708-G0584
287 | *10710030-006-0012 | 2017 | Installation of Electrical System at Sitio Malampa, Brgy. Pagatban | Pagatban | 50000 | 2018-06-01 | 2018-06-30 | 100% | 44857.31 |  |  | 264-005-1708-G0059
288 | 0 | 2017 | Improvement of FMR at Brgy. Banaybanay | Banaybanay | 100000 |  |  |  | 0 |  |  | 0
289 | *10710030-006-0013 | 2017 | Installation of Electrical System in Brgy. Malabugas | Malabugas | 50000 | 2018-03-16 | 2018-04-30 | 100% | 46024.73 |  |  | 264-005-1708-G0060
290 | 10710020-002-0051 | 2017 | Improvement of Canabuan Water System, Brgy. Minaba | Minaba | 200000 |  |  |  | 62827.91 |  |  | 269-001-1711-g0051
291 | *10710020-001-0080 | 2017 | Slope Protection at Barangay Proper, San Isidro | San Isidro | 50000 | 2017-11-16 | 2018-01-31 | 100% | 48807.67 |  |  | 266-001-1708-G0395
292 | 264-009-1711-g0596 | 2017 | Improvement of Barangay Multi-Purpose Hall, Brgy. Ali-is | Ali-is | 200000 |  |  |  | 0
293 | 10710030-030-0097 | 2017 | Construction of Multi-Purpose Pavement at Purok 2, Brgy. Kalamtukan | Kalamtukan | 250000 | 2018-01-16 | 2018-06-30 | 100% | 224233.82 |  |  | 264-009-1708-G0585
294 | *10710020-001-0071 | 2017 | Installation of Street Lights at Purok 4, Cansilong, Brgy. Malabugas | Malabugas | 100000 | 2018-03-16 | 2018-05-31 | 100% | 90521.66 |  |  | 266-004-1708-G0057
295 | 10710020-001-0078 | 2017 | Improvement of FMR at Sitio Napit-an, Brgy. Maninihon | Maninihon | 220000 | 2018-04-01 | 2018-07-31 | 100% | 189414.53 |  |  | 266-001-1708-g0400
296 | 0 | 2017 | Improvement of Water System, Brgy. Minaba | Minaba | 110000 |  |  |  | 93457 |  |  | 0
297 | 10710020-001-0082 | 2017 | Improvement of FMR at Sitio Ondol, Brgy. Nangka | Nangka | 100000 | 2018-04-01 | 2018-08-31 | 100% | 95011 |  |  | 266-001-1709-G0406
298 | 0 | 2017 | Installation of Electrical System for Purok Ipil-Ipil, Brgy. San Roque | San Roque | 200000 |  |  |  | 0 |  |  | 0
299 | *10710020-001-0077 | 2017 | Road Improvement at Brgy. Ubos | Ubos | 170000 | 2018-01-01 | 2018-02-15 | 100% | 148018.03 |  |  | 266-001-1708-g0397
300 | *10710020-030-0002 | 2017 | Construction of Pathway to Banay-Banay Proper | Banay-Banay | 100000 | 2017-10-16 | 2018-02-28 | 100% | 89325.07 |  |  | 266-001-1708-g0399
301 | 0 | 2017 | Construction of Alternative Learning System (ALS) Building, Brgy. Kalumboyan | Kalumboyan | 200000 |  |  |  | 0 |  |  | 0
302 | 10710020-001-0084 | 2017 | Road Opening from National Highway to Purok 1 Pasil, Brgy. Malabugas | Malabugas | 150000 |  |  |  | 70424.49 |  | No ROW | 266-001-1711-g0409
303 | 10710020-002-0048 | 2017 | Installation of Deep Well at Atilano Cabangal High School, Brgy. Nangka | Nangka | 250000 |  |  |  | 10606.87 |  | Pending: re-PR magsaysay type deepwell not available anymore in the market | 269-001-1707-g0045
304 | 10710020-002-0081 | 2017 | Installation of Water System at Brgy. Pagatban | Pagatban | 50000 | 2018-03-16 | 2019-06-30 | 100% | 41977.04 |  |  | 269-001-1801-g0058
305 | 10710020-001-0083 | 2017 | Improvement of FMR at Sitio San Ramon, Brgy. Poblacion | Poblacion | 150000 | 2018-04-01 | 2018-08-31 | 100% | 143423.48 |  |  | 266-001-1709-G0407
306 | *10710020-002-0045 | 2017 | Improvement of Water System at Purok Dol-Dol, Brgy. San Roque | San Roque | 100000 | 2017-11-16 | 2018-01-31 | 100% | 69781.89 |  |  | 269-001-1707-g0044
307 | *10710020-007-0016 | 2017 | Construction of Concrete Covered Canals, Brgy. Tinago | Tinago | 50000 | 2017-10-01 | 2017-10-31 | 100% | 46908.05 |  |  | 271-002-1708-G0043
308 | *10710020-007-0019 | 2017 | Construction of Concrete Covered Canals, Brgy. Ubos | Ubos | 100000 | 2017-10-16 | 2017-11-30 | 100% | 84467.6 |  |  | 271-002-1708-G0046
309 | 264-009-1712-g0607 | 2017 | Improvement of Multi-Purpose Gym & Evacuation Center, Brgy. San Isidro | San Isidro | 495000 |  |  |  | 0
310 | *10710030-030-0092 | 2017 | Construction of Multi-Purpose Pavement, Brgy. Dawis | Dawis | 340000 | 2017-11-01 | 2018-02-28 | 100% | 326849.92 |  |  | 264-009-1708-g0578
311 | *10710020-007-0015 | 2017 | Construction of Concrete Covered Canal, Brgy. Suba | Suba | 400000 | 2017-08-16 | 2018-01-31 | 100% | 360021.69 |  |  | 271-002-1708-G0042
312 | 264-009-1712-g0604 | 2017 | Construction of Multi-Purpose Building at Relocation Site, Brgy. San Miguel | San Miguel | 500000
313 | 10710020-001-0070 | 2017 | Rehabilitation of Farm to Market Road from Sitio Bosque to Tavera, Barangay Nangka | Nangka | 1000000 |  |  |  | 439057.6 |  |  | 266-001-1706-g0393
314 | 10710030-030-0193 | 2017 | Construction of CICL at BADC Magsulay, Barangay Narra | Narra | 1000000 | 2018-09-10 |  | 37% | 1000000 |  | Temporarily stopped: Suspended due site location | 0
315 | budget data | 2017 | Purchase of Livestock Breeding Stocks |  | 533460 |  |  | 100% | 515555.56
316 | no obligation | 2017 | Purchase of Lot(Road Right of Way for Various Road Projects) |  | 2980124.07 |  |  |  | 0
317 | 0 | 2017 | Const. of Livelihood Center for Women at Brgy Villasol Proper |  | 100000 |  |  |  | 0 |  |  | 0
318 | 10710030-030-0104 | 2017 | Construction of Multi-purpose Pavement at Sitio Kaayahan (Phase 1) |  | 100000 |  |  |  | 62571.46 |  |  | 264-009-1710-G0591
319 | *10710030-030-0103 | 2017 | Completion of Multi-purpose Pavement at Sitio Tangistangisan |  | 330000 | 2018-02-01 | 2018-06-30 | 100% | 306358.29 |  |  | 264-009-1709-G0590
320 | *10710020-007-0020 | 2017 | Construction of Concrete Covered Canal at Zamora St. Brgy Suba |  | 173060.9 | 2017-08-16 | 2018-01-31 | 100% | 170642.5 |  |  | 271-002-1709-G0049
321 | *10710020-007-0021 | 2017 | Construction of Concrete Canal Cover Along Rizat St. Brgy Tinago |  | 1000000 | 2017-11-16 | 2018-03-31 | 100% | 678776.75 |  |  | 271-002-1709-G0047
322 |  |  | Water Supply Systems
323 | 10710020-002-0082 | 2017 | Development of Water System at Sitio Tavera, Nangka |  | 5700000 |  |  | 28.3% | 2367310.55 |  | Turn-over to BAWAD | 269-001-1709-G0049
324 | *10710020-002-0087 | 2017 | Improvement of Cabatangan-Tavera Water System |  | 154784.58 | 2019-01-16 | 2019-03-31 | 100% | 133057.22
325 |  |  | Parks, Plazas & Monuments
326 | 0 | 2017 | Improvement of Sports Center and Children's Playground, Boulevard |  | 1000000 |  |  |  | 0 |  |  | 0
327 |  |  | School Buildings
328 | 10710030-002-0018 | 2017 | Establishment of Early Child Development Center |  | 2300000 | 2018-03-31 | 2019-12-15 | 99.79% | 2106628.3 |  |  | 264-009-1709-g0589/264-002-1711-g0080/81/82
329
330 |  |  | Other Structures
331 | no obligation | 2017 | Construction of Workshop Area for Bayawan City Technology & Livelihood Development Center (BCTLDC) |  | 3000000 |  |  |  | 0
332 |  | 2017 | Purchase of Workshop Tools and Equipment for BCTLDC:
333 |  | 2017 | Furniture & Fixtures
334 |  | 2017 | 3 units Exhaust Fan |  | 4500 |  |  | 100% | 4500
335 |  | 2017 | 3 units Industrial Fan |  | 19656 |  |  | 100% | 19656
336 |  | 2017 | 4 units White Board with Movable Stand |  | 11000 |  |  | 100% | 11000
337 |  | 2017 | 3 units White Board (4x8x3/4) |  | 9900 |  |  | 100% | 9900
338 |  | 2017 | Machinery |  |  |  |  | 100%
339 |  | 2017 | 18 units Arc Welding Machine AC/DC & Acc |  | 698040 |  |  | 100% | 698040
340 |  | 2017 | Communication Equipment |  |  |  |  | 100%
341 |  | 2017 | 1 unit LCD projector |  | 26000 |  |  | 100% | 22995
342 |  | 2017 | Disaster Response & Rescue Equipment |  |  |  |  | 100%
343 |  | 2017 | 4 units Fire Extinguishers |  | 12364 |  |  | 100% | 12364
344 |  | 2017 | Military, Police & Security Equipment |  |  |  |  | 100%
345 |  | 2017 | 1 Set Security Equipment Access Control (CCTV) |  | 29845 |  |  | 100% | 29845
346 |  | 2017 | Other Machinery & Equipment |  |  |  |  | 100%
347 |  | 2017 | 6 units Work Bench w/ Bench Vice on 4 Corners |  | 204000 |  |  | 100% | 204000
348 |  | 2017 | 25 sets Combination Spanner (6mm to 24 mm) |  | 80000 |  |  | 100% | 80000
349 |  | 2017 | 12 units Blow Torch |  | 18000 |  |  | 100% | 18000
350 |  | 2017 | 12 units Clamp on Meter |  | 36000 |  |  | 100% | 36000
351 |  | 2017 | 6 units Portable Electric Drill |  | 30000 |  |  | 100% | 30000
352 |  | 2017 | 6 units Portable Planer |  | 51600 |  |  | 100% | 51600
353 |  | 2017 | 6 units Portable Circular Saw |  | 47220 |  |  | 100% | 47220
354 |  | 2017 | 25 pcs Welding Positioners |  | 96250 |  |  | 100% | 96250
355 |  | 2017 | 6 units Electrode Oven |  | 24000 |  |  | 100% | 24000
356 |  | 2017 | 25 units Portable Disc Grinder |  | 78750 |  |  | 100% | 78750
357 |  | 2017 | 6 units Pipe Threader 1/2-2" |  | 343200 |  |  | 100% | 343200
358 |  | 2017 | 6 units Pipe Bender |  | 26400 |  |  | 100% | 26400
359 |  | 2017 | 6 units Heat Gun 1200 watts |  | 18900 |  |  | 100% | 18900
360 |  | 2017 | 6 units Bolt Cutter |  | 7680 |  |  | 100% | 7680
361 |  | 2017 | 12 pcs Box Wrench |  | 58800 |  |  | 100% | 58800
362 |  | 2017 | 12 pcs Wire Splicer |  | 25320 |  |  | 100% | 25320
363 |  | 2017 | 12 pcs Wire Stripper |  | 25320 |  |  | 100% | 25320
364 |  | 2017 | 12 units Electric Drill |  | 58800 |  |  | 100% | 58800
365 |  | 2017 | 12 units Portable Grinder |  | 52500 |  |  | 100% | 52500
366 |  | 2017 | 6 units Pipe Cutter (1/2"-1") |  | 31590 |  |  | 100% | 31590
367 |  | 2017 | 3 units Manual Pipe Threader (1/2", 3/4", 1") |  | 33705 |  |  | 100% | 33705
368 |  | 2017 | 3 units Fusion Machine (20mm-32mm) |  | 34020 |  |  | 100% | 34020
369 |  | 2017 | 4 units Electric Grinder (4") |  | 20520 |  |  | 100% | 20520
370 |  | 2017 | 12 units Angle Grinder |  | 61560 |  |  | 100% | 61560
371 |  | 2017 | 2 units Labelling Machine |  | 2200 |  |  | 100% | 2200
372 |  | 2017 | 6 units Insulation Resistance Tester |  | 9900 |  |  | 100% | 9900
373 |  | 2017 | 6 units Earth Resistance Tester |  | 13200 |  |  | 100% | 13200
374 |  | 2017 | 4 units Pedestal/Bench Grinding Machine |  | 9400 |  |  | 100% | 9400
375 |  | 2017 | 10 units Panel Board with 70 amp main & 4 |  | 34450 |  |  | 100% | 34450
376 |  | 2017 | 25 pcs Electrician Pliers |  | 66250 |  |  | 100% | 66250
377 |  | 2017 | Other Property, Plant & Equipment
378 |  | 2017 | 3 units Wheelbarrow |  | 6600 |  |  | 100% | 6000
379 |  | 2017 | 6 sets Oxy-Acetylene/Oxy-LPG Cutting Outfit |  | 72000 |  |  | 100% | 72000
380 |  | 2017 | 6 units Plastic Drum (200 liters) |  | 10560 |  |  | 100% | 10560
381
382 |  |  | Power Supply System
383 |  | 2017 | Purchase of 50 KVA Transformer for BCTLDC |  | 500000 |  |  |  | 0
384 |  |  | Hospital and Health Centers
385 |  | 2017 | Construction of City Health Office Building |  | 1000000
386 |  | 2018 | Loan Amortization |  | 9809031.89 |  |  |  | 0
387 |  | 2018 | Lot Acquisition for Development Projects |  | 1754285.71 |  |  |  | 0
388 |  | 2018 | Purchase of Lot for Multi-Purpose Hall at Sitio Cambulo. Banga |  | 600000 |  |  |  | 0
389 | 10710020-001-0112 | 2018 | Widening of Malabugas-San Roque Road |  | 3500000 | 2019-09-01 | 2019-12-31 | 30% | 931407.77
390 | 10710020-001-0095 | 2018 | Concreting of Road Approaching Lapay Box Culvert with Slope Protection, Dawis | Bayawan Creek, Dawis | 1000000 | 2018-04-01 | 2018-08-31 | 100% | 746162.76
391 | 10710020-001-0094 | 2018 | Concreting of Road Approaching Candalaga Box Culvert with Slope Protection, Nangka | Nangka | 1000000 | 2018-04-01 | 2018-11-30 | 100% | 870445.24
392 | 10710020-001-0098 | 2018 | Concreting of Road Approaching Pusi-on Box Culvert with Slope Protection, Maninihon | Maninihon | 1000000 | 2018-04-01 | 2019-02-28 | 100% | 851903.96
393 | 10710020-001-0093 | 2018 | Concreting of Road Approaching Camandagan Box Culvert with Slope Protection, Maninihon | Maninihon | 1000000 | 2018-04-01 | 2018-09-30 | 100% | 787342.62
394 | 10710020-001-0091 | 2018 | Concreting of Road Approaching Balao Box Culvert with Slope Protection, San Miguel | San Miguel | 1000000 | 2018-04-01 | 2018-10-30 | 100% | 828417.41
395 | 10710020-001-0096 | 2018 | Concreting of Road Approaching Magsakang Box Culvert with Slope Protection, Tayawan | Tayawan | 1000000 | 2018-04-01 | 2019-07-31 | 100% | 851245.15
396 | 10710020-006-0016 | 2018 | Completion of Magsakang Flat Slab Bridge, Tayawan | Tayawan | 1000000 | 2018-04-01 | 2019-04-30 | 100% | 954259.8
397 | 10710020-001-0097 | 2018 | Concreting of Road Approaching Pamuat Box Culvert with Slope Protection, San Isidro | San Isidro | 1000000 | 2018-04-01 | 2019-06-30 | 100% | 928312.72
398 | 10710020-001-0092 | 2018 | Concreting of Road Approaching Binanigan Box Culvert with Slope Protection, Tayawan | Tayawan | 1000000 | 2018-04-01 | 2018-09-30 | 100% | 760523.42
399 | *10710020-001-0086 | 2018 | Concreting of Road at Purok 7, Barangay Tinago | Tinago | 2000000 | 2018-02-16 | 2018-08-31 | 100% | 1714331.49
400 | 10710020-001-0088 | 2018 | Concreting of Dawis-Lapay FMR | Bayawan City | 5500000 | 2018-04-01 | 2019-07-31 | 100% | 4536505.09
401 | 10710020-001-0087 | 2018 | Concreting of Banga-San Roque-Minaba-San Miguel-Tayawan FMR | Bayawan City | 5872000 | 2018-04-01 | 2019-06-30 | 100% | 5221497.1
402 | 10710020-001-0090 | 2018 | Concreting of Nangka-Narra FMR | Bayawan City | 5500000 | 2018-04-01 | 2019-05-31 | 100% | 4586263.85
403 | 10710020-001-0105 | 2018 | Concreting of Tabuan- Banaybanay-Lapay-Bugay-San Jose-Manduao FMR | Bayawan City | 28340000 | 2018-05-29 |  | 96.5% | 21144768.47
404 | 10710020-001-0103 | 2018 | Concreting of Road from Sitio Balastro to Sitio Candulion to Pulangyuta, Barangay Kalamtukan | Kalamtukan | 10500000 | 2018-08-01 | 2019-08-31 | 95% | 6516585.43
405 | 10710020-001-0104 | 2018 | Concreting of Road with Drainage Canal at Upper Napit-an, Maninihon | Maninihon | 300000 | 2018-04-01 | 2018-07-31 | 100% | 173965.88
406 | 10710020-001-0102 | 2018 | Concreting of Road from Highway Intersection to Minaba Elem. School, Brgy. Minaba | Bayawan City | 1000000 | 2018-04-01 | 2018-09-30 | 100% | 701735.4
407 | 10710020-001-0099 | 2018 | Concreting of Road at Sitio Kasla, Brgy. Nangka | Nangka | 850000 | 2018-04-01 | 2018-09-30 | 100% | 653409.03
408 | 10710020-006-0020 | 2018 | Construction of Flat Slab Bridge at Sitio Terong, Narra | Narra | 600000 | 2018-04-01 | 2019-06-30 | 100% | 520886.82
409 | 10710020-001-0107 | 2018 | Road Concreting from Proper Narra to Purok III, Brgy. Narra | Narra | 500000 | 2018-04-01 | 2018-10-16 | 100% | 394052.4
410 | 10710020-001-0089 | 2018 | Concreting of FMR from National Highway to Sitio Lapacon, Brgy. Pagatban | Bayawan City | 500000 | 2018-04-01 | 2018-08-31 | 100% | 394562.39
411 | 10710020-001-0100 | 2018 | Concreting of Road at Sitio Upper Pamu-at, San Isidro | San Isidro | 500000 | 2018-04-01 |  | 92.5% | 266044 |  | Temporarily Stopped: Road not yet passable; Materials delivered - 100%
412 | 10710020-001-0101 | 2018 | Concreting of Road at Upper Talao, San Isidro | San Isidro | 600000 | 2018-10-01 | 2019-03-31 | 100% | 514849.54
413 | 10710020-001-0108 | 2018 | Road Shouldering Along Zamora St., Brgy. Ubos | Ubos | 500000 | 2018-06-16 | 2018-11-30 | 100% | 428565.85
414 | 10710020-001-0110 | 2018 | Road Surfacing from Barangay Proper to Sitio Gawgaw to Sitio Aya, Brgy. Bugay | Bugay | 839286.43 | 2019-03-01 |  | 12% | 214010.55 |  | Pending: road not yet passable
415 | 10710020-001-0111 | 2018 | Road Surfacing from Barangay Proper to Sitio Mambuy-og to Sitio Canlantang, Brgy. Bugay | Bugay | 839285 | 2019-04-01 | 2019-12-31 | 92% | 337109.44
416 | 10710020-001-0109 | 2018 | Road Surfacing from Barangay Cansumalig | Cansumalig | 1078571.43 |  |  |  | 118966.57 |  | Pending: Road not yet passable
417 | 10710020-007-0026 | 2018 | Construction of Drainage Canal from Upper Napit-an to Lower Napit-an, Brgy. Maninihon | Maninihon | 650000 | 2018-06-01 | 2018-09-30 | 100% | 544106.01
418 | 10710020-004-0017 | 2018 | Installation of Cylindrical Culvert with Riprap at Proper Narra | Narra | 578571.43 | 2018-06-16 | 2019-08-31 | 100% | 495318.65
419 | 10710020-007-0025 | 2018 | Covering of Drainage Canals along Gomez St., Brgy. Ubos | Ubos | 1078571.43 |  |  |  | 542372.16 |  |  | GSO
420 | 0 | 2018 | Construction of Small Scale Irrigation Projects (SSIP): | Bayawan City
421 | 10710020-003-0007 | 2018 | a. Purok Mangga, Brgy. Manduao | Manduao | 800000 |  |  |  | 569072.95
422 | 10710020-003-0008 | 2018 | b. Sitio Dita, Brgy. Tabuan | Tabuan | 800000 |  |  |  | 299129.89
423 | 10710020-003-0009 | 2018 | c. Upper Canlinte, Brgy Ali-is | Ali-is | 800000 |  |  |  | 380721.33
424 | 10710020-003-0010 | 2018 | Rehabilitation of Irrigation Canal at Brgy. Tabuan | Tabuan | 915000 | 2019-03-01 |  | 95% | 765127.66 |  | Turn-over to BAWAD
425 | 10710020-002-0057 | 2018 | Water System Development at Bugay Proper | Bugay | 500000 |  |  |  | 148710.4 |  | Turn-over to BAWAD
426 | 10710020-002-0056 | 2018 | Development of Water System at Brgy. Villareal | Villareal | 1000000 |  |  |  | 327600 |  | Turn-over to BAWAD
427 | 10710020-001-0113 | 2018 | Installation of Street Lighting from Purok 1 to Purok IV, Brgy. Tayawan | Tayawan | 500000 |  |  |  | 144025.62
428 | 10710020-009-0001 | 2018 | Improvement of Barangay Plaza and Children's Park, Tayawan | Tayawan | 500000 |  |  |  | 24636.1
429 | 0 | 2018 | Establishment of Early Child Care Dev't Centers: | Bayawan City
430 | 10710030-002-0021 | 2018 | a. Brgy. Villareal | Villareal | 5000000 |  |  |  | 20850.19
431 | 10710030-002-0022 | 2018 | b. Brgy. Malabugas | Malabugas | 5000000 | 2018-06-21 |  | 95% | 4436517.58
432 | 10710030-002-0023 | 2018 | Construction of Day Care Center at Sitio Mantapi, Nangka | Nangka | 578571.43 |  |  |  | 324562.46 |  |  |  | GSO
433 | 0 | 2018 | Improvement of Barangay Health Center & Lying-In Clinic, Brgy. Malabugas | Malabugas | 1000000 |  |  |  | 0
434 | 10710030-003-0008 | 2018 | Construction of Health Center at Sitio Mantapi, Nangka | Nangka | 500000 |  |  |  | 110023.07 |  |  |  | GSO
435 | 0 | 2018 | Construction of Barangay Public Market, Ali-is (Phase 1) | Bayawan City | 1000000 |  |  |  | 0
436 | 10710030-005-0001 | 2018 | Completion of Minaba Mini Slaughterhouse Phase III | Minaba | 500000 | 2018-10-16 | 2019-07-31 | 100% | 419375.96
437 |  | 2018 | Construction of Rainwater Harvesting Systems for Nurseries:
438 | 10710020-002-0075 | 2018 | a. Brgy. San Miguel | San Miguel | 250000 | 2018-10-01 | 2018-11-30 | 100% | 193602.58
439 | 10710020-002-0076 | 2018 | b. Brgy. Tayawan | Tayawan | 250000 | 2018-10-16 | 2019-05-31 | 100% | 190464.82
440 | 10710020-002-0077 | 2018 | c. Brgy. Cansumalig | Cansumalig | 250000 | 2018-10-16 | 2019-06-30 | 100% | 166198.33
441 | 10710020-002-0078 | 2018 | d. Brgy. Manduao | Manduao | 250000 |  |  |  | 90276.74
442 | 10710020-002-0079 | 2018 | e. Brgy. Kalamtukan | Kalamtukan | 250000 |  |  |  | 116439.5
443 | 10710030-030-0138 | 2018 | Construction of Bleachers at Barangay Evacuation Center, Ali-is | Ali-is | 678571.43 | 2018-04-01 | 2019-04-30 | 100% | 555739.56
444 | 10710030-030-0146 | 2018 | Improvement of Barangay Multi-Purpose Building, Banaybanay | Banaybanay | 1000000 |  |  |  | 0 |  | CONTRACT
445 | 10710030-030-0150 | 2018 | Improvement of Barangay Multi-Purpose Hall, Brgy. Boyco | Boyco | 1678571.43 |  |  |  | 0 |  | CONTRACT
446 | 10710030-030-0144 | 2018 | Construction of Barangay Multi-Purpose Building, Cansumalig | Cansumalig | 1300000 | 2019-07-16 |  | 25% | 737028.54
447 | 10710030-002-0024 | 2018 | Construction of Feeding Center at Damig Elementary School, Brgy. Kalamtukan | Kalamtukan | 778571.43 |  |  |  | 0 |  | CONTRACT
448 | 10710030-030-0147 | 2018 | Improvement of Barangay Multi-Purpose Building, Maninihon | Maninihon | 1000000 |  |  |  | 140346.6 |  | CONTRACT
449 | 10710030-030-0155 | 2018 | Construction of Multi-Purpose Pavement at Sitio Mantapi, Nangka | Mantapi, Nangka | 600000 | 2018-07-01 | 2018-12-31 | 100% | 546309.58
450 | 10710030-030-0148 | 2018 | Construction of Barangay Multi-Purpose Building, Narra | Narra | 1000000 |  |  |  | 0
451 | 10710010-002-0005 | 2018 | Construction of Concrete Perimeter Fence of Covered Court and Evacuation Center, Brgy. Pagatban | Pagatban | 100000 | 2018-07-01 | 2018-08-31 | 100% | 86496.06
452 | 10710030-030-0145 | 2018 | Construction of Multi-Purpose Building, Brgy. San Isidro (Phase 2) | San Isidro | 1078571.43 | 2019-08-01 |  | 25% | 479335.65
453 | 10710030-030-0137 | 2018 | Construction of Children and Women's Crisis Center, Brgy. Suba | Suba | 600000 |  |  |  | 0
454 | 10710030-030-0153 | 2018 | Improvement of Multi-Purpose Hall, Brgy. Suba | Suba | 578571.43 |  |  |  | 0
455 | 10710030-030-0149 | 2018 | Construction of Multi-Purpose Hall, Brgy. Tinago | Tinago | 2278571.43 |  |  |  | 0
456 | 10710030-030-0159 | 2018 | Construction of Fish Processing Center @ Brgy. Suba | Suba | 2500000 | 2019-04-01 | 2019-12-31 | 80% | 1918428.71 |  |  |  | GSO
457 | 10710030-030-0152 | 2018 | Improvement of Multi-Purpose Hall, Banga | Banga | 2078571.43 |  |  |  | 0
458 | 10710030-030-0161 | 2018 | Major Repair of Narra Barangay Agricultural Development Center (BADC) | Narra | 520000 |  |  |  | 304815.17 |  |  |  | GSO
459 | 10710030-030-0160 | 2018 | Major Repair of Manduao Barangay Agricultural Development Center (BADC) | Manduao | 290000 |  |  |  | 179168.68 |  |  |  | GSO
460 | 10710030-030-0151 | 2018 | Improvement of Barangay Multi-Purpose Hall, Manduao | Manduao | 600000 |  |  |  | 440893.31
461 | no obligation | 2018 | Purchase of Boom Truck | Bayawan City | 1600000 |  |  |  | 0
462 |  | 2018 | Purchase of 1 Unit Backhoe for Barangay Tayawan | Tayawan | 1678571.43 |  |  |  | 0
463 |  | 2018 | Purchase of Garbage Compactor Truck | Bayawan City | 1500000 |  |  |  | 0
464 | 10701010-001-0129 | 2018 | Purchase of Lot for Agricultural Research Center | Maninihon | 16000000 |  |  | 100% | 15710989
465 | 0 | 2018 | Establishment of Agricultural Research Center | Maninihon | 6895568.71 |  |  |  | 0
466 | 10710020-001-0125 | 2018 | Improvement of Bugay-San Jose-Manduao FMR | Bayawan City | 3000000 | 2018-10-15 | 2019-01-06 | 100% | 2959185.3
467 | 10710020-001-0127 | 2018 | Concreting of Urban Roads with Drainage System (GomeZ St.) | Poblacion | 12885436.16 | 2019-01-16 |  | 85% | 7856967.44
468 |  | TOTAL EDF CONTINUING APPROPRIATION |  |  | 485745064.02 |  |  |  | 296186115.63
469 |  | TOTAL EDF - CURRENT & CONTINUING APPROPRIATION |  |  | 688414349.51 |  |  |  | 363811777.6
|  |  | CORAZON P. LIRAZAN, CPA | [5 empty] | HON. PRYDE HENRY A. TEVES
|  |  | City Accountant | [5 empty] | City Mayor
26 | reverted SB10 | 2019 | Establishment of Cotton Ginnery and Spinning Center |  | 10000000
27 | reverted SB10 | 2019 | Site Improvement of Bayawan City Waste Management & Ecology Center |  | 9300000
Note on F29: MARY DECEE B. RIZADA: 16m reverted sb11
Note on L39: MARY DECEE B. RIZADA: On-Going: We cannot predict 100% completion due to the recent procurement process of materials
Note on L40: MARY DECEE B. RIZADA: On-Going: We cannot predict 100% completion due to the recent procurement process of materials
Note on L41: MARY DECEE B. RIZADA: On-Going: We cannot predict 100% completion due to the recent procurement process of materials
Note on L46: MARY DECEE B. RIZADA: On-Going: We cannot predict 100% completion due to the recent procurement process of materials
Note on L67: MARY DECEE B. RIZADA: deposit for expropriation case regarding adjacent lots for sanitary landfill (2007)
Note on L82: MARY DECEE B. RIZADA: obligation per SAAOB
Note on L106: MARY DECEE B. RIZADA: Physically Completed, For COC issuance
Note on L155: MARY DECEE B. RIZADA: Ford Tractor, Phils. PIS 100-17-05-0049
Note on L242: MARY DECEE B. RIZADA: why not yet started
Note on L255: MARY DECEE B. RIZADA: Temporary stopped: Road not yet passable
Note on L256: MARY DECEE B. RIZADA: Temporarily Stopped: No Heavy Equipment available
Note on L265: MARY DECEE B. RIZADA: Pending: Due to transfer of site location and Barangay & SP resolution on process
Note on L273: MARY DECEE B. RIZADA: Physically Completed, obligation per SAAOB
Note on L470: MARY DECEE B. RIZADA: Site-Napit-an, Brgy. Maninihon; TD No. 2016-04-0013-02364;