## EDITED MARCH 2020
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION REPORT
As of March 31, 2020
CITY OF BAYAWAN
[5 empty] | Location | Total Cost (per Budget Approp) | Target Start Date | Target Completion Date | Project Status |  | No. of Ext., if any | Remarks
1 | Project Code | Year |  | Program/Project |  |  |  |  | % of Completion | Total Cost Incurred (per Acctg)
3 |  | CURRENT APPROPRIATION
4
SOCIAL DEVELOPMENT
|  | 2019 |  | Construction of Multi-Purpose Pavement at Sitio -Upper Pinangimnan | San Jose | 839285.7 | 2020-04-15 |  | 20% |  |  | On-going: Advance Implementation
|  | 2019 |  | Construction of Multi-Purpose Pavement at Sitio Pitogo 1 | San Jose | 839285.73 | 2020-04-15 |  | 20% |  |  | On-going: Advance Implementation
7 |  | 2019 |  | Lot Acquisition for Dita Relocation | Tabuan | 5000000
23 | 0 | 2019 |  | Construction & Installation of Water Supply Systems for Barangays Malabugas, San Roque, Minaba, San Miguel and Tayawan | Various Brgys | 11000000 | [5 empty] | Implemented by BAWAD
28 | 10710030-002-0028 | 2019 |  | Construction of Day Care Center, Brgy San Miguel | Bayawan City | 400000 | 2019-07-16 | 2019-09-30 | 100% | 231032.84 |  | Physically Completed: COC Issued 01/23/2020
25 | 0 | 2019 |  | Electrification Project at Purok Ipil-Ipil, San Roque | San Roque | 600000 | [5 empty] | Implemented by NORECO
33 | 10710010-002-0011 | 2019 |  | Construction of Concrete Fence of Minaba Elementary School | Minaba | 500000 | 2019-05-16 | 2020-03-31 | 90% | 206871.98 |  | Physically Completed: Materials delivered- 92%; for delivery - 4%; Re-ad- 4%
34 | 10710010-002-0013 | 2019 |  | Construction of Concrete Fence of Canabuan Elementary School | Minaba | 500000 | 2019-01-06 | 2020-03-31 | 90% | 222376.86 |  | On-Going; Materials delivered- 19%; for delivery-4%; re-ad-77% (P.O. cancelled); Procurement Problem; Temprary Stopped
35 | 10710010-002-0012 | 2019 |  | Construction of Concrete Fence of Minaba High School | Minaba | 678571.43 | 2019-01-06 | 2020-03-31 | 90% | 191587.41 |  | On-Going; Materials delivered- 20%; for delivery-4%; re-ad-76% (P.O. cancelled); Procurement Problem; Temporary Stopped
38 | 10710010-002-0015 | 2019 |  | Construction of Concrete Fence of Bolirocon Elementary School, San Isidro | Bolirocon, San Isidro | 278571.43 | 2019-01-08 | 2020-03-31 | 100% | 188217 |  | Physically Completed: Materials delivered- 92%; for delivery - 4%; Re-ad- 4%
40 | 10710010-002-0010 | 2019 |  | Construction of Perimeter Fence at San Roque Elementary School | San Roque | 578571.43 | 2019-01-06 | 2020-03-31 | 90% | 180751.8 |  | On-Going; Materials delivered- 20%; for delivery-4%; re-ad-76% (P.O. cancelled) ; Procurement Problem; Temporary Stopped
32 | 10710030-030-0198 | 2019 |  | Completion of Lapay Multi-Purpose Pavement | Dawis | 360000 | 2019-06-16 | 2019-08-31 | 100% | 211987.95 |  | Physically Completed: COC Issued 01/23/2020
36 | 10710030-030-0211 | 2019 |  | Construction of Barangay Multi-Purpose Building, Nangka | Nangka | 1678571.43 | 2019-06-30 | 2020-04-30 | 15% | 797308.96 |  | Materials delivered- 56%; for delivery- 3%; re-ad- 41%; For Implementation
37 | 10710030-030-0209 | 2019 |  | Construction of 2-Storey Multi-Purpose Building, Brgy. Poblacion | Poblacion | 1678571.43 | 2019-06-30 | 2020-06-30 | 30% | 498221.59 |  | Materials delivered- 27%; for delivery- 58%; re-ad- 25%
39 | 10710030-001-0012 | 2019 |  | Construction of Multi-Purpose Building, Barangay San Isidro (Phase 3) | San Roque | 1000000 | 2019-09-30 | 2020-07-31 | 8% | 86417.86 |  | Materials delivered - 6%;for delivery- 46%; re-ad- 48%
41 | 0 | 2019 |  | Construction of Barangay Multi-Purpose Building, Tinago (Phase 3) | Tinago | 1678571.43 | 2020-03-01 |  | 30% | 0 |  | On- Going
|  |  |  | Total Projects for Social Development - Current Appropriation |  | 27610000.01 |  |  |  | 2814774.25
ECONOMIC DEVELOPMENT
|  | 2019 |  | Supply & Installation of Hog & Cattle Slaughterhouse Equipment for Bayawan City AA Slaughterhouse Plant | Bayawan City | 16478571.43
|  | 2019 |  | Construction of Dawis Public Market (Phase 2) | Dawis | 2000000
5 |  | 2019 |  | Loan Amortization |  | 58000000 |  |  |  | 49166376.06
8 |  | 2019 |  | Lot Acquisition for Road Right of Way | Villareal | 500000
9 |  | 2019 |  | Lot Acquisition for Agricultural Development Center (Tan-ayan) | Tan-ayan | 2500000
11 | 10710020-001-0135 | 2019 |  | Wayang Access Road Development | Nangka | 20000000 | 2019-02-16 | 2020-04-30 | 75% | 10007792.96 |  | On- Going: Materials delivered- 97%; re-ad- 3%
12 | 10710020-002-0088 | 2019 |  | Construction of Ondol-Napit-an FMR | Bayawan City | 20000000 | 2019-03-15 | 2020-08-31 | 40% | 8057412.12 |  | Materials delivered- 97%; re-ad- 3%
13 | 10710020-001-0136 | 2019 |  | Concreting of Access Road from National Highway to Palongpong Agricultural Development Center | Bayawan City | 9000000 | 2019-01-04 | 2020-03-31 | 99% | 2731842.29 |  | On-Going; Materials delivered- 72%; partial delivery- 2%; for delivery- 10%; re-ad- 16%
14 | 10710020-001-0134 | 2019 |  | Improvement of Road Leading to Danapa Inland Aquaculture Facility | Nangka | 2000000 | 2019-03-16 | 2019-12-31 | 100% | 1138792.68 |  | Physically Completed: COC Issued 01/23/2020
15 | 10710020-001-0137 | 2019 |  | Concreting of Perimeter Road at BCWMEC | Maninihon | 2000000 | 2019-01-06 | 2020-02-15 | 100% | 1089250.38 |  | Physically Completed
16 | 10710020-001-0139 | 2019 |  | Concreting of Urban Roads with Drainage System (Gomez St.) | Poblacion | 3000000 | 2019-07-16 | 2020-03-31 | 80% | 1050985.38
17 | 10710020-001-0041 | 2019 |  | Improvement of Maninihon-Cansumalig-San Isidro FMR |  | 2387650.49
30 | 10710030-004-0006 | 2019 |  | Construction of Public Market Stalls in Omod, Maninihon (Phase 1) | Bayawan City | 1678571.43 | 2019-06-16 | 2020-05-31 | 80% | 1249810.6 |  | On-Going; Materials delivered - 96%; for delivery - 2%: re-ad - 2%
42 | 0 | 2019 |  | Establishment of Agricultural Research Center |  | 10877134.99 |  |  |  | 0
43 |  |  |  | Purchase of Construction & Heavy Equipment:
44 |  |  |  | 1 unit Bulldozer |  | 15000000 |  |  |  | 0
45 |  |  |  | 1 unit Backhoe |  | 12000000 |  |  |  | 0
46 |  |  |  | 1 unit Trailer Mounted DW100-T Drilling Rig with Accessories |  | 3594500 |  |  |  | 0
47 |  |  |  | 2 units 6-Wheeler Dump Truck |  | 4400000 |  |  |  | 0
52 |  | 2019 |  | Purchase of Livestock Breeding Stocks |  | 2000000 |  |  |  | 0
|  |  |  | Total Projects for Economic Development - Current Appropriation |  | 187416428.34 |  |  |  | 74492262.47
ENVIRONMENTAL MANAGEMENT
19 | 10710020-007-0030 | 2019 |  | Construction of Drainage Canal at Magsulay Agricultural Development Center | Narra | 400000 | 2019-07-16 | 2020-03-31 | 97% | 223061.75 |  | On-Going: Materials delivered- 100%
21 | 10710020-007-0029 | 2019 |  | Concreting of Drainage Canals at Barangay Proper, San Isidro | Bayawan City | 400000 | 2019-01-06 | 2019-08-31 | 100% | 331852.13 |  | Physically Completed: COC Issued 01/23/2020
49 |  | 2019 |  | Purchase of Garbage Compactor Truck |  | 5000000 |  |  |  | 0
50 |  | 2019 |  | Purchase of Vacuum Declogger Truck |  | 2000000 |  |  |  | 0
|  |  |  | Total Projects for Environmental Mgt - Current Appropriation |  | 7800000 |  |  |  | 554913.88
53 |  |  | TOTAL DF - CURRENT APPROPRIATION |  |  | 222826428.35 |  |  |  | 77861950.6
54
55
56 |  | CONTINUING APPROPRIATION
57
SOCIAL DEVELOPMENT
63 |  | 2011 |  | Renovation of BDH Canteen | BDH, Ubos | 114000 | 2011-06-01 | 2012-12-31 | 100% | 80418
66 | *10710030-030-0023 | 2012 |  | Improvement of Bayawan City Boulevard (Landscaping fronting GK Village) | Villareal | 535115.83 | 2013-08-01 | 2014-03-15 | 100% | 495907.52 |  | Physically Completed: COC issued on 05/23/18 ( Liquidating balances, Materials delivered - 93%; rebid - 7% ;# 12,16-rebid, P.O cancelled)
67 | *10710030-030-0021 | 2013 |  | Construction of Sports Center and Children's Playground, Phase 3 | Suba | 3000000 | 2013-03-18 | 2015-05-30 | 100% | 2668470.08 |  | Physically Completed: COC issued on 05/23/18; (delivered materials- 82%; for delivery-2%; re-bid-16%); ITEM# 35, 53, 54, 55 for Canvass & referred to BAC
68 | *10710030-030-0024 | 2013 |  | Construction of Covered Court at BCsTEC, Phase II | Cabcabon, Banga | 3008100 | 2013-10-01 | 2017-06-30 | 100% | 2783489.42 |  | Physically Completed: COC issued on 05/23/18
69 | 10710030-030-0025 | 2013 |  | Rehabilitation of GK Septic Tanks | Villareal | 3104400 | 2013-11-18 | 2020-12-31 | 2% | 77968.68 |  | Pending: sub-standard Fiber Glass septic Tank delivered by supplier not accepted by LGU
70 | *10710020-002-0036 | 2013 |  | Improvement of Water System for 21 Rural Barangays | Bayawan City | 568710 | 2016-07-01 | 2017-07-31 | 100% | 468013.78
82 | 10710030-030-0058 | 2015 |  | Construction of Evacuation Center, Brgy. San Miguel | San Miguel | 800000 | 2016-01-02 | 2019-10-31 | 100% | 602620.16
83 | *10710030-030-0059 | 2015 |  | Construction of Portable Toilet | Bayawan City | 770000 | 2016-01-15 | 2018-03-31 | 100% | 542396.04
84 | 10710010-002-0003 | 2015 |  | Const. of GK Village Perimeter Fence | Villareal | 2000000 | 2019-01-10 | 2020-12-31 | 95% | 1716184.88
96 | 10710020-002-0037 | 2015 |  | Water System Development @ Sitio Camague to Cabiguhan, Brgy Banaybanay | Banaybanay | 303389.8 | 2017-02-16 | 2020-12-31 | 50% | 206913.03 |  | Pending: Declared site has no water source
98 | 10710030-003-0001 | 2016 |  | Rehabilitation of Health Center & Const. of Lying-in Facility, Brgy. Poblacion, Phase 2 | Poblacion | 500000 | 2016-09-16 | 2017-06-30 | 100% | 320188.77
106 | 10710030-002-0010 | 2016 |  | Construction of Day Care Centers in Nangka and Napit-an/Rehabilitation of Day Care Centers in Minaba, Narra, Purok 4 Tayawan | Nangka, Napit-an, Minaba, Narra, Tayawan | 2000000 | 2017-01-06 | 2020-12-31 | 51.7% | 1442480.16 |  | Pending: 4 Units Completed, 1 unit not yet started due to no lot available
107 | *10710030-030-0079 | 2016 |  | Improvement of CICL Center Faciltities | Banga | 975000 | 2017-11-16 | 2019-03-31 | 100% | 764122.65
108 | *10710030-030-0081 | 2016 |  | Completion of Paglaum Center at Cabcabon | Cabcabon | 500000 | 2016-10-16 | 2018-05-31 | 100% | 352817.03
109 | *10710030-030-0069 | 2016 |  | Completion of Women's Multi-purpose Center | Boyco | 1000000 | 2016-12-01 | 2018-11-30 | 100% | 783751.69
110 | 10710030-030-0078 | 2016 |  | Construction of Women's Detention Cell | Banga | 400000 | 2019-07-29 | 2019-10-30 | 53% | 211222.56 |  | Cancelled as per instruction from DSWD
111 | 10710030-030-0067 | 2016 |  | Construction of Women's Facilities in Evacuation Center | Var. Brgys | 200000 | 2019-07-16 | 2020-03-31 | 98% | 168303.43 |  | Material Estimates is inadequate
112 | *10710030-002-0009 | 2016 |  | Construction of Day Care Center at Brgy. Proper, Brgy,. San Miguel | San Miguel | 500000 | 2016-08-16 | 2017-05-31 | 100% | 440367.22
113 | 10710030-030-0073 | 2016 |  | Const. of Bleachers & CRs @ Existing Gyms for evacuation (Tinago, Boyco, Suba,Poblacion, Banga, Malabugas, Villareal, BNHS) | Various Brgys | 6000000 | 2019-07-30 | 2019-07-31 | 100% | 5105050.96
114 |  |  |  | a. Tinago |  |  |  |  | 100%
115 |  |  |  | b. Boyco |  |  |  |  | 100%
116 |  |  |  | c. Suba |  |  |  |  | 100%
117 |  |  |  | d. Poblacion |  |  |  |  | 100%
118 |  |  |  | e. Banga |  |  |  |  | 100%
119 |  |  |  | f. Malabugas |  |  |  |  | 100%
120 |  |  |  | g.Villareal |  |  |  |  | 100%
121 |  |  |  | h. BNHS |  |  |  |  | 100%
123 | *10710030-030-0074 | 2016 |  | Const. of Comfort Rooms in 13 Evacuation Ctrs. | Var Brgys | 1054174.83 | 2019-04-30 | 2018-02-28 | 100% | 1056488.39
124 |  |  |  | a. Banga Central School |  |  |  |  | 100%
125 |  |  |  | b. BCSTEC Elementary & Highschool |  |  |  |  | 100%
126 |  |  |  | c. Malabugas Highschool |  |  |  |  | 100%
127 |  |  |  | d. Nangka Elementary School |  |  |  |  | 100%
128 |  |  |  | e. Guisocon Elementary School |  |  |  |  | 100%
129 |  |  |  | f. Atilano Cabangal Memorial Highschool |  |  |  |  | 100%
130 |  |  |  | g. Tavera Elementary School |  |  |  |  | 100%
131 |  |  |  | h. Dean Felix Gaudiel Memorial Elementary School |  |  |  |  | 100%
132 |  |  |  | i. H. Bido Jordan Elementary School |  |  |  |  | 100%
133 |  |  |  | j. Bayawan National Highschool |  |  |  |  | 100%
134 |  |  |  | k. Maninihon Elementary & Highschool |  |  |  |  | 100%
135 |  |  |  | l. H. Bido Jordan Highschool School |  |  |  |  | 100%
136 |  |  |  | m. SLGTMES |  |  |  |  | 100%
137 | *10710030-030-0072 | 2016 |  | Improvement of Covered Court/Evacuation Ctr., Bry. Banga | Banga | 500000 | 2019-03-16 | 2020-03-31 | 100% | 435324.88
138 | 10710030-030-0071 | 2016 |  | Const. of Evacuation Ctr., Brgy. San Roque | San Roque | 500000 | 2017-06-16 | 2019-06-30 | 100% | 361521.48
139 | *10710030-030-0070 | 2016 |  | Const. of Covered Court/Evacuation Ctr., Bry. Suba | Suba | 500000 | 2016-12-16 | 2017-05-31 | 100% | 454964.53
140 | *10710030-030-0082 | 2016 |  | Const. of Multi-Purpose Bldg. for Evacuation Ctr., Brgy Villareal | Villareal | 500000 | 2019-01-05 | 2018-11-30 | 100% | 431575.23
143 | *10710030-030-0084 | 2016 |  | Establishment of Youth Development Center |  | 5000000 | 2017-06-15 | 2018-09-01 | 100% | 4000896.6
146 | 0 | 2016 |  | LGU Counterpart for the Construction of Sports Complex |  | 15000000 |  |  |  | 0 |  | No Funding
175 | 10710020-002-0041 | 2016 |  | Rehabilitation of San Isidro Water Supply System | Villareal | 350000 | 2019-05-15 | 2020-06-30 | 54% | 189138.38
176 | *10710030-030-0085 | 2016 |  | Const. of Water Tank & Pipeline at Tabuan Brgy Proper | Tabuan | 500000 | 2017-05-01 | 2018-05-31 | 99.5% | 424113.31
177 | 10710020-002-0039 | 2016 |  | Construction of Tayawan Water System | Tayawan | 300000 | 2017-01-06 | 2020-02-29 | 95% | 255424.64 |  | Pending: Remaing work is installation of RCPC at the water source
100 | *10710030-006-0010 | 2016 |  | Installation of Electrical System (Sitio Napit-an, Brgy Maninihon & Zamora Streets, Brgy. Suba) - | Suba | 1500000 | 2016-11-15 | 2018-08-31 | 100% | 1439250.62
101 | *264-005-1606-G0056 | 2016 |  | Purchase of Transforments & Primary Metering @ New Gov't. Center | Banga | 2545000 | 2016-11-24 | 2016-11-29 | 100% | 2540000
102 | *10710030-006-0009 | 2016 |  | Installation of Secondary Line Feeder @ New Gov't. Center | Banga | 800000 | 2016-02-13 | 2018-07-15 | 100% | 669519.56
103 | 10710020-001-0044 | 2016 |  | Establishment of Street Lighting Facilities - 2016 | Var. Brgys. | 400000 | 2019-03-15 | 2020-04-15 | 78% | 314630
104 | *10710020-001-0065 | 2016 |  | Installation of Street Lightings at Brgy Proper, Villasol | Villasol | 140000 | 2017-10-02 | 2017-10-30 | 100% | 132852.6
190 |  | 2017 |  | Establishment of Montessori-Type Early Child Care Development Centers | Various Brgys
191 | 10710030-002-0011 | 2017 |  | a. Establishment of Montessori-Type Early Child Care Development Centers Phase 2 | Boyco | 2289000 | 2017-12-16 | 2020-02-10 | 99% | 1310863.71 |  | On-going
192 | 10710030-002-0014 | 2017 |  | b. Establishment of Montessori-Type Early Child Care Development Centers | Poblacion | 1211000 | 2018-01-01 | 2018-11-30 | 100% | 742624.7 |  | Physically completed
195 | 10710020-009-0003 | 2017 |  | Development of Tabuan People's Park | Tabuan | 2000000 | 2018-12-31 | 2020-04-20 | 100% | 1396904.13
196 | *10710030-030-0128/0129/0130 | 2017 |  | Construction of Coastal Park Comfort Rooms | Coastal Road | 4500000 | 2018-02-15 | 2018-05-27 | 100% | 4497336
197 | 264-009-1711-G0600 | 2017 |  | Construction of Children's Playground with Facilities, Ali-is | Ali-is | 500000 |  |  |  | 0 |  | Contract
198 | 10710030-003-0016 | 2017 |  | Improvement of Barangay Health Center Lying-In Clinic, Brgy. Malabugas | Malabugas | 678571.43 | 2019-01-10 | 2020-12-31 | 92% | 320022.59
199 | 264-004-1711-G0033 | 2017 |  | Improvement of Barangay Health Center & Lying-in Clinic, Brgy. Manduao | Manduao | 100000 |  |  |  | 0 |  | Contract
200 | 10710030-030-0132 | 2017 |  | Construction of Covered Court and Evacuation Center, Brgy. Pagatban | Pagatban | 1728571.43 |  |  |  | 0 |  | Contract
201 | 10710030-030-0135 | 2017 |  | Improvement of Evacuation Center and Multi-Purpose Building, Brgy. Poblacion | Poblacion | 878571.43 | 2020-03-15 |  | 30% | 0 |  | On-going
202 | 10710030-002-0019 | 2017 |  | Construction of New Day Care Center at Brgy. Poblacion | Poblacion | 800000 |  |  |  | 0 |  | Outsource waiting for CTYRC Decision
203 | 10710030-003-0015 | 2017 |  | Construction of Lying-In Clinic, Brgy. San Isidro | San Isidro | 1178571.43 | 2019-02-24 | 2019-12-15 | 99.5% | 590297.46
204 | 10710030-003-0006 | 2017 |  | Improvemen of Health Center and Lying-in Clinic, Brgy.San Roque | San Roque | 1678571.43 |  |  |  | 0 |  | Outsource
205 | 0 | 2017 |  | Improvement of Barangay Health Center, Brgy. Tinago | Tinago | 600000 |  |  |  | 0 |  | Outsource
206 | 10710030-030-0131 | 2017 |  | Construction of Children's Playground with Facilities, Brgy. Villareal | Villareal | 500000 |  |  |  | 0 |  | Outsource
207 | 0 | 2017 |  | Construction of Multi-Purpose Center for Senior Citizens, Brgy. Villasol | Bayawan City | 50000 |  |  |  | 0 |  | Outsource
208 | 10710030-003-0005 | 2017 |  | Improvement of Barangay Health Center, Brgy. San Jose | San Jose | 60000 |  |  |  | 0 |  | Outsource
209 | 10710030-003-0007 | 2017 |  | Renovation of Barangay Health Center at Brgy. Tayawan | Tayawan | 150000 |  |  |  | 0 |  | Outsource
210 | 10710030-002-0020 | 2017 |  | Renovation of Day Care Center, Brgy. Tayawan | Tayawan | 100000 |  |  |  | 0 |  | Outsource
244 | 10710020-002-0052 | 2017 |  | Water System Development Project at Sitio Upper Camandagan, Brgy. Maninihon | Maninihon | 1000000 | 2019-05-01 | 2020-10-31 | 65% | 647344.67 |  | Implemented By BAWAD
242 | 10710020-002-0047 | 2017 |  | Construction of Water System at Proper Manduao | Manduao | 678571.43 | 2019-08-03 | 2019-12-31 | 99.8% | 459267.54 |  | Implemented By BAWAD
245 | 264-009-1712-g0606 | 2017 |  | Improvement of Multi-Purpose Gymnasium and Evacuation Center, Brgy. Maninihon | Maninihon | 678571.43 | 2019-01-25 | 2020-02-15 | 60% | 0 |  | Outsource
248 | 0 | 2017 |  | Establishment of Barangay Water Refilling Station, Brgy. Nangka | Nangka | 678571.43 |  |  |  | 0 |  | BAWAD
254 | 10710030-030-0134 | 2017 |  | Improvement of Covered Court for Evacuation Center, Brgy Suba | Suba | 1678571.43 | [5 empty] | Outsource
262 | 10710020-002-0050 | 2017 |  | Improvement/Rehabilitation of Water Systems for Various Barangays | Various Brgys | 934500 | 2019-01-31 | 2020-05-31 | 100% | 575402.78 |  | Physically Completed for COC: Materials Delivered 92%
263 | 10710030-030-0195 | 2017 |  | Installation of Water Refilling Stations at Various Barangays | Various Brgys | 2200000 | 2019-01-21 | 6/31/2020 | 48% | 1054599.9 |  | Pending: Building is not yet ready
264 | 10710030-030-0094 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Bolo, Brgy. Villasol | Villasol | 600000 | 2018-02-16 | 2018-06-30 | 100% | 563177.77
265 | 264-009-1712-g0605 | 2017 |  | Construction of Multi-Purpose Building in Barangay Tayawan | Tayawan | 900000
266 | 0 | 2017 |  | Construction of Multi-Purpose Building in Barangay San Jose | San Jose | 900000 |  |  |  | 0
268 | *10710020-007-0018 | 2017 |  | Construction of Drainage Canal at Cansumalig High School | Cansumalig | 150000 | 2017-12-16 | 2018-03-30 | 100% | 126833.17
269 | 10710010-002-0004 | 2017 |  | Construction of Perimeter Fence of Multi-Purpose Building, Brgy. San Miguel | San Miguel | 100000 | [5 empty] | Contract
270 | 10710020-002-0086 | 2017 |  | Improvement of Water Systems of Guintanaan Tayawan | Tayawan | 100000 | 2018-06-15 | 2020-12-31 | 3% | 3058 |  | Bawad
271 | 10710020-002-0046 | 2017 |  | Improvement of Water Systems at Manduao | Manduao | 110000 | 2019-07-20 | 2020-12-31 | 14% | 16811.66 |  | Bawad
272 | 0 | 2017 |  | Installation of Solar-Driven Water System for Catumbalan, Minaba | Minaba | 100000 |  |  |  | 0 |  | Bawad
273 | 10710030-006-0015 | 2017 |  | Installation of Solar-Driven Water System for Oban-Oban, Brgy. Kalumboyan | Kalumboyan | 50000 | 2019-08-15 | 2020-04-05 | 27% | 13835.24 |  | Bawad
274 | 0 | 2017 |  | Installation of Solar-Driven Water Systems for Napo, Brgy. Tayawan | Tayawan | 50000 |  |  |  | 0 |  | Bawad
275 | 0 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Upper Manlubid, Ali-is | Ali-is | 50000 |  |  |  | 0
276 | *10710030-030-0095 | 2017 |  | Construction of Multi-Purpose Pavement at Inner Canabuan, Minaba | Minaba | 300000 | 2018-02-16 | 2018-06-30 | 100% | 286328.7 |  | Completed: COC Issued on 07/01/19 Materials delivered- 100%
277 | 269-001-1712-g0052 | 2017 |  | Improvement of Water System at Sitio Pag-awitan, Brgy. Ali-is | Ali-is | 50000 | 2018-11-16 | 2020-04-30 | 70% | 35325 |  | BAWAD
278 | 10710020-002-0089 | 2017 |  | Rehabilitation and Improvement of Water System at Brgy. Banaybanay | Banaybanay | 220000 | 2019-03-26 | 2020-06-30 | 61% | 135396.8 |  | BAWAD
279 | 10710030-004-0004 | 2017 |  | Improvement of Barangay Public Market, Brgy. Malabugas | Malabugas | 50000 |  |  |  | 0 |  | CONTRACT
280 | 10710030-006-0016 | 2017 |  | Installation of Electrical System in Sitio Buli-buli, Brgy. Banga | Banga | 60000 | 2019-01-02 | 2019-02-28 | 100% | 43514.9
281 | 0 | 2017 |  | Installation of Electrical System in Brgy. Kalamtukan | Kalamtukan | 60000 | 2019-06-16 | 2019-07-31 | 100% | 60000
282 | 10710030-006-0014 | 2017 |  | Installation of Electrical System in Brgy. Kalumboyan | Kalumboyan | 70000 | 2019-06-16 | 2019-07-31 | 100% | 54252.49
283 | 269-001-1801-g0057 | 2017 |  | Improvement of Water System, Brgy. San Roque | San Roque | 70000 | 2019-10-25 | 2020-05-01 | 67% | 47394 |  | BAWAD
284 | *10710020-002-0054 | 2017 |  | Improvement of Water System, Brgy. Ubos | Ubos | 145000 | 2018-01-06 | 2018-06-15 | 100% | 136216.2 |  | BAWAD
285 | 0 | 2017 |  | Improvement of Water System at Brgy. Villasol | Villasol | 70000 | 2019-08-31 | 2020-02-29 | 89% | 62346
286 | 10710030-030-0096 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Ponong, Brgy. Villasol | Villasol | 100000 | 2019-07-31 | 2020-05-31 | 62% | 62715.89 |  | Pending: Road not yet passable
287 | *10710030-006-0012 | 2017 |  | Installation of Electrical System at Sitio Malampa, Brgy. Pagatban | Pagatban | 50000 | 2018-01-06 | 2018-06-30 | 100% | 44857.31
289 | *10710030-006-0013 | 2017 |  | Installation of Electrical System in Brgy. Malabugas | Malabugas | 50000 | 2018-03-16 | 2018-04-30 | 100% | 46024.73
290 | 10710020-002-0051 | 2017 |  | Improvement of Canabuan Water System, Brgy. Minaba | Minaba | 200000 | 6/31/2018 | 2020-12-31 | 30% | 62827.91 |  | BAWAD
292 | 264-009-1711-g0596 | 2017 |  | Improvement of Barangay Multi-Purpose Hall, Brgy. Ali-is | Ali-is | 200000 |  |  |  | 0 |  | CONTRACT
293 | 10710030-030-0097 | 2017 |  | Construction of Multi-Purpose Pavement at Purok 2, Brgy. Kalamtukan | Kalamtukan | 250000 | 2018-01-16 | 2018-06-30 | 100% | 224233.82
294 | *10710020-001-0071 | 2017 |  | Installation of Street Lights at Purok 4, Cansilong, Brgy. Malabugas | Malabugas | 100000 | 2018-03-16 | 2018-05-31 | 100% | 90521.66
296 | 0 | 2017 |  | Improvement of Water System, Brgy. Minaba | Minaba | 110000 | 2018-02-01 | 2020-02-20 | 84% | 93457 |  | BAWAD
298 | 0 | 2017 |  | Installation of Electrical System for Purok Ipil-Ipil, Brgy. San Roque | San Roque | 200000 |  |  |  | 0 |  | Implemented by NORECO
267 | *10710030-006-0018 | 2017 |  | Electrification Project for Various Barangays | Various Brgys | 10000 | 2018-01-06 | 2018-06-15 | 100% | 9060.49
301 | 0 | 2017 |  | Construction of Alternative Learning System (ALS) Building, Brgy. Kalumboyan | Kalumboyan | 200000 |  |  |  | 0 |  | CONTRACT
303 | 10710020-002-0048 | 2017 |  | Installation of Deep Well at Atilano Cabangal High School, Brgy. Nangka | Nangka | 250000 | 2018-11-15 | 2020-12-31 | 4% | 10606.87 |  | Pending: re-PR magsaysay type deepwell not available anymore in the market
304 | 10710020-002-0081 | 2017 |  | Installation of Water System at Brgy. Pagatban | Pagatban | 50000 | 2018-03-16 | 2019-06-30 | 100% | 41977.04
251 | *10710020-002-0053 | 2017 |  | Installation of Water System at Brgy. Poblacion | Poblacion | 70000 | 2018-03-01 | 2018-03-15 | 100% | 28933.33
306 | *10710020-002-0045 | 2017 |  | Improvement of Water System at Purok Dol-Dol, Brgy. San Roque | San Roque | 100000 | 2017-11-16 | 2018-01-31 | 100% | 69781.89
309 | 264-009-1712-g0607 | 2017 |  | Improvement of Multi-Purpose Gym & Evacuation Center, Brgy. San Isidro | San Isidro | 495000 |  |  |  | 0 |  | CONTRACT
310 | *10710030-030-0092 | 2017 |  | Construction of Multi-Purpose Pavement, Brgy. Dawis | Dawis | 340000 | 2017-11-01 | 2018-02-28 | 100% | 326849.92
312 | 264-009-1712-g0604 | 2017 |  | Construction of Multi-Purpose Building at Relocation Site, Brgy. San Miguel | San Miguel | 500000 | [5 empty] | CONTRACT
314 | 10710030-030-0193 | 2017 |  | Construction of CICL at BADC Magsulay, Barangay Narra | Narra | 1000000 | 2018-10-09 | 2020-05-31 | 59.8% | 4759509.79 |  | CONTRACT: Temporary Suspended need supplemental budget
317 | 0 | 2017 |  | Const. of Livelihood Center for Women at Brgy Villasol Proper |  | 100000 | [5 empty] | CONTRACT
318 | 10710030-030-0104 | 2017 |  | Construction of Multi-purpose Pavement at Sitio Kaayahan (Phase 1) |  | 100000 | 2017-07-31 | 2020-03-31 | 100% | 62571.46 |  | Physically completed
319 | *10710030-030-0103 | 2017 |  | Completion of Multi-purpose Pavement at Sitio Tangistangisan |  | 330000 | 2018-01-02 | 2018-06-30 | 100% | 306358.29 |  | Physically completed
323 | 10710020-002-0082 | 2017 |  | Development of Water System at Sitio Tavera, Nangka |  | 5700000 | 2019-03-01 | 2020-03-01 | 83% | 2633466.89 |  | Implemented by: BAWAD
324 | *10710020-002-0087 | 2017 |  | Improvement of Cabatangan-Tavera Water System |  | 154784.58 | 2019-01-16 | 2019-03-31 | 100% | 133057.22 |  | Implemented by: BAWAD
326 | 0 | 2017 |  | Improvement of Sports Center and Children's Playground, Boulevard |  | 1000000 |  |  |  | 0 |  | CONTRACT
328 | 10710030-002-0018 | 2017 |  | Establishment of Early Child Development Center |  | 2300000 | 2018-03-31 | 2019-12-31 | 99.79% | 2107332.3 |  | Physically completed
226 | 10710030-030-0101 | 2017 |  | Construction of Multi-Purpose Pavement at Brgy. Ali-is | Ali-is | 580000 | 2017-12-16 | 2018-06-30 | 100% | 549090.35 |  | Physically completed
234 | *10710030-030-0093 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Guinhamogan, Brgy. Cansumalig | Cansumalig | 559523.81 | 2018-04-18 | 2018-07-31 | 100% | 519399.55 |  | Physically completed
235 | 10710030-030-0099 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Punong, Brgy. Cansumalig | Cansumalig | 559523.81 | 2018-03-16 | 2019-08-31 | 100% | 505035.42 |  | Physically completed
233 | 10710030-030-0090 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Guintalasan, Brgy. Cansumalig | Cansumalig | 559523.81 | 2018-09-15 | 2020-09-15 | 52% | 293822.16 |  | No existing road
237 | 264-009-1711-g0595 | 2017 |  | Improvement of Multi-Purpose Building at Brgy. Dawis | Dawis | 678571.43 |  |  |  | 0 |  | CONTRACT
240 | 10710030-030-0100 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Cogon, Brgy. Kalamtukan | Kalamtukan | 500000 | 2018-01-16 | 2018-06-30 | 100% | 471707.38 |  | Physically completed
243 | 10710030-030-0089 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Bocaw, Manduao | Manduao | 500000 | 2019-01-01 | 2019-07-31 | 100% | 463687.64 |  | Physically completed
258 | 264-009-1711-g0602 | 2017 |  | Improvement of Multi-Purpose Building, Brgy. Tinago | Tinago | 1128571.43 | 2018-03-16 | 2020-12-31 | 15% | 168535.72 |  | CONTRACT
261 | *10710030-030-0098 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Manghakayhakay, Brgy. Villasol | Villasol | 600000 | 2017-12-16 | 2018-03-31 | 100% | 560025.05 |  | Physically completed
383 |  | 2017 |  | Purchase of 50 KVA Transformer for BCTLDC |  | 500000 |  |  |  | 0
385 |  | 2017 |  | Construction of City Health Office Building |  | 1000000 | [5 empty] | Materials Completely Delivered: No site available
331 | no obligation | 2017 |  | Construction of Workshop Area for Bayawan City Technology & Livelihood Development Center (BCTLDC) |  | 3000000 | 2019-05-17 | 2019-10-31 | 100% | 0 |  | Contract: Physically Completed
332 |  | 2017 |  | Purchase of Workshop Tools and Equipment for BCTLDC:
333 |  |  |  | Furniture & Fixtures
334 |  | 2017 |  | 3 units Exhaust Fan |  | 4500 |  |  | 100% | 4500
335 |  | 2017 |  | 3 units Industrial Fan |  | 19656 |  |  | 100% | 19656
336 |  | 2017 |  | 4 units White Board with Movable Stand |  | 11000 |  |  | 100% | 11000
337 |  | 2017 |  | 3 units White Board (4x8x3/4) |  | 9900 |  |  | 100% | 9900
338 |  |  |  | Machinery
339 |  | 2017 |  | 18 units Arc Welding Machine AC/DC & Acc |  | 698040 |  |  | 100% | 698040
340 |  |  |  | Communication Equipment
341 |  | 2017 |  | 1 unit LCD projector |  | 26000 |  |  | 100% | 22995
342 |  |  |  | Disaster Response & Rescue Equipment
343 |  | 2017 |  | 4 units Fire Extinguishers |  | 12364 |  |  | 100% | 12364
344 |  |  |  | Military, Police & Security Equipment
345 |  | 2017 |  | 1 Set Security Equipment Access Control (CCTV) |  | 29845 |  |  | 100% | 29845
346 |  |  |  | Other Machinery & Equipment
347 |  | 2017 |  | 6 units Work Bench w/ Bench Vice on 4 Corners |  | 204000 |  |  | 100% | 204000
348 |  | 2017 |  | 25 sets Combination Spanner (6mm to 24 mm) |  | 80000 |  |  | 100% | 80000
349 |  | 2017 |  | 12 units Blow Torch |  | 18000 |  |  | 100% | 18000
350 |  | 2017 |  | 12 units Clamp on Meter |  | 36000 |  |  | 100% | 36000
351 |  | 2017 |  | 6 units Portable Electric Drill |  | 30000 |  |  | 100% | 30000
352 |  | 2017 |  | 6 units Portable Planer |  | 51600 |  |  | 100% | 51600
353 |  | 2017 |  | 6 units Portable Circular Saw |  | 47220 |  |  | 100% | 47220
354 |  | 2017 |  | 25 pcs Welding Positioners |  | 96250 |  |  | 100% | 96250
355 |  | 2017 |  | 6 units Electrode Oven |  | 24000 |  |  | 100% | 24000
356 |  | 2017 |  | 25 units Portable Disc Grinder |  | 78750 |  |  | 100% | 78750
357 |  | 2017 |  | 6 units Pipe Threader 1/2-2" |  | 343200 |  |  | 100% | 343200
358 |  | 2017 |  | 6 units Pipe Bender |  | 26400 |  |  | 100% | 26400
359 |  | 2017 |  | 6 units Heat Gun 1200 watts |  | 18900 |  |  | 100% | 18900
360 |  | 2017 |  | 6 units Bolt Cutter |  | 7680 |  |  | 100% | 7680
361 |  | 2017 |  | 12 pcs Box Wrench |  | 58800 |  |  | 100% | 58800
362 |  | 2017 |  | 12 pcs Wire Splicer |  | 25320 |  |  | 100% | 25320
363 |  | 2017 |  | 12 pcs Wire Stripper |  | 25320 |  |  | 100% | 25320
364 |  | 2017 |  | 12 units Electric Drill |  | 58800 |  |  | 100% | 58800
365 |  | 2017 |  | 12 units Portable Grinder |  | 52500 |  |  | 100% | 52500
366 |  | 2017 |  | 6 units Pipe Cutter (1/2"-1") |  | 31590 |  |  | 100% | 31590
367 |  | 2017 |  | 3 units Manual Pipe Threader (1/2", 3/4", 1") |  | 33705 |  |  | 100% | 33705
368 |  | 2017 |  | 3 units Fusion Machine (20mm-32mm) |  | 34020 |  |  | 100% | 34020
369 |  | 2017 |  | 4 units Electric Grinder (4") |  | 20520 |  |  | 100% | 20520
370 |  | 2017 |  | 12 units Angle Grinder |  | 61560 |  |  | 100% | 61560
371 |  | 2017 |  | 2 units Labelling Machine |  | 2200 |  |  | 100% | 2200
372 |  | 2017 |  | 6 units Insulation Resistance Tester |  | 9900 |  |  | 100% | 9900
373 |  | 2017 |  | 6 units Earth Resistance Tester |  | 13200 |  |  | 100% | 13200
374 |  | 2017 |  | 4 units Pedestal/Bench Grinding Machine |  | 9400 |  |  | 100% | 9400
375 |  | 2017 |  | 10 units Panel Board with 70 amp main & 4 |  | 34450 |  |  | 100% | 34450
376 |  | 2017 |  | 25 pcs Electrician Pliers |  | 66250 |  |  | 100% | 66250
377 |  | 2017 |  | Other Property, Plant & Equipment
378 |  | 2017 |  | 3 units Wheelbarrow |  | 6600 |  |  | 100% | 6000
379 |  | 2017 |  | 6 sets Oxy-Acetylene/Oxy-LPG Cutting Outfit |  | 72000 |  |  | 100% | 72000
380 |  | 2017 |  | 6 units Plastic Drum (200 liters) |  | 10560 |  |  | 100% | 10560
388 |  | 2018 |  | Purchase of Lot for Multi-Purpose Hall at Sitio Cambulo. Banga | Banga | 600000 |  |  |  | 0
425 | 10710020-002-0057 | 2018 |  | Water System Development at Bugay Proper | Bugay | 500000 | 2019-04-01 | 2020-12-31 | 30% | 148710.4 |  | Implemented by: BAWAD
426 | 10710020-002-0056 | 2018 |  | Development of Water System at Brgy. Villareal | Villareal | 1000000 | 2019-08-12 | 2020-11-30 | 30% | 327600 |  | Implemented by: BAWAD
427 | 10710020-001-0113 | 2018 |  | Installation of Street Lighting from Purok 1 to Purok IV, Brgy. Tayawan | Tayawan | 500000 | 2018-06-21 | 2020-12-31 | 33% | 166705.62
428 | 10710020-009-0001 | 2018 |  | Improvement of Barangay Plaza and Children's Park, Tayawan | Tayawan | 500000 | 2018-06-21 | 2020-12-31 | 85% | 143163.53 |  | Temporarily Stopped: Due to COA remarks
429 | 0 | 2018 |  | Establishment of Early Child Care Dev't Centers: | Bayawan City
430 | 10710030-002-0021 | 2018 |  | a. Brgy. Villareal | Villareal | 5000000 | 2018-06-21 | 2020-03-31 | 95% | 3101471.04
431 | 10710030-002-0022 | 2018 |  | b. Brgy. Malabugas | Malabugas | 5000000 | 2018-06-21 | 2019-11-15 | 100% | 4874380.13 |  | Physically Completed: COC Issued on 11/20/20
432 | 10710030-002-0023 | 2018 |  | Construction of Day Care Center at Sitio Mantapi, Nangka | Nangka | 578571.43 | 2018-12-01 | 2020-12-01 | 56% | 325812.46 |  | C/O GSO; Materials delivered- 100%
433 | 0 | 2018 |  | Improvement of Barangay Health Center & Lying-In Clinic, Brgy. Malabugas | Malabugas | 1000000 |  |  |  | 0
434 | 10710030-003-0008 | 2018 |  | Construction of Health Center at Sitio Mantapi, Nangka | Nangka | 500000 | 2019-11-12 | 2020-11-12 | 22% | 110023.07 |  | C/O GSO; Materials delivered- 100%
443 | 10710030-030-0138 | 2018 |  | Construction of Bleachers at Barangay Evacuation Center, Ali-is | Ali-is | 678571.43 | 2018-01-04 | 2019-04-30 | 100% | 555739.56
444 | 10710030-030-0146 | 2018 |  | Improvement of Barangay Multi-Purpose Building, Banaybanay | Banaybanay | 1000000 |  |  |  | 0 |  | Contract
445 | 10710030-030-0150 | 2018 |  | Improvement of Barangay Multi-Purpose Hall, Brgy. Boyco | Boyco | 1678571.43 |  |  |  | 0 |  | Contract
446 | 10710030-030-0144 | 2018 |  | Construction of Barangay Multi-Purpose Building, Cansumalig | Cansumalig | 1300000 | 2019-07-16 | 2020-07-16 | 75% | 973876.6 |  | Materials delivered - 96%; re-ad - 4%
447 | 10710030-002-0024 | 2018 |  | Construction of Feeding Center at Damig Elementary School, Brgy. Kalamtukan | Kalamtukan | 778571.43 |  |  |  | 0
448 | 10710030-030-0147 | 2018 |  | Improvement of Barangay Multi-Purpose Building, Maninihon | Maninihon | 1000000 | 2019-11-01 | 2020-08-15 | 70% | 279102.05
449 | 10710030-030-0155 | 2018 |  | Construction of Multi-Purpose Pavement at Sitio Mantapi, Nangka | Mantapi, Nangka | 600000 | 2018-01-07 | 2018-12-31 | 100% | 546309.58
450 | 10710030-030-0148 | 2018 |  | Construction of Barangay Multi-Purpose Building, Narra | Narra | 1000000 |  |  |  | 0
451 | 10710010-002-0005 | 2018 |  | Construction of Concrete Perimeter Fence of Covered Court and Evacuation Center, Brgy. Pagatban | Pagatban | 100000 | 2018-01-07 | 2018-08-31 | 100% | 86496.06
452 | 10710030-030-0145 | 2018 |  | Construction of Multi-Purpose Building, Brgy. San Isidro (Phase 2) | San Isidro | 1078571.43 | 2019-01-08 | 2020-04-15 | 75% | 823155.03 |  | Materials delivered - 100%
453 | 10710030-030-0137 | 2018 |  | Construction of Children and Women's Crisis Center, Brgy. Suba | Suba | 600000 |  |  |  | 0
454 | 10710030-030-0153 | 2018 |  | Improvement of Multi-Purpose Hall, Brgy. Suba | Suba | 578571.43 |  |  |  | 0
455 | 10710030-030-0149 | 2018 |  | Construction of Multi-Purpose Hall, Brgy. Tinago | Tinago | 2278571.43 | 2019-07-01 | 2020-12-31 | 30% | 389078.02
457 | 10710030-030-0152 | 2018 |  | Improvement of Multi-Purpose Hall, Banga | Banga | 2078571.43 |  |  |  | 0
460 | 10710030-030-0151 | 2018 |  | Improvement of Barangay Multi-Purpose Hall, Manduao | Manduao | 600000 | 2019-05-24 | 2020-03-15 | 100% | 440893.31
|  |  |  | Total Projects for Social Development - Contg App |  | 144078603.64 |  |  |  | 75549898.23
ECONOMIC DEVELOPMENT
64 | 10710020-006-0003 | 2011 |  | Const. of Hanging Bridge at Sitio Tiki, Kalumboyan (Phase 3) | Kalumboyan | 700000 | 2011-07-01 | 2020-12-31 | 37% | 546410.34 |  | Project heavily damaged by typhoon - discontinued
65 | 10710030-005-0002 | 2012 |  | Construction of Slaughterhouse | Suba | 10000000 | 2016-09-16 | 2018-03-31 | 100% | 7818835.46 |  | 100% Completed as per POW: Materials delivered- 75%; cancelled- 25%(rectangular tube, CHB, plywood, floor/wall tiles, blind rivets, drill bits, electrical materials & steel plate - for re-P.R. (100-17-01-023 -
72 | 0 | 2013 |  | Fabrication of Distillation Chamber for Essential Oil Production | Banga | 150000 |  |  |  | 0
73 | *10710020-001-0011 | 2014 |  | Construction of Bayawan City Boulevard/Phase 2 | Bayawan City | 1000000 | 2014-08-16 | 2014-10-30 | 100% | 936750.81
74 | *10710030-030-0031 | 2014 |  | Const. of Motorpool Building, Phase 1, Cabcabon | Cabcabon, Banga | 8483700 | 2015-07-06 | 09/31/17 | 100% | 7911686.98
76 | per saaob | 2014 |  | Major Repair - Construction & Heavy Equipment | Motorpool Area | 10000000 | 2014-06-11 | 2020-12-31 | 22.43% | 2242763 |  | Temporary Standby due to some equipments already deteriorated
78 | 10710020-001-0039 | 2014 |  | Road Surfacing from Sitio Binanigan to Sitio Guintana-an, Brgy. Tayawan, Phase 1 | Tayawan | 500000 | 2016-03-16 | 2020-04-01 | 90% | 173183.68 |  | Temporary stopped: Need to look other quarry source, road not yet passable, no Backhoe available
80 | *10710020-002-0025 | 2014 |  | Construction of Water System-Crusher Kalumboyan |  | 212800 | 2015-06-01 | 2016-06-30 | 100% | 182355.32
86 | no obligation | 2015 |  | Purchase of Various Heavy Equipment |  | 3476406.99 |  |  |  | 0
88 | *10710020-001-0019 | 2015 |  | Reblocking of Concrete Pavement at Villareal-Cansumalig-San Isidro FMR, Phase 2 | Bayawan City | 500000 | 2015-06-01 | 2015-06-30 | 100% | 457677.34
89 | 10710020-001-0013 | 2015 |  | Construction of Gomez Street Extension | Bayawan City | 3000000 | 2016-03-16 | 2018-06-30 | 100% | 1148517.88
90 | *10710020-001-0016 | 2015 |  | Concreting of Road Shoulder of National Highway Fronting BNHS, | Bayawan City | 3000000 | 2016-02-09 | 2017-01-15 | 100% | 2935348.39
91 | *10710020-001-0017 | 2015 |  | Construction of Access Road at Bayawan East, | Bayawan City | 2053659.56 | 2015-04-01 | 2016-03-15 | 100% | 1967337.73
92 | 10710020-001-0040 | 2015 |  | Road Surfacing of Sitio Hag-um and Sitio Mambunot, Brgy. Tayawan, Phase 1 | Tayawan, Bayawan City | 500000 | 2016-03-16 | 2020-02-15 | 99% | 369872.41 |  | On-going
93 | *10710020-001-0022 | 2015 |  | Rehabilitation of FMR at Sitio Tubod, Brgy. Tabuan | Tubod, Tabuan | 100000 | 2015-10-01 | 2016-03-15 | 100% | 56654.12
94 | *10710020-001-0021 | 2015 |  | Rehabilitation of Pulangyuta-Lapay FMR | Bayawan City | 2014400 | 2015-09-16 | 2017-03-31 | 100% | 2008455.26
122 | 10710030-030-0076 | 2016 |  | Improvement of Agricultural Dev. Ctr. (ADC), Cansumalig, Phase 2 | Cansumalig | 400000 | 2017-06-01 | 2018-06-30 | 100% | 348687.17
141 | *10710020-002-0043 | 2016 |  | Const. of Rain Collector at Brgy. San Isidro | San Isidro | 150000 | 2017-12-16 | 2018-05-31 | 100% | 137210.67
142 | 0 | 2016 |  | Fish Farm Development Program |  | 900000 |  |  |  | 0
144 | 10710030-003-0009 | 2016 |  | Renovation of the Integrated Business Center(IBC) Building | Villareal | 8000000 | 2017-04-27 | 2020-02-15 | 100% | 7082075.46 |  | Physically Completed: COC Issued on 01/27/20
145 | 10710030-030-0086 | 2016 |  | Pilot Livestock Silage Stocking Project |  | 2000000 |  |  |  | 1650821.2
147 | *10710030-004-0005 | 2016 |  | Establishment of Bayawan Farmers' Market in Dumaguete |  | 5000000 | 2018-02-05 | 2018-10-31 | 100% | 4994489.13
149 | per saaob | 2016 |  | Purchase of Agricultural & Forestry Equipment and Implements |  | 8800000 | 2018-01-02 | 2018-12-31 | 100% | 8400000
151 | no obligation |  |  |  |  | 250000 |  |  |  | 0
153 | *10710020-001-0031 | 2016 |  | Improvement of Nangka-Narra FMR | Bayawan City | 5000000 | 2016-06-16 | 2017-08-31 | 100% | 4454951.93
154 | *10710020-001-0041 | 2016 |  | Improvement of Maninihon-Cansumalig-San Isidro FMR | Bayawan City | 5000000 | 2016-06-16 | 2017-09-15 | 100% | 4802539.95
155 | *10710020-001-0053 | 2016 |  | Reblocking of Concrete Pavement at Villareal-Cansumalig-San Isidro FMR, Phase 3 | Bayawan City | 500000 | 2017-03-01 | 2017-07-31 | 100% | 470136.11
156 | *10710020-001-0043 | 2016 |  | Reblocking of Concrete Pavement Nangka- Narra FMR | Bayawan City | 500000 | 2017-02-16 | 2017-06-30 | 100% | 472475.09
157 | *10710020-001-0062 | 2016 |  | Reblocking of Concrete Pavement with Slope Protection at Malabugas-San Roque Route | Bayawan City | 500000 | 2017-05-01 | 2017-10-31 | 100% | 459598.82
158 | *10710020-001-0052 | 2016 |  | Reblocking of Concrete Pavement with Slope Protection at Tabuan-Banay-banay Route | Bayawan City | 500000 | 2017-05-01 | 2017-10-31 | 100% | 463537.29
159 | *10710020-001-0049 | 2016 |  | Concreting of Road Approaching Upper Baican Box Culvert with Slope Protection | Bugay | 1000000 | 2016-10-16 | 2017-06-30 | 100% | 974648.99
160 | *10710020-001-0048 | 2016 |  | Concreting of Road Approaching Nayabaan Box Culvert with Slope Protection | Bugay | 1000000 | 2016-09-16 | 2017-07-15 | 100% | 908111.85
161 | *10710020-001-0063 | 2016 |  | Concreting of Road Approaching Cagayon Box Culvert with Slope Protection | Banaybanay | 1000000 | 2017-01-01 | 2017-10-31 | 100% | 905886.26
162 | *10710020-001-0061 | 2016 |  | Concreting of Road Approaching Cabigohan Box Culvert with Slope Protection | Dawis | 1000000 | 2017-05-01 | 2017-10-15 | 100% | 930476.68
163 | 10710020-030-0001 | 2016 |  | Installation of Guardrails at Kalumboyan Bridge Approaches | Kalumboyan | 2000000 | 2017-08-01 | 2018-06-30 | 100% | 1710926.68
164 | *10710020-006-0008 | 2016 |  | Const. Tiki Footbridge, Phase 2 Brgy. Kalumboyan | Kalumboyan | 700000 | 2017-04-16 | 2018-02-28 | 100% | 685551.67
165 | 10710020-001-0025 | 2016 |  | Const. of Urban Roads (Gomez to Kabankalan Road) | City Proper | 8000000 | 2017-06-01 | 2018-12-31 | 100% | 5854241.79
166 | 10710020-001-0032 | 2016 |  | Rehab of FMR at So. Pag-awitan, Ali-is | Ali-is | 500000 | 2018-05-16 | 2018-12-31 | 100% | 296371.2
167 | 10710020-001-0036 | 2016 |  | Road Opening at Sitio Palasanon, Cansinacao, Guintalasan Mangharaw & Guinhamogan, Brgy Cansumalig | Cansumalig | 500000 | 2018-02-16 | 2020-06-30 | 50% | 114051.44 |  | Temporarily Stopped: Road no longer passable & no available heavy equipment
168 | 10710020-001-0033 | 2016 |  | Road Rehabilitation at so. Camague, Brgy Dawis | Villareal | 500000 | 11/31/2019 | 2020-07-31 | 15% | 82591.46 |  | Materials Completely Delivered; No available H.E. and Road not yet passable
169 | 10710020-001-0035 | 2016 |  | Road surfacing at Manduao-Bucao, Brgy Manduao | Manduao | 500000 | 2016-03-16 | 2020-12-31 | 5% | 167283.93 |  | Temporarily stopped: road not yet passable & no available heavy equipment
170 | *10710020-006-0009 | 2016 |  | Const. of Steel Bridge Connecting So. Malampa to So. Tab-ang, Brgy Pagatban | Pagatban | 500000 | 2017-06-16 | 2018-01-31 | 100% | 360828.1
171 | *10710020-001-0060 | 2016 |  | Const. or Road from Gov't. Ctr. To sitio Buli-buli/Phase 2 | Banga | 2000000 | 2017-01-01 | 11-31-17 | 100% | 1670978.21
172 | 10710020-001-0064 | 2016 |  | Improvement of Road Along Bayawan CIP Main Canal | Bayawan City | 190000 | 2019-08-16 | 2020-05-15 | 47% | 90000
173 | *10710020-006-0010 | 2016 |  | Const. of Footbridge at Sitio Lower Baican, Brgy Villasol | Baican, Villasol | 220000 | 2018-02-01 | 2018-06-30 | 100% | 189061.91
179 | *10710020-003-0004 | 2016 |  | Rehabilitation of Bayawan Communal Irrigation System | Pagatban | 500000 | 2016-08-16 | 2016-12-31 | 100% | 458455.32
180 | 10710020-003-0005 | 2016 |  | Const. of Small Scale Irrigation Project at Sitio Magsulay | Narra | 1000000 | 2016-08-16 | 2019-12-31 | 100% | 1031939.62
184 | *10710020-004-0011 | 2016 |  | Const. of Box Culvert in So. Candalaga, Brgy Nangka | Nangka | 500000 | 2017-03-16 | 2017-06-30 | 100% | 381385.53
185 | *10710020-002-0042 | 2016 |  | Construction of Spring Box at Upper Talao, San Isidro | San Isidro | 500000 | 2018-04-15 | 2019-03-31 | 100% | 253922.18
186 | *10710020-004-0016 | 2016 |  | Const. of 1 unit Single Box Culvert Phase 1 at So, Magsakang, brgy Tayawan | Tayawan | 500000 | 2018-01-16 | 2018-05-15 | 100% | 410379.87
211 | 10710030-030-0049 | 2017 |  | Construction of Pigpens |  | 400000 | 2019-12-01 | 2020-12-01 | 1% | 3301.01
212 | 0 | 2017 |  | Construction of 2 Units Small Scale Rubber Processing Plant with Shed |  | 300000 |  |  |  | 0
213 | budget data | 2017 |  | Purchase of Breeding Stocks | Bayawan City | 1944000
214 | 0 | 2017 |  | Improvement of Brgy. Dawis Livestock Auction Market | Dawis | 150000 |  |  |  | 0
215 | *10710030-030-0091 | 2017 |  | Fabrication of Portable Batching Plant |  | 500000 | 2017-10-16 | 2018-05-31 | 100% | 325671.05
216 | *10710030-001-0004 | 2017 |  | Construction of CEO Multi-Purpose Building | Cabcabon | 2000000 | 2017-04-16 | 2019-04-30 | 100% | 1744342.36
217 | 10710030-030-0088 | 2017 |  | Construction of Motorpool Building at Cabcabon | Cabcabon | 8000000 | 2017-05-16 | 2019-12-15 | 99.5% | 6196472.82
218 | no obligation | 2017 |  | Lot Acquisition |  | 500000 |  |  |  | 0
219 | 0 | 2017 |  | Establishment of Livestock Auction Market |  | 2000000 |  |  |  | 0
220 | 0 | 2017 |  | Improvement of Public Market Water System | Bayawan City | 500000 |  |  |  | 0
221 | *10710020-001-0076 | 2017 |  | Construction of Slope Protection at Narra-Duyanduyan FMR, Sito Duyan-duyan, Brgy. Narra | Bayawan City | 1000000 | 2017-10-16 | 2018-05-31 | 100% | 895097.05
225 | no obligation | 2017 |  | Purchase of Various Agricultural Equipment | Bayawan City | 4000000
291 | *10710020-001-0080 | 2017 |  | Slope Protection at Barangay Proper, San Isidro | San Isidro | 50000 | 2017-11-16 | 2018-01-31 | 100% | 48807.67
227 | 10710020-006-0012 | 2017 |  | Construction of Flat Slab Bridge at Brgy. Proper, Banaybanay | Banaybanay | 600000 | 2018-01-16 | 2018-09-30 | 100% | 641521.88
228 | 0 | 2017 |  | Improvement of FMR at Sitio Cangcawit, Banaybanay | Banaybanay | 1078571.43 |  |  | 72% | 0 |  | On- Going
229 | 10710030-030-0189 | 2017 |  | Improvement of Covered Court & Evacuation Center, Brgy. Banga | Banga | 500000 | 2019-03-16 | 2019-10-30 | 100% | 358699.53 |  | Physically Completed: Materials delivered - 93%; cancelled - 7%
230 | *10710020-001-0079 | 2017 |  | Improvement of FMR at Sitio Cansig-id, Brgy. Banga | Banga | 500000 | 2017-12-01 | 2018-01-31 | 100% | 455034
231 | 0 | 2017 |  | Improvement of FMR from Brgy. Proper to Sitio Aya, Brgy. Bugay | Bugay | 839286.43 |  |  |  | 0
232 | 0 | 2017 |  | Improvement of FMR from Brgy Proper to Sitio Canlantang,Brgy. Bugay | Bugay | 839285 |  |  |  | 0
236 | 264-009-1711-g0597 | 2017 |  | Construction of Satellite Farmers' Market, Brgy. Dawis | Dawis | 1000000 |  |  |  | 0
238 | 10710020-001-0115 | 2017 |  | Improvement of FMR at Brgy. Dawis | Dawis | 150000 | 2018-06-01 | 2019-02-22 | 100% | 146687.65
239 | 10710020-001-0081 | 2017 |  | Improvement of Road from Barangay Proper to Kalamtukan Elementary School, Brgy. Kalamtukan | Kalamtukan | 1178571.43 | 2017-10-16 | 2018-06-15 | 100% | 1083384.59
241 | 0 | 2017 |  | Improvement of FMR at Brgy. Proper, Manduao | Manduao | 500000 |  |  |  | 0 |  | Pending: Road not yet passable
246 | *10710020-001-0114 | 2017 |  | Improvement of FMR at Brgy. Minaba | Minaba | 678571.43 | 2018-05-16 | 2019-01-31 | 100% | 532636.79
247 | 10710020-001-0075 | 2017 |  | Improvement of FMR at Sitio Kasla, Brgy. Nangka | Nangka | 1000000 | 2017-12-01 | 2018-07-31 | 100% | 1167704.06 |  | Completed: COC Issued on 07/01/19 Materials Delivered - 96%; cancelled - 4%
249 | 10710020-001-0085 | 2017 |  | Improvement of FMR at Sitios Terong, Palongpong, Canggabi and Cadal-ugan, Brgy. Narra | Narra | 1000000 | 2018-05-16 | 2020-08-01 | 35% | 246842 |  | On- Going
250 | 10710020-001-0072 | 2017 |  | Road Opening at Brgy. Narra Proper | Narra | 678571.43 | 2018-06-16 | 2019-12-31 | 90% | 301799.59 |  | On- Going; Delivered - 100%
252 | 0 | 2017 |  | Construction of Barangay Public Market, Brgy. San Jose | San Jose | 1678571.43 |  |  |  | 0
253 | 0 | 2017 |  | Construction of Cloning Chamber at San Roque BADC | San Roque | 50000 |  |  |  | 0
255 | 10710020-006-0013 | 2017 |  | Improvement of Flat Slab Bridge at Sitio Magsakang, Brgy Tayawan | Tayawan | 500000 | 2019-02-16 | 2019-10-31 | 100% | 359123.07 |  | Physically Completed: COC Issued 01/23/2020
256 | 10710020-001-0074 | 2017 |  | Improvement of Binanigan-Guintanaan FMR, Tayawan | Tayawan | 678571.43 | 2019-10-15 | 2020-07-31 | 96% | 24776.18 |  | On- Going
257 | 10710020-001-0073 | 2017 |  | Improvement of Binanigan-Napo FMR, Brgy. Tayawan | Tayawan | 500000 | 2019-01-10 | 2020-03-16 | 95% | 226881.08 |  | On-Going: Delivered - 100%
260 | 10710020-006-0014 | 2017 |  | Construction of Flat Slab Bridge Connecting Barangay Proper to Purok Malinong, Brgy. Villasol | Villasol | 1078571.43 | 2018-02-15 | 2019-04-30 | 100% | 1055559.54 |  | Completed: COC Issued on 07/01/9; Materials Delivered - 100%
288 | 0 | 2017 |  | Improvement of FMR at Brgy. Banaybanay | Banaybanay | 100000 |  |  |  | 0
295 | 10710020-001-0078 | 2017 |  | Improvement of FMR at Sitio Napit-an, Brgy. Maninihon | Maninihon | 220000 | 2018-04-01 | 2018-07-31 | 100% | 191064.53
297 | 10710020-001-0082 | 2017 |  | Improvement of FMR at Sitio Ondol, Brgy. Nangka | Nangka | 100000 | 2018-04-01 | 2018-08-31 | 100% | 95011
299 | *10710020-001-0077 | 2017 |  | Road Improvement at Brgy. Ubos | Ubos | 170000 | 2018-01-01 | 2018-02-15 | 100% | 148018.03
300 | *10710020-030-0002 | 2017 |  | Construction of Pathway to Banay-Banay Proper | Banay-Banay | 100000 | 2017-10-16 | 2018-02-28 | 100% | 89325.07
302 | 10710020-001-0084 | 2017 |  | Road Opening from National Highway to Purok 1 Pasil, Brgy. Malabugas | Malabugas | 150000 | 2019-09-15 | 2020-09-16 | 50% | 70424.49 |  | No ROW
305 | 10710020-001-0083 | 2017 |  | Improvement of FMR at Sitio San Ramon, Brgy. Poblacion | Poblacion | 150000 | 2018-04-01 | 2018-08-31 | 100% | 143423.48
313 | 10710020-001-0070 | 2017 |  | Rehabilitation of Farm to Market Road from Sitio Bosque to Tavera, Barangay Nangka | Nangka | 1000000 | 2019-06-12 | 2020-06-10 | 80% | 447997.6 |  | Materials delivered- 100% (aggregate sub-base course)
316 | no obligation | 2017 |  | Purchase of Lot(Road Right of Way for Various Road Projects) |  | 2980124.07 |  |  |  | 0
193 | 10710010-001-0003 | 2017 |  | Development of Danapa Eco Park | Nangka | 18000000 | 2017-12-06 | 2020-02-29 | 98% | 16778685.58 |  | Pending: Punch list not yet rectify & Subject For Termination
194 | 10710020-030-0003 | 2017 |  | Development of Narra Water Park | Narra | 16000000 | 2017-09-12 | 2018-09-30 | 100% | 15993892.48 |  | Physically Completed: COC Issued 07/03/18
315 | budget data | 2017 |  | Purchase of Livestock Breeding Stocks |  | 533460 | 2017-05-31 | 11/31/2019 | 100% | 515555.56
386 |  | 2018 |  | Loan Amortization |  | 9809031.89 |  |  |  | 0
387 |  | 2018 |  | Lot Acquisition for Development Projects |  | 1754285.71 |  |  |  | 0
389 | 10710020-001-0112 | 2018 |  | Widening of Malabugas-San Roque Road |  | 3500000 | 2019-01-09 | 2019-12-31 | 85% | 1445228.52 |  | Materials delivered - 97%; cancelled - 3%
390 | 10710020-001-0095 | 2018 |  | Concreting of Road Approaching Lapay Box Culvert with Slope Protection, Dawis | Bayawan Creek, Dawis | 1000000 | 2018-04-01 | 2018-08-31 | 100% | 747362.76 |  | Completed: COC Issued on 07/01/9; Materials delivered- 97%; partial delivery - 3%
391 | 10710020-001-0094 | 2018 |  | Concreting of Road Approaching Candalaga Box Culvert with Slope Protection, Nangka | Nangka | 1000000 | 2018-04-01 | 2018-11-30 | 100% | 871645.24 |  | Completed: COC Issued on 07/01/9; Materials delivered- 97%; Partial delivery - 3%
392 | 10710020-001-0098 | 2018 |  | Concreting of Road Approaching Pusi-on Box Culvert with Slope Protection, Maninihon | Maninihon | 1000000 | 2018-04-01 | 2019-02-28 | 100% | 853103.96 |  | Completed: COC Issued on 07/01/9; Materials delivered- 97%; Partial delivery - 3%
393 | 10710020-001-0093 | 2018 |  | Concreting of Road Approaching Camandagan Box Culvert with Slope Protection, Maninihon | Maninihon | 1000000 | 2018-04-01 | 2018-09-30 | 100% | 788542.62 |  | Completed: COC Issued on 07/01/9; Materials delivered- 100%
394 | 10710020-001-0091 | 2018 |  | Concreting of Road Approaching Balao Box Culvert with Slope Protection, San Miguel | San Miguel | 1000000 | 2018-04-01 | 2018-10-30 | 100% | 829617.41 |  | Completed: COC Issued on 07/01/9; Materials delivered- 97%; Partial delivery - 3%
395 | 10710020-001-0096 | 2018 |  | Concreting of Road Approaching Magsakang Box Culvert with Slope Protection, Tayawan | Tayawan | 1000000 | 2018-04-01 | 2019-07-31 | 100% | 852445.15 |  | Physically Completed: Materials delivered- 97%; Partial delivery - 3%
396 | 10710020-006-0016 | 2018 |  | Completion of Magsakang Flat Slab Bridge, Tayawan | Tayawan | 1000000 | 2018-04-01 | 2019-04-30 | 100% | 954259.8 |  | Physically Completed: Materials delivered- 95%; for delivery- 5%
397 | 10710020-001-0097 | 2018 |  | Concreting of Road Approaching Pamuat Box Culvert with Slope Protection, San Isidro | San Isidro | 1000000 | 2018-04-01 | 2019-06-30 | 100% | 929512.72 |  | Physically Completed: Materials delivered - 100%
398 | 10710020-001-0092 | 2018 |  | Concreting of Road Approaching Binanigan Box Culvert with Slope Protection, Tayawan | Tayawan | 1000000 | 2018-04-01 | 2018-09-30 | 100% | 761723.42 |  | Completed: COC Issued on 07/01/9; Materials delivered- 100%
399 | *10710020-001-0086 | 2018 |  | Concreting of Road at Purok 7, Barangay Tinago | Tinago | 2000000 | 2018-02-16 | 2018-08-31 | 100% | 1714331.49
400 | 10710020-001-0088 | 2018 |  | Concreting of Dawis-Lapay FMR | Bayawan City | 5500000 | 2018-04-01 | 2019-07-31 | 100% | 4539005.09 |  | Physically Completed: Materials delivered- 96%; re-bid- 4%
401 | 10710020-001-0087 | 2018 |  | Concreting of Banga-San Roque-Minaba-San Miguel-Tayawan FMR | Bayawan City | 5872000 | 2018-04-01 | 2019-06-30 | 100% | 5221497.1 |  | Physically Completed: Materials delivered- 96%; Partial delivery- 2%; for delivery- 2%
402 | 10710020-001-0090 | 2018 |  | Concreting of Nangka-Narra FMR | Bayawan City | 5500000 | 2018-04-01 | 2019-05-31 | 100% | 4539901.35 |  | Completed: COC Issued on 07/01/9; Materials delivered- 96%; re-bid- 4%
403 | 10710020-001-0105 | 2018 |  | Concreting of Tabuan- Banaybanay-Lapay-Bugay-San Jose-Manduao FMR | Bayawan City | 28340000 | 2019-05-29 | 43716 | 100% | 28213392.75
404 | 10710020-001-0103 | 2018 |  | Concreting of Road from Sitio Balastro to Sitio Candulion to Pulangyuta, Barangay Kalamtukan | Kalamtukan | 10500000 | 2018-01-08 | 2019-08-31 | 99% | 7285218.13 |  | On-Going: Materials delivered- 96%; partial delivery- 2%; for delivery- 2%
405 | 10710020-001-0104 | 2018 |  | Concreting of Road with Drainage Canal at Upper Napit-an, Maninihon | Maninihon | 300000 | 2018-04-01 | 2018-07-31 | 100% | 175615.88
406 | 10710020-001-0102 | 2018 |  | Concreting of Road from Highway Intersection to Minaba Elem. School, Brgy. Minaba | Bayawan City | 1000000 | 2018-04-01 | 2018-09-30 | 100% | 703131.2 |  | Completed: COC Issued on 07/01/9; Materials delivered- 100%
407 | 10710020-001-0099 | 2018 |  | Concreting of Road at Sitio Kasla, Brgy. Nangka | Nangka | 850000 | 2018-04-01 | 2018-09-30 | 100% | 653409.03
408 | 10710020-006-0020 | 2018 |  | Construction of Flat Slab Bridge at Sitio Terong, Narra | Narra | 600000 | 2018-04-01 | 2019-06-30 | 100% | 520886.82 |  | Physically Completed: Materials delivered- 100%
409 | 10710020-001-0107 | 2018 |  | Road Concreting from Proper Narra to Purok III, Brgy. Narra | Narra | 500000 | 2018-04-01 | 2018-10-16 | 100% | 394052.4 |  | Physically Completed: Materials delivered- 88%; Partial delivery - 4%; For delivery- 8%
410 | 10710020-001-0089 | 2018 |  | Concreting of FMR from National Highway to Sitio Lapacon, Brgy. Pagatban | Bayawan City | 500000 | 2018-04-01 | 2018-08-31 | 100% | 394562.39 |  | Physically Completed: Materials delivered- 87%; partial delivery - 5%; For delivery- 8%
411 | 10710020-001-0100 | 2018 |  | Concreting of Road at Sitio Upper Pamu-at, San Isidro | San Isidro | 500000 | 2018-04-01 | 2020-03-16 | 92.5% | 266044 |  | Temporarily Stopped: Road not yet passable
412 | 10710020-001-0101 | 2018 |  | Concreting of Road at Upper Talao, San Isidro | San Isidro | 600000 | 2018-10-01 | 2019-03-31 | 100% | 514849.54 |  | Completed: COC Issued on 07/01/19Consolidated Materials delivered- 94%; rebid- 3% [plywood]; cancelled-3% [sack cloth][sack cloth]
413 | 10710020-001-0108 | 2018 |  | Road Shouldering Along Zamora St., Brgy. Ubos | Ubos | 500000 | 2018-06-16 | 2018-11-30 | 100% | 428565.85 |  | Completed: COC Issued on 07/01/9; Materials delivered- 98%; partial delivery- 2%
414 | 10710020-001-0110 | 2018 |  | Road Surfacing from Barangay Proper to Sitio Gawgaw to Sitio Aya, Brgy. Bugay | Bugay | 839286.43 | 2019-03-01 | 2020-12-31 | 20% | 216510.55 |  | Temporarily Stopped: due to road not passable; Pending: Materials delivered- 97%; re-bid- 3%: No H.E Available
415 | 10710020-001-0111 | 2018 |  | Road Surfacing from Barangay Proper to Sitio Mambuy-og to Sitio Canlantang, Brgy. Bugay | Bugay | 839285 | 2019-01-04 | 2019-12-31 | 97.5% | 442836.94 |  | On-Going Materials delivered- 97%; re-bid- 3%: No H.E Available
416 | 10710020-001-0109 | 2018 |  | Road Surfacing at Barangay Cansumalig | Cansumalig | 1078571.43 |  |  |  | 134866.57
418 | 10710020-004-0017 | 2018 |  | Installation of Cylindrical Culvert with Riprap at Proper Narra | Narra | 578571.43 | 2018-06-16 | 2019-08-31 | 100% | 497818.65
420 | 0 | 2018 |  | Construction of Small Scale Irrigation Projects (SSIP): | Bayawan City
421 | 10710020-003-0007 | 2018 |  | a. Purok Mangga, Brgy. Manduao | Manduao | 800000 | 2018-06-01 | 2020-04-30 | 74% | 593670.45 |  | Materials delivered- 95%; re-ad - 5% C/O D.A
422 | 10710020-003-0008 | 2018 |  | b. Sitio Dita, Brgy. Tabuan | Tabuan | 800000 | 2018-06-01 | 2020-04-30 | 37% | 299129.89 |  | Materials delivered- 95%; re-ad - 5% C/O D.A
423 | 10710020-003-0009 | 2018 |  | c. Upper Canlinte, Brgy Ali-is | Ali-is | 800000 | 2018-06-01 | 2020-04-30 | 54% | 438996.33 |  | Materials delivered- 95%; re-ad - 5% C/O D.A
424 | 10710020-003-0010 | 2018 |  | Rehabilitation of Irrigation Canal at Brgy. Tabuan | Tabuan | 915000 | 2019-03-01 | 2020-03-10 | 95% | 773915.66
435 | 0 | 2018 |  | Construction of Barangay Public Market, Ali-is (Phase 1) | Bayawan City | 1000000 |  |  |  | 0
436 | 10710030-005-0001 | 2018 |  | Completion of Minaba Mini Slaughterhouse Phase III | Minaba | 500000 | 2018-10-16 | 2019-07-31 | 100% | 419375.96
437 |  | 2018 |  | Construction of Rainwater Harvesting Systems for Nurseries:
438 | 10710020-002-0075 | 2018 |  | a. Brgy. San Miguel | San Miguel | 250000 | 2018-10-01 | 2018-11-30 | 100% | 193602.58
439 | 10710020-002-0076 | 2018 |  | b. Brgy. Tayawan | Tayawan | 250000 | 2018-10-16 | 2019-05-31 | 100% | 190464.82
440 | 10710020-002-0077 | 2018 |  | c. Brgy. Cansumalig | Cansumalig | 250000 | 2018-10-16 | 2019-06-30 | 100% | 189960.28
441 | 10710020-002-0078 | 2018 |  | d. Brgy. Manduao | Manduao | 250000 | 2018-10-16 | 2020-05-31 | 60% | 158504.74
442 | 10710020-002-0079 | 2018 |  | e. Brgy. Kalamtukan | Kalamtukan | 250000 | 2018-10-16 | 2020-05-31 | 73% | 183871.5
456 | 10710030-030-0159 | 2018 |  | Construction of Fish Processing Center @ Brgy. Suba | Suba | 2500000 | 2019-04-01 | 2019-12-31 | 80% | 1940773.71
458 | 10710030-030-0161 | 2018 |  | Major Repair of Narra Barangay Agricultural Development Center (BADC) | Narra | 520000 | 2018-09-30 | 2020-03-31 | 69% | 360902.67 |  | C/O GSO; Materials delivered- 100%
459 | 10710030-030-0160 | 2018 |  | Major Repair of Manduao Barangay Agricultural Development Center (BADC) | Manduao | 290000 | 2018-09-30 | 2020-03-31 | 78% | 227443.68 |  | C/O GSO; Materials delivered- 97%; for delivery- 3%
461 | no obligation | 2018 |  | Purchase of Boom Truck | Bayawan City | 1600000 |  |  |  | 0
462 |  | 2018 |  | Purchase of 1 Unit Backhoe for Barangay Tayawan | Tayawan | 1678571.43 |  |  |  | 0
464 | 10701010-001-0129 | 2018 |  | Purchase of Lot for Agricultural Research Center | Maninihon | 16000000 | 2018-12-01 | 2019-12-31 | 100% | 15710989
465 | 0 | 2018 |  | Establishment of Agricultural Research Center | Maninihon | 6895568.71 |  |  |  | 0
466 | 10710020-001-0125 | 2018 |  | Improvement of Bugay-San Jose-Manduao FMR | Bayawan City | 3000000 | 2018-10-15 | 2019-01-06 | 100% | 2959185.3
467 | 10710020-001-0127 | 2018 |  | Concreting of Urban Roads with Drainage System (GomeZ St.) | Poblacion | 12885436.16 | 2019-01-16 | 2020-02-29 | 80% | 9845590.5 |  | Materials delivered- 57%; for delivery- 15%; cancelled- 1%; re-bid- 27%; Pending waiting for electrical materials delivery
|  |  |  | Total Projects for Economic Development - Contg App |  | 323572730.25 |  |  |  | 230633518.37
ENVIRONMENTAL MANAGEMENT
61 |  | 2004 |  | Sanitary Landfill (Land Acquisition) 2004 | Maninihon | 1000000 |  |  |  | 8311
62 |  | 2001 |  | Sanitary Landfill - Dumpsite Acquisition | Maninihon | 500000 |  |  |  | 0
71 | *10710020-007-0002 | 2013 |  | Construction of Drainage Canal with Cover Along City Streets | Bayawan City | 606779.6 | 2014-06-02 | 2014-11-30 | 100% | 544360.59
182 | *10710020-007-0010 | 2016 |  | Construction of Drainage City Streets - Zamora, Teologio Sts, Subd Area | Zamora, Teologio & Subd Area | 3000000 | 2017-01-01 | 2017-09-15 | 100% | 2461029.39
183 | *10710020-005-0008 | 2016 |  | Rehabilitation of River Bank Protection at Sitio Ebuan | Nangka | 2000000 | 2017-03-16 | 2018-12-31 | 100% | 1451778.7
187 | *10710020-007-0011 | 2016 |  | Const. of Drainage Canal at along Burgos St. & AlongBollos St. Brgy Ubos | Ubos | 500000 | 2017-02-01 | 2017-06-30 | 100% | 442668.24
189 | *10710020-005-0007 | 2016 |  | Rehabilitation of Riverbank @ Brgy. Nangka | Nangka | 1000000 | 2018-05-16 | 2018-12-31 | 100% | 1013905.35
259 | 10710020-007-0017 | 2017 |  | Concreting of Drainage Canal Cover Along National Highway, Brgy. Villareal | Villareal | 678571.43 | 2017-11-16 | 2019-12-31 | 90% | 491510.65 |  | Pending: Due to transfer of site location, Barangay & SP resolution on process; Materials Delivered - 92%: cancelled- 8%
307 | *10710020-007-0016 | 2017 |  | Construction of Concrete Covered Canals, Brgy. Tinago | Tinago | 50000 | 2017-10-01 | 2017-10-31 | 100% | 46908.05
308 | *10710020-007-0019 | 2017 |  | Construction of Concrete Covered Canals, Brgy. Ubos | Ubos | 100000 | 2017-10-16 | 2017-11-30 | 100% | 84467.6
311 | *10710020-007-0015 | 2017 |  | Construction of Concrete Covered Canal, Brgy. Suba | Suba | 400000 | 2017-08-16 | 2018-01-31 | 100% | 360021.69
223 | 10710020-007-0022 | 2017 |  | Construction of Drainage at Cabugcabugan Creek, Brgy. Poblacion, Phase 4 | Poblacion | 1356746.77 | 2017-11-16 | 2020-08-31 | 83% | 1197855.77 |  | Pending: Awaits Consultation( BMAKBI, Eldie Tinapao)
320 | *10710020-007-0020 | 2017 |  | Construction of Concrete Covered Canal at Zamora St. Brgy Suba |  | 173060.9 | 2017-08-16 | 2018-01-31 | 100% | 170642.5
321 | *10710020-007-0021 | 2017 |  | Construction of Concrete Canal Cover Along Rizat St. Brgy Tinago |  | 1000000 | 2017-11-16 | 2018-03-31 | 100% | 678776.75
224 | 10710020-005-0010 | 2017 |  | Construction of Riverbank Protection at Camayaan Creek,Brgy. Malabugas | Malabugas | 1000000 | 2018-01-16 | 2018-10-16 | 100% | 898258.82 |  | Physically Completed: Materials Delivered - 100%
222 | 10710020-008-0006 | 2017 |  | Flood Control Project at Brgy. Malabugas, Phase 2 | Malabugas | 1500000 | 2017-09-01 | 2018-06-30 | 100% | 1331896.08 |  | Completed: COC Issued on 07/01/19 Materials Delivered - 100%
417 | 10710020-007-0026 | 2018 |  | Construction of Drainage Canal from Upper Napit-an to Lower Napit-an, Brgy. Maninihon | Maninihon | 650000 | 2018-06-01 | 2018-09-30 | 100% | 546606.01 |  | Completed: COC Issued on 07/01/9; Materials delivered- 100%
419 | 10710020-007-0025 | 2018 |  | Covering of Drainage Canals along Gomez St., Brgy. Ubos | Ubos | 1078571.43 | 2018-08-12 | 2020-03-31 | 100% | 775677.86 |  | C/O GSO; Materials delivered- 100%
463 |  | 2018 |  | Purchase of Garbage Compactor Truck | Bayawan City | 1500000 |  |  |  | 0
|  |  |  | Total Projects for Environmental Management - Contg App |  | 18093730.13 |  |  |  | 12504675.05
|  | TOTAL EDF CONTINUING APPROPRIATION |  |  |  | 485745064.02 |  |  |  | 318688091.65
|  | TOTAL EDF - CURRENT & CONTINUING APPROPRIATION |  |  |  | 708571492.37 |  |  |  | 396550042.25
|  |  |  | CORAZON P. LIRAZAN, CPA | [5 empty] | HON. PRYDE HENRY A. TEVES
|  |  |  | City Accountant | [5 empty] | City Mayor

## file
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION REPORT
As of March 31, 2020
CITY OF BAYAWAN
[5 empty] | Location | Total Cost (per Budget Approp) | Target Start Date | Target Completion Date | Project Status |  | No. of Ext., if any | Remarks
1 | Project Code | Year |  | Program/Project |  |  |  |  | % of Completion | Total Cost Incurred (per Acctg)
3 |  | CURRENT APPROPRIATION
4
SOCIAL DEVELOPMENT
|  | 2019 |  | Construction of Multi-Purpose Pavement at Sitio -Upper Pinangimnan | San Jose | 839285.7 | 2020-04-15 |  | 20% | 0 |  | On-going: Advance Implementation |  |  |  |  | 839285.7
|  | 2019 |  | Construction of Multi-Purpose Pavement at Sitio Pitogo 1 | San Jose | 839285.73 | 2020-04-15 |  | 20% | 0 |  | On-going: Advance Implementation |  |  |  |  | 839285.73
7 |  | 2019 |  | Lot Acquisition for Dita Relocation | Tabuan | 5000000 | [10 empty] | 5000000
23 | 0 | 2019 |  | Construction & Installation of Water Supply Systems for Barangays Malabugas, San Roque, Minaba, San Miguel and Tayawan | Various Brgys | 11000000 |  |  |  | 0 |  | Implemented by BAWAD |  |  |  |  | 11000000
28 | 10710030-002-0028 | 2019 |  | Construction of Day Care Center, Brgy San Miguel | Bayawan City | 400000 | 2019-07-16 | 2019-09-30 | 100% | 258202.4 |  | Physically Completed: COC Issued 01/23/2020 |  | 231032.84 | 27169.56 | 258202.4 | 141797.6
25 | 0 | 2019 |  | Electrification Project at Purok Ipil-Ipil, San Roque | San Roque | 600000 |  |  |  | 0 |  | Implemented by NORECO |  |  |  |  | 600000
33 | 10710010-002-0011 | 2019 |  | Construction of Concrete Fence of Minaba Elementary School | Minaba | 500000 | 2019-05-16 | 2020-03-31 | 90% | 206871.98 |  | Physically Completed: Materials delivered- 92%; for delivery - 4%; Re-ad- 4% |  |  |  |  | 293128.02
34 | 10710010-002-0013 | 2019 |  | Construction of Concrete Fence of Canabuan Elementary School | Minaba | 500000 | 2019-01-06 | 2020-03-31 | 90% | 222376.86 |  | On-Going; Materials delivered- 19%; for delivery-4%; re-ad-77% (P.O. cancelled); Procurement Problem; Temprary Stopped |  |  |  |  | 277623.14
35 | 10710010-002-0012 | 2019 |  | Construction of Concrete Fence of Minaba High School | Minaba | 678571.43 | 2019-01-06 | 2020-03-31 | 90% | 191587.41 |  | On-Going; Materials delivered- 20%; for delivery-4%; re-ad-76% (P.O. cancelled); Procurement Problem; Temporary Stopped |  |  |  |  | 486984.02
38 | 10710010-002-0015 | 2019 |  | Construction of Concrete Fence of Bolirocon Elementary School, San Isidro | Bolirocon, San Isidro | 278571.43 | 2019-01-08 | 2020-03-31 | 100% | 188217 |  | Physically Completed: Materials delivered- 92%; for delivery - 4%; Re-ad- 4% |  |  |  |  | 90354.43
40 | 10710010-002-0010 | 2019 |  | Construction of Perimeter Fence at San Roque Elementary School | San Roque | 578571.43 | 2019-01-06 | 2020-03-31 | 90% | 180751.8 |  | On-Going; Materials delivered- 20%; for delivery-4%; re-ad-76% (P.O. cancelled) ; Procurement Problem; Temporary Stopped |  |  |  |  | 397819.63
32 | 10710030-030-0198 | 2019 |  | Completion of Lapay Multi-Purpose Pavement | Dawis | 360000 | 2019-06-16 | 2019-08-31 | 100% | 211987.95 |  | Physically Completed: COC Issued 01/23/2020 |  |  |  |  | 148012.05
36 | 10710030-030-0211 | 2019 |  | Construction of Barangay Multi-Purpose Building, Nangka | Nangka | 1678571.43 | 2019-06-30 | 2020-04-30 | 15% | 860544.88 |  | Materials delivered- 56%; for delivery- 3%; re-ad- 41%; For Implementation |  |  |  |  | 818026.55
37 | 10710030-030-0209 | 2019 |  | Construction of 2-Storey Multi-Purpose Building, Brgy. Poblacion | Poblacion | 1678571.43 | 2019-06-30 | 2020-06-30 | 30% | 961005.84 |  | Materials delivered- 27%; for delivery- 58%; re-ad- 25% |  |  |  |  | 717565.59
39 | 10710030-001-0012 | 2019 |  | Construction of Multi-Purpose Building, Barangay San Isidro (Phase 3) | San Roque | 1000000 | 2019-09-30 | 2020-07-31 | 8% | 169435.96 |  | Materials delivered - 6%;for delivery- 46%; re-ad- 48% |  |  |  |  | 830564.04
41 | 0 | 2019 |  | Construction of Barangay Multi-Purpose Building, Tinago (Phase 3) | Tinago | 1678571.43 | 2020-03-01 |  | 30% | 0 |  | On- Going |  |  |  |  | 1678571.43
|  |  |  | Total Projects for Social Development - Current Appropriation |  | 27610000.01 |  |  |  | 3450982.08 | [6 empty] | 24159017.93
0
0
0
|  |  | ECONOMIC DEVELOPMENT | [13 empty] | 0
|  | 2019 |  | Supply & Installation of Hog & Cattle Slaughterhouse Equipment for Bayawan City AA Slaughterhouse Plant | Bayawan City | 16478571.43 |  |  |  | 0 | [6 empty] | 16478571.43
|  | 2019 |  | Construction of Dawis Public Market (Phase 2) | Dawis | 2000000 |  |  |  | 0 | [6 empty] | 2000000
5 |  | 2019 |  | Loan Amortization |  | 58000000 |  |  |  | 49166376.06 | [6 empty] | 8833623.94
8 |  | 2019 |  | Lot Acquisition for Road Right of Way | Villareal | 500000 | [10 empty] | 500000
9 |  | 2019 |  | Lot Acquisition for Agricultural Development Center (Tan-ayan) | Tan-ayan | 2500000 | [10 empty] | 2500000
11 | 10710020-001-0135 | 2019 |  | Wayang Access Road Development | Nangka | 20000000 | 2019-02-16 | 2020-04-30 | 75% | 11084614.23 |  | On- Going: Materials delivered- 97%; re-ad- 3% |  |  |  |  | 8915385.77
12 | 10710020-002-0088 | 2019 |  | Construction of Ondol-Napit-an FMR | Bayawan City | 20000000 | 2019-03-15 | 2020-08-31 | 40% | 9678023.68 |  | Materials delivered- 97%; re-ad- 3% |  |  |  |  | 10321976.32
13 | 10710020-001-0136 | 2019 |  | Concreting of Access Road from National Highway to Palongpong Agricultural Development Center | Bayawan City | 9000000 | 2019-01-04 | 2020-03-31 | 99% | 4299985.96 |  | On-Going; Materials delivered- 72%; partial delivery- 2%; for delivery- 10%; re-ad- 16% |  |  |  |  | 4700014.04
14 | 10710020-001-0134 | 2019 |  | Improvement of Road Leading to Danapa Inland Aquaculture Facility | Nangka | 2000000 | 2019-03-16 | 2019-12-31 | 100% | 1240696.65 |  | Physically Completed: COC Issued 01/23/2020 | 1138792.68 | 101903.97 |  | 1240696.65 | 759303.35
15 | 10710020-001-0137 | 2019 |  | Concreting of Perimeter Road at BCWMEC | Maninihon | 2000000 | 2019-01-06 | 2020-02-15 | 100% | 1596679.95 |  | Physically Completed |  |  |  |  | 403320.05
16 | 10710020-001-0139 | 2019 |  | Concreting of Urban Roads with Drainage System (Gomez St.) | Poblacion | 3000000 | 2019-07-16 | 2020-03-31 | 80% | 1363098.11 | [6 empty] | 1636901.89
17 | 10710020-001-0041 | 2019 |  | Improvement of Maninihon-Cansumalig-San Isidro FMR |  | 2387650.49 |  |  |  | 0 | [6 empty] | 2387650.49
30 | 10710030-004-0006 | 2019 |  | Construction of Public Market Stalls in Omod, Maninihon (Phase 1) | Bayawan City | 1678571.43 | 2019-06-16 | 2020-05-31 | 80% | 1340463.01 |  | On-Going; Materials delivered - 96%; for delivery - 2%: re-ad - 2% |  |  |  |  | 338108.42
42 | 0 | 2019 |  | Establishment of Agricultural Research Center |  | 10877134.99 |  |  |  | 0 | [6 empty] | 10877134.99
43 |  |  |  | Purchase of Construction & Heavy Equipment: | [12 empty] | 0
44 |  |  |  | 1 unit Bulldozer |  | 15000000 |  |  |  | 0 | [6 empty] | 15000000
45 |  |  |  | 1 unit Backhoe |  | 12000000 |  |  |  | 0 | [6 empty] | 12000000
46 |  |  |  | 1 unit Trailer Mounted DW100-T Drilling Rig with Accessories |  | 3594500 |  |  |  | 0 | [6 empty] | 3594500
47 |  |  |  | 2 units 6-Wheeler Dump Truck |  | 4400000 |  |  |  | 0 | [6 empty] | 4400000
52 |  | 2019 |  | Purchase of Livestock Breeding Stocks |  | 2000000 |  |  |  | 0 | [6 empty] | 2000000
|  |  |  | Total Projects for Economic Development - Current Appropriation |  | 187416428.34 |  |  |  | 79769937.65 | [6 empty] | 107646490.69
0
0
|  |  | ENVIRONMENTAL MANAGEMENT | [13 empty] | 0
19 | 10710020-007-0030 | 2019 |  | Construction of Drainage Canal at Magsulay Agricultural Development Center | Narra | 400000 | 2019-07-16 | 2020-03-31 | 97% | 328396.65 |  | On-Going: Materials delivered- 100% |  |  |  |  | 71603.35
21 | 10710020-007-0029 | 2019 |  | Concreting of Drainage Canals at Barangay Proper, San Isidro | Bayawan City | 400000 | 2019-01-06 | 2019-08-31 | 100% | 335921.21 |  | Physically Completed: COC Issued 01/23/2020 |  |  |  |  | 64078.79
49 |  | 2019 |  | Purchase of Garbage Compactor Truck |  | 5000000 |  |  |  | 0 | [6 empty] | 5000000
50 |  | 2019 |  | Purchase of Vacuum Declogger Truck |  | 2000000 |  |  |  | 0 | [6 empty] | 2000000
|  |  |  | Total Projects for Environmental Mgt - Current Appropriation |  | 7800000 |  |  |  | 664317.86 | [6 empty] | 7135682.14
0
53 |  |  | TOTAL DF - CURRENT APPROPRIATION |  |  | 222826428.35 |  |  |  | 83885237.59 | [6 empty] | 138941190.76
54 | [16 empty] | 0
55 | [16 empty] | 0
0
0
0
56 |  | CONTINUING APPROPRIATION | [14 empty] | 0
57 | [16 empty] | 0
0
|  |  | SOCIAL DEVELOPMENT | [13 empty] | 0
63 |  | 2011 |  | Renovation of BDH Canteen | BDH, Ubos | 114000 | 2011-06-01 | 2012-12-31 | 100% | 80418 | [6 empty] | 33582
66 | *10710030-030-0023 | 2012 |  | Improvement of Bayawan City Boulevard (Landscaping fronting GK Village) | Villareal | 535115.83 | 2013-08-01 | 2014-03-15 | 100% | 495907.52 |  | Physically Completed: COC issued on 05/23/18 ( Liquidating balances, Materials delivered - 93%; rebid - 7% ;# 12,16-rebid, P.O cancelled) |  |  |  |  | 39208.31
67 | *10710030-030-0021 | 2013 |  | Construction of Sports Center and Children's Playground, Phase 3 | Suba | 3000000 | 2013-03-18 | 2015-05-30 | 100% | 2668470.08 |  | Physically Completed: COC issued on 05/23/18; (delivered materials- 82%; for delivery-2%; re-bid-16%); ITEM# 35, 53, 54, 55 for Canvass & referred to BAC |  |  |  |  | 331529.92
68 | *10710030-030-0024 | 2013 |  | Construction of Covered Court at BCsTEC, Phase II | Cabcabon, Banga | 3008100 | 2013-10-01 | 2017-06-30 | 100% | 2783489.42 |  | Physically Completed: COC issued on 05/23/18 |  |  |  |  | 224610.58
69 | 10710030-030-0025 | 2013 |  | Rehabilitation of GK Septic Tanks | Villareal | 3104400 | 2013-11-18 | 2020-12-31 | 2% | 77968.68 |  | Pending: sub-standard Fiber Glass septic Tank delivered by supplier not accepted by LGU |  |  |  |  | 3026431.32
70 | *10710020-002-0036 | 2013 |  | Improvement of Water System for 21 Rural Barangays | Bayawan City | 568710 | 2016-07-01 | 2017-07-31 | 100% | 468013.78 | [6 empty] | 100696.22
82 | 10710030-030-0058 | 2015 |  | Construction of Evacuation Center, Brgy. San Miguel | San Miguel | 800000 | 2016-01-02 | 2019-10-31 | 100% | 753942.58 | [6 empty] | 46057.42
83 | *10710030-030-0059 | 2015 |  | Construction of Portable Toilet | Bayawan City | 770000 | 2016-01-15 | 2018-03-31 | 100% | 542396.04 | [6 empty] | 227603.96
84 | 10710010-002-0003 | 2015 |  | Const. of GK Village Perimeter Fence | Villareal | 2000000 | 2019-01-10 | 2020-12-31 | 95% | 1716184.88 | [6 empty] | 283815.12
96 | 10710020-002-0037 | 2015 |  | Water System Development @ Sitio Camague to Cabiguhan, Brgy Banaybanay | Banaybanay | 303389.8 | 2017-02-16 | 2020-12-31 | 50% | 206913.03 |  | Pending: Declared site has no water source |  |  |  |  | 96476.77
98 | 10710030-003-0001 | 2016 |  | Rehabilitation of Health Center & Const. of Lying-in Facility, Brgy. Poblacion, Phase 2 | Poblacion | 500000 | 2016-09-16 | 2017-06-30 | 100% | 320188.77 | [6 empty] | 179811.23
106 | 10710030-002-0010 | 2016 |  | Construction of Day Care Centers in Nangka and Napit-an/Rehabilitation of Day Care Centers in Minaba, Narra, Purok 4 Tayawan | Nangka, Napit-an, Minaba, Narra, Tayawan | 2000000 | 2017-01-06 | 2020-12-31 | 51.7% | 1593541.55 |  | Pending: 4 Units Completed, 1 unit not yet started due to no lot available |  |  |  |  | 406458.45
107 | *10710030-030-0079 | 2016 |  | Improvement of CICL Center Faciltities | Banga | 975000 | 2017-11-16 | 2019-03-31 | 100% | 810122.28 |  |  | 764122.65 | 45999.63 |  | 810122.28 | 164877.72
108 | *10710030-030-0081 | 2016 |  | Completion of Paglaum Center at Cabcabon | Cabcabon | 500000 | 2016-10-16 | 2018-05-31 | 100% | 374922.29 |  |  | 352817.03 | 22105.26 |  | 374922.29 | 125077.71
109 | *10710030-030-0069 | 2016 |  | Completion of Women's Multi-purpose Center | Boyco | 1000000 | 2016-12-01 | 2018-11-30 | 100% | 832656.5 |  |  | 783751.69 | 48904.81 |  | 832656.5 | 167343.5
110 | 10710030-030-0078 | 2016 |  | Construction of Women's Detention Cell | Banga | 400000 | 2019-07-29 | 2019-10-30 | 53% | 223432.29 |  | Cancelled as per instruction from DSWD | 211222.56 | 12209.73 |  | 223432.29 | 176567.71
111 | 10710030-030-0067 | 2016 |  | Construction of Women's Facilities in Evacuation Center | Var. Brgys | 200000 | 2019-07-16 | 2020-03-31 | 98% | 168303.43 |  | Material Estimates is inadequate |  |  |  |  | 31696.57
112 | *10710030-002-0009 | 2016 |  | Construction of Day Care Center at Brgy. Proper, Brgy,. San Miguel | San Miguel | 500000 | 2016-08-16 | 2017-05-31 | 100% | 447026.94 |  |  | 440367.22 | 6659.72 |  | 447026.94 | 52973.06
113 | 10710030-030-0073 | 2016 |  | Const. of Bleachers & CRs @ Existing Gyms for evacuation (Tinago, Boyco, Suba,Poblacion, Banga, Malabugas, Villareal, BNHS) | Various Brgys | 6000000 | 2019-07-30 | 2019-07-31 | 100% | 5105050.96 | [6 empty] | 894949.04
114 |  |  |  | a. Tinago |  |  |  |  | 100% | [7 empty] | 0
115 |  |  |  | b. Boyco |  |  |  |  | 100% | [7 empty] | 0
116 |  |  |  | c. Suba |  |  |  |  | 100% | [7 empty] | 0
117 |  |  |  | d. Poblacion |  |  |  |  | 100% | [7 empty] | 0
118 |  |  |  | e. Banga |  |  |  |  | 100% | [7 empty] | 0
119 |  |  |  | f. Malabugas |  |  |  |  | 100% | [7 empty] | 0
120 |  |  |  | g.Villareal |  |  |  |  | 100% | [7 empty] | 0
121 |  |  |  | h. BNHS |  |  |  |  | 100% | [7 empty] | 0
123 | *10710030-030-0074 | 2016 |  | Const. of Comfort Rooms in 13 Evacuation Ctrs. | Var Brgys | 1054174.83 | 2019-04-30 | 2018-02-28 | 100% | 1056488.39 | [6 empty] | -2313.56
124 |  |  |  | a. Banga Central School |  |  |  |  | 100% | [7 empty] | 0
125 |  |  |  | b. BCSTEC Elementary & Highschool |  |  |  |  | 100% | [7 empty] | 0
126 |  |  |  | c. Malabugas Highschool |  |  |  |  | 100% | [7 empty] | 0
127 |  |  |  | d. Nangka Elementary School |  |  |  |  | 100% | [7 empty] | 0
128 |  |  |  | e. Guisocon Elementary School |  |  |  |  | 100% | [7 empty] | 0
129 |  |  |  | f. Atilano Cabangal Memorial Highschool |  |  |  |  | 100% | [7 empty] | 0
130 |  |  |  | g. Tavera Elementary School |  |  |  |  | 100% | [7 empty] | 0
131 |  |  |  | h. Dean Felix Gaudiel Memorial Elementary School |  |  |  |  | 100% | [7 empty] | 0
132 |  |  |  | i. H. Bido Jordan Elementary School |  |  |  |  | 100% | [7 empty] | 0
133 |  |  |  | j. Bayawan National Highschool |  |  |  |  | 100% | [7 empty] | 0
134 |  |  |  | k. Maninihon Elementary & Highschool |  |  |  |  | 100% | [7 empty] | 0
135 |  |  |  | l. H. Bido Jordan Highschool School |  |  |  |  | 100% | [7 empty] | 0
136 |  |  |  | m. SLGTMES |  |  |  |  | 100% | [7 empty] | 0
137 | *10710030-030-0072 | 2016 |  | Improvement of Covered Court/Evacuation Ctr., Bry. Banga | Banga | 500000 | 2019-03-16 | 2020-03-31 | 100% | 435324.84 | [6 empty] | 64675.16
138 | 10710030-030-0071 | 2016 |  | Const. of Evacuation Ctr., Brgy. San Roque | San Roque | 500000 | 2017-06-16 | 2019-06-30 | 100% | 361521.48 | [6 empty] | 138478.52
139 | *10710030-030-0070 | 2016 |  | Const. of Covered Court/Evacuation Ctr., Bry. Suba | Suba | 500000 | 2016-12-16 | 2017-05-31 | 100% | 454964.53 | [6 empty] | 45035.47
140 | *10710030-030-0082 | 2016 |  | Const. of Multi-Purpose Bldg. for Evacuation Ctr., Brgy Villareal | Villareal | 500000 | 2019-01-05 | 2018-11-30 | 100% | 436829.46 |  |  | 431575.23 | 5254.23 |  | 436829.46 | 63170.54
143 | *10710030-030-0084 | 2016 |  | Establishment of Youth Development Center |  | 5000000 | 2017-06-15 | 2018-09-01 | 100% | 4000896.6 | [6 empty] | 999103.4
146 | 0 | 2016 |  | LGU Counterpart for the Construction of Sports Complex |  | 15000000 |  |  |  | 0 |  | No Funding |  |  |  |  | 15000000
175 | 10710020-002-0041 | 2016 |  | Rehabilitation of San Isidro Water Supply System | Villareal | 350000 | 2019-05-15 | 2020-06-30 | 54% | 189138.38 | [6 empty] | 160861.62
176 | *10710030-030-0085 | 2016 |  | Const. of Water Tank & Pipeline at Tabuan Brgy Proper | Tabuan | 500000 | 2017-05-01 | 2018-05-31 | 99.5% | 424113.31 | [6 empty] | 75886.69
177 | 10710020-002-0039 | 2016 |  | Construction of Tayawan Water System | Tayawan | 300000 | 2017-01-06 | 2020-02-29 | 95% | 267009.23 |  | Pending: Remaing work is installation of RCPC at the water source | 255424.64 | 11584.59 |  | 267009.23 | 32990.77
100 | *10710030-006-0010 | 2016 |  | Installation of Electrical System (Sitio Napit-an, Brgy Maninihon & Zamora Streets, Brgy. Suba) - | Suba | 1500000 | 2016-11-15 | 2018-08-31 | 100% | 1439250.62 | [6 empty] | 60749.38
101 | *264-005-1606-G0056 | 2016 |  | Purchase of Transforments & Primary Metering @ New Gov't. Center | Banga | 2545000 | 2016-11-24 | 2016-11-29 | 100% | 2540000 | [6 empty] | 5000
102 | *10710030-006-0009 | 2016 |  | Installation of Secondary Line Feeder @ New Gov't. Center | Banga | 800000 | 2016-02-13 | 2018-07-15 | 100% | 669519.56 | [6 empty] | 130480.44
103 | 10710020-001-0044 | 2016 |  | Establishment of Street Lighting Facilities - 2016 | Var. Brgys. | 400000 | 2019-03-15 | 2020-04-15 | 78% | 314630 | [6 empty] | 85370
104 | *10710020-001-0065 | 2016 |  | Installation of Street Lightings at Brgy Proper, Villasol | Villasol | 140000 | 2017-10-02 | 2017-10-30 | 100% | 133422.04 |  |  | 132852.6 | 569.44 |  | 133422.04 | 6577.96
190 |  | 2017 |  | Establishment of Montessori-Type Early Child Care Development Centers | Various Brgys | 1211000 | 2018-01-01 | 2018-11-30 | 100% | [7 empty] | 1211000
191 | 10710030-002-0011 | 2017 |  | a. Establishment of Montessori-Type Early Child Care Development Centers Phase 2 | Boyco | 2289000 | 2017-12-16 | 2020-02-10 | 99% | 1310863.71 |  | On-going |  |  |  |  | 978136.29
192 | 10710030-002-0014 | 2017 |  | b. Establishment of Montessori-Type Early Child Care Development Centers | Poblacion | 1211000 | 2018-01-01 | 2018-11-30 | 100% | 742624.7 |  | Physically completed |  |  |  |  | 468375.3
195 | 10710020-009-0003 | 2017 |  | Development of Tabuan People's Park | Tabuan | 2000000 | 2018-12-31 | 2020-04-20 | 100% | 1991861.08 |  |  | 1396904.13 | 594956.95 |  | 1991861.08 | 8138.92
196 | *10710030-030-0128/0129/0130 | 2017 |  | Construction of Coastal Park Comfort Rooms | Coastal Road | 4500000 | 2018-02-15 | 2018-05-27 | 100% | 4497336 | [6 empty] | 2664
197 | 264-009-1711-G0600 | 2017 |  | Construction of Children's Playground with Facilities, Ali-is | Ali-is | 500000 |  |  |  | 0 |  | Contract |  |  |  |  | 500000
198 | 10710030-003-0016 | 2017 |  | Improvement of Barangay Health Center Lying-In Clinic, Brgy. Malabugas | Malabugas | 678571.43 | 2019-01-10 | 2020-12-31 | 92% | 406333.27 | [6 empty] | 272238.16
199 | 264-004-1711-G0033 | 2017 |  | Improvement of Barangay Health Center & Lying-in Clinic, Brgy. Manduao | Manduao | 100000 |  |  |  | 0 |  | Contract |  |  |  |  | 100000
200 | 10710030-030-0132 | 2017 |  | Construction of Covered Court and Evacuation Center, Brgy. Pagatban | Pagatban | 1728571.43 |  |  |  | 0 |  | Contract |  |  |  |  | 1728571.43
201 | 10710030-030-0135 | 2017 |  | Improvement of Evacuation Center and Multi-Purpose Building, Brgy. Poblacion | Poblacion | 878571.43 | 2020-03-15 |  | 30% | 0 |  | On-going |  |  |  |  | 878571.43
202 | 10710030-002-0019 | 2017 |  | Construction of New Day Care Center at Brgy. Poblacion | Poblacion | 800000 |  |  |  | 0 |  | Outsource waiting for CTYRC Decision |  |  |  |  | 800000
203 | 10710030-003-0015 | 2017 |  | Construction of Lying-In Clinic, Brgy. San Isidro | San Isidro | 1178571.43 | 2019-02-24 | 2019-12-15 | 99.5% | 1177768.28 |  |  | 590297.46 | 587470.82 |  | 1177768.28 | 803.15
204 | 10710030-003-0006 | 2017 |  | Improvemen of Health Center and Lying-in Clinic, Brgy.San Roque | San Roque | 1678571.43 |  |  |  | 0 |  | Outsource |  |  |  |  | 1678571.43
205 | 0 | 2017 |  | Improvement of Barangay Health Center, Brgy. Tinago | Tinago | 600000 |  |  |  | 0 |  | Outsource |  |  |  |  | 600000
206 | 10710030-030-0131 | 2017 |  | Construction of Children's Playground with Facilities, Brgy. Villareal | Villareal | 500000 |  |  |  | 0 |  | Outsource |  |  |  |  | 500000
207 | 0 | 2017 |  | Construction of Multi-Purpose Center for Senior Citizens, Brgy. Villasol | Bayawan City | 50000 |  |  |  | 0 |  | Outsource |  |  |  |  | 50000
208 | 10710030-003-0005 | 2017 |  | Improvement of Barangay Health Center, Brgy. San Jose | San Jose | 60000 |  |  |  | 0 |  | Outsource |  |  |  |  | 60000
209 | 10710030-003-0007 | 2017 |  | Renovation of Barangay Health Center at Brgy. Tayawan | Tayawan | 150000 |  |  |  | 0 |  | Outsource |  |  |  |  | 150000
210 | 10710030-002-0020 | 2017 |  | Renovation of Day Care Center, Brgy. Tayawan | Tayawan | 100000 |  |  |  | 0 |  | Outsource |  |  |  |  | 100000
244 | 10710020-002-0052 | 2017 |  | Water System Development Project at Sitio Upper Camandagan, Brgy. Maninihon | Maninihon | 1000000 | 2019-05-01 | 2020-10-31 | 65% | 647344.67 |  | Implemented By BAWAD |  |  |  |  | 352655.33
242 | 10710020-002-0047 | 2017 |  | Construction of Water System at Proper Manduao | Manduao | 678571.43 | 2019-08-03 | 2019-12-31 | 99.8% | 485410.54 |  | Implemented By BAWAD | 459267.54 | 26143 |  | 485410.54 | 193160.89
245 | 264-009-1712-g0606 | 2017 |  | Improvement of Multi-Purpose Gymnasium and Evacuation Center, Brgy. Maninihon | Maninihon | 678571.43 | 2019-01-25 | 2020-02-15 | 60% | 588793.99 |  | Outsource |  |  |  |  | 89777.44
248 | 0 | 2017 |  | Establishment of Barangay Water Refilling Station, Brgy. Nangka | Nangka | 678571.43 |  |  |  | 0 |  | BAWAD |  |  |  |  | 678571.43
254 | 10710030-030-0134 | 2017 |  | Improvement of Covered Court for Evacuation Center, Brgy Suba | Suba | 1678571.43 |  |  |  | 0 |  | Outsource |  |  |  |  | 1678571.43
262 | 10710020-002-0050 | 2017 |  | Improvement/Rehabilitation of Water Systems for Various Barangays | Various Brgys | 934500 | 2019-01-31 | 2020-05-31 | 100% | 575402.78 |  | Physically Completed for COC: Materials Delivered 92% |  |  |  |  | 359097.22
263 | 10710030-030-0195 | 2017 |  | Installation of Water Refilling Stations at Various Barangays | Various Brgys | 2200000 | 2019-01-21 | 6/31/2020 | 48% | 1054599.9 |  | Pending: Building is not yet ready |  |  |  |  | 1145400.1
264 | 10710030-030-0094 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Bolo, Brgy. Villasol | Villasol | 600000 | 2018-02-16 | 2018-06-30 | 100% | 563174.77 | [6 empty] | 36825.23
265 | 264-009-1712-g0605 | 2017 |  | Construction of Multi-Purpose Building in Barangay Tayawan | Tayawan | 900000 |  |  |  | 0 | [6 empty] | 900000
266 | 0 | 2017 |  | Construction of Multi-Purpose Building in Barangay San Jose | San Jose | 900000 |  |  |  | 0 | [6 empty] | 900000
268 | *10710020-007-0018 | 2017 |  | Construction of Drainage Canal at Cansumalig High School | Cansumalig | 150000 | 2017-12-16 | 2018-03-30 | 100% | 126833.17 | [6 empty] | 23166.83
269 | 10710010-002-0004 | 2017 |  | Construction of Perimeter Fence of Multi-Purpose Building, Brgy. San Miguel | San Miguel | 100000 |  |  |  | 0 |  | Contract |  |  |  |  | 100000
270 | 10710020-002-0086 | 2017 |  | Improvement of Water Systems of Guintanaan Tayawan | Tayawan | 100000 | 2018-06-15 | 2020-12-31 | 3% | 3058 |  | Bawad |  |  |  |  | 96942
271 | 10710020-002-0046 | 2017 |  | Improvement of Water Systems at Manduao | Manduao | 110000 | 2019-07-20 | 2020-12-31 | 14% | 16811.66 |  | Bawad |  |  |  |  | 93188.34
272 | 0 | 2017 |  | Installation of Solar-Driven Water System for Catumbalan, Minaba | Minaba | 100000 |  |  |  | 0 |  | Bawad |  |  |  |  | 100000
273 | 10710030-006-0015 | 2017 |  | Installation of Solar-Driven Water System for Oban-Oban, Brgy. Kalumboyan | Kalumboyan | 50000 | 2019-08-15 | 2020-04-05 | 27% | 13835.24 |  | Bawad |  |  |  |  | 36164.76
274 | 0 | 2017 |  | Installation of Solar-Driven Water Systems for Napo, Brgy. Tayawan | Tayawan | 50000 |  |  |  | 0 |  | Bawad |  |  |  |  | 50000
275 | 0 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Upper Manlubid, Ali-is | Ali-is | 50000 |  |  |  | 0 | [6 empty] | 50000
276 | *10710030-030-0095 | 2017 |  | Construction of Multi-Purpose Pavement at Inner Canabuan, Minaba | Minaba | 300000 | 2018-02-16 | 2018-06-30 | 100% | 286328.7 |  | Completed: COC Issued on 07/01/19 Materials delivered- 100% |  |  |  |  | 13671.3
277 | 269-001-1712-g0052 | 2017 |  | Improvement of Water System at Sitio Pag-awitan, Brgy. Ali-is | Ali-is | 50000 | 2018-11-16 | 2020-04-30 | 70% | 35325 |  | BAWAD |  |  |  |  | 14675
278 | 10710020-002-0089 | 2017 |  | Rehabilitation and Improvement of Water System at Brgy. Banaybanay | Banaybanay | 220000 | 2019-03-26 | 2020-06-30 | 61% | 135396.8 |  | BAWAD |  |  |  |  | 84603.2
279 | 10710030-004-0004 | 2017 |  | Improvement of Barangay Public Market, Brgy. Malabugas | Malabugas | 50000 |  |  |  | 0 |  | CONTRACT |  |  |  |  | 50000
280 | 10710030-006-0016 | 2017 |  | Installation of Electrical System in Sitio Buli-buli, Brgy. Banga | Banga | 60000 | 2019-01-02 | 2019-02-28 | 100% | 43514.9 | [6 empty] | 16485.1
281 | 0 | 2017 |  | Installation of Electrical System in Brgy. Kalamtukan | Kalamtukan | 60000 | 2019-06-16 | 2019-07-31 | 100% | 60000 | [6 empty] | 0
282 | 10710030-006-0014 | 2017 |  | Installation of Electrical System in Brgy. Kalumboyan | Kalumboyan | 70000 | 2019-06-16 | 2019-07-31 | 100% | 54252.49 | [6 empty] | 15747.51
283 | 269-001-1801-g0057 | 2017 |  | Improvement of Water System, Brgy. San Roque | San Roque | 70000 | 2019-10-25 | 2020-05-01 | 67% | 64349.22 |  | BAWAD |  |  |  |  | 5650.78
284 | *10710020-002-0054 | 2017 |  | Improvement of Water System, Brgy. Ubos | Ubos | 145000 | 2018-01-06 | 2018-06-15 | 100% | 136216.2 |  | BAWAD |  |  |  |  | 8783.8
285 | 0 | 2017 |  | Improvement of Water System at Brgy. Villasol | Villasol | 70000 | 2019-08-31 | 2020-02-29 | 89% | 62346 | [6 empty] | 7654
286 | 10710030-030-0096 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Ponong, Brgy. Villasol | Villasol | 100000 | 2019-07-31 | 2020-05-31 | 62% | 73715.89 |  | Pending: Road not yet passable | 62715.89 | 11000 |  | 73715.89 | 26284.11
287 | *10710030-006-0012 | 2017 |  | Installation of Electrical System at Sitio Malampa, Brgy. Pagatban | Pagatban | 50000 | 2018-01-06 | 2018-06-30 | 100% | 44857.31 | [6 empty] | 5142.69
289 | *10710030-006-0013 | 2017 |  | Installation of Electrical System in Brgy. Malabugas | Malabugas | 50000 | 2018-03-16 | 2018-04-30 | 100% | 46024.73 | [6 empty] | 3975.27
290 | 10710020-002-0051 | 2017 |  | Improvement of Canabuan Water System, Brgy. Minaba | Minaba | 200000 | 6/31/2018 | 2020-12-31 | 30% | 62827.91 |  | BAWAD |  |  |  |  | 137172.09
292 | 264-009-1711-g0596 | 2017 |  | Improvement of Barangay Multi-Purpose Hall, Brgy. Ali-is | Ali-is | 200000 |  |  |  | 0 |  | CONTRACT |  |  |  |  | 200000
293 | 10710030-030-0097 | 2017 |  | Construction of Multi-Purpose Pavement at Purok 2, Brgy. Kalamtukan | Kalamtukan | 250000 | 2018-01-16 | 2018-06-30 | 100% | 224233.82 | [6 empty] | 25766.18
294 | *10710020-001-0071 | 2017 |  | Installation of Street Lights at Purok 4, Cansilong, Brgy. Malabugas | Malabugas | 100000 | 2018-03-16 | 2018-05-31 | 100% | 90521.66 | [6 empty] | 9478.34
296 | 0 | 2017 |  | Improvement of Water System, Brgy. Minaba | Minaba | 110000 | 2018-02-01 | 2020-02-20 | 84% | 93457 |  | BAWAD |  |  |  |  | 16543
298 | 0 | 2017 |  | Installation of Electrical System for Purok Ipil-Ipil, Brgy. San Roque | San Roque | 200000 |  |  |  | 0 |  | Implemented by NORECO |  |  |  |  | 200000
267 | *10710030-006-0018 | 2017 |  | Electrification Project for Various Barangays | Various Brgys | 10000 | 2018-01-06 | 2018-06-15 | 100% | 9060.49 | [6 empty] | 939.51
301 | 0 | 2017 |  | Construction of Alternative Learning System (ALS) Building, Brgy. Kalumboyan | Kalumboyan | 200000 |  |  |  | 0 |  | CONTRACT |  |  |  |  | 200000
303 | 10710020-002-0048 | 2017 |  | Installation of Deep Well at Atilano Cabangal High School, Brgy. Nangka | Nangka | 250000 | 2018-11-15 | 2020-12-31 | 4% | 10606.87 |  | Pending: re-PR magsaysay type deepwell not available anymore in the market |  |  |  |  | 239393.13
304 | 10710020-002-0081 | 2017 |  | Installation of Water System at Brgy. Pagatban | Pagatban | 50000 | 2018-03-16 | 2019-06-30 | 100% | 41977.04 | [6 empty] | 8022.96
251 | *10710020-002-0053 | 2017 |  | Installation of Water System at Brgy. Poblacion | Poblacion | 70000 | 2018-03-01 | 2018-03-15 | 100% | 28933.33 | [6 empty] | 41066.67
306 | *10710020-002-0045 | 2017 |  | Improvement of Water System at Purok Dol-Dol, Brgy. San Roque | San Roque | 100000 | 2017-11-16 | 2018-01-31 | 100% | 69781.89 | [6 empty] | 30218.11
309 | 264-009-1712-g0607 | 2017 |  | Improvement of Multi-Purpose Gym & Evacuation Center, Brgy. San Isidro | San Isidro | 495000 |  |  |  | 0 |  | CONTRACT |  |  |  |  | 495000
310 | *10710030-030-0092 | 2017 |  | Construction of Multi-Purpose Pavement, Brgy. Dawis | Dawis | 340000 | 2017-11-01 | 2018-02-28 | 100% | 327529.86 | [6 empty] | 12470.14
312 | 264-009-1712-g0604 | 2017 |  | Construction of Multi-Purpose Building at Relocation Site, Brgy. San Miguel | San Miguel | 500000 | [5 empty] | CONTRACT |  |  |  |  | 500000
314 | 10710030-030-0193 | 2017 |  | Construction of CICL at BADC Magsulay, Barangay Narra | Narra | 1000000 | 2018-10-09 | 2020-05-31 | 59.8% | 0 |  | CONTRACT: Temporary Suspended need supplemental budget |  |  |  |  | 1000000
317 | 0 | 2017 |  | Const. of Livelihood Center for Women at Brgy Villasol Proper |  | 100000 |  |  |  | 0 |  | CONTRACT |  |  |  |  | 100000
318 | 10710030-030-0104 | 2017 |  | Construction of Multi-purpose Pavement at Sitio Kaayahan (Phase 1) |  | 100000 | 2017-07-31 | 2020-03-31 | 100% | 79896.46 |  | Physically completed |  |  |  |  | 20103.54
319 | *10710030-030-0103 | 2017 |  | Completion of Multi-purpose Pavement at Sitio Tangistangisan |  | 330000 | 2018-01-02 | 2018-06-30 | 100% | 306358.29 |  | Physically completed |  |  |  |  | 23641.71
323 | 10710020-002-0082 | 2017 |  | Development of Water System at Sitio Tavera, Nangka |  | 5700000 | 2019-03-01 | 2020-03-01 | 83% | 2785304.59 |  | Implemented by: BAWAD |  |  |  |  | 2914695.41
324 | *10710020-002-0087 | 2017 |  | Improvement of Cabatangan-Tavera Water System |  | 154784.58 | 2019-01-16 | 2019-03-31 | 100% | 133057.22 |  | Implemented by: BAWAD |  |  |  |  | 21727.36
326 | 0 | 2017 |  | Improvement of Sports Center and Children's Playground, Boulevard |  | 1000000 |  |  |  | 0 |  | CONTRACT |  |  |  |  | 1000000
328 | 10710030-002-0018 | 2017 |  | Establishment of Early Child Development Center |  | 2300000 | 2018-03-31 | 2019-12-31 | 99.79% | 2107332.3 |  | Physically completed |  |  |  |  | 192667.7
226 | 10710030-030-0101 | 2017 |  | Construction of Multi-Purpose Pavement at Brgy. Ali-is | Ali-is | 580000 | 2017-12-16 | 2018-06-30 | 100% | 549090.35 |  | Physically completed |  |  |  |  | 30909.65
234 | *10710030-030-0093 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Guinhamogan, Brgy. Cansumalig | Cansumalig | 559523.81 | 2018-04-18 | 2018-07-31 | 100% | 519399.55 |  | Physically completed |  |  |  |  | 40124.26
235 | 10710030-030-0099 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Punong, Brgy. Cansumalig | Cansumalig | 559523.81 | 2018-03-16 | 2019-08-31 | 100% | 505035.42 |  | Physically completed |  |  |  |  | 54488.39
233 | 10710030-030-0090 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Guintalasan, Brgy. Cansumalig | Cansumalig | 559523.81 | 2018-09-15 | 2020-09-15 | 52% | 293908.16 |  | No existing road |  |  |  |  | 265615.65
237 | 264-009-1711-g0595 | 2017 |  | Improvement of Multi-Purpose Building at Brgy. Dawis | Dawis | 678571.43 |  |  |  | 0 |  | CONTRACT |  |  |  |  | 678571.43
240 | 10710030-030-0100 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Cogon, Brgy. Kalamtukan | Kalamtukan | 500000 | 2018-01-16 | 2018-06-30 | 100% | 471707.38 |  | Physically completed |  |  |  |  | 28292.62
243 | 10710030-030-0089 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Bocaw, Manduao | Manduao | 500000 | 2019-01-01 | 2019-07-31 | 100% | 463687.64 |  | Physically completed |  |  |  |  | 36312.36
258 | 264-009-1711-g0602 | 2017 |  | Improvement of Multi-Purpose Building, Brgy. Tinago | Tinago | 1128571.43 | 2018-03-16 | 2020-12-31 | 15% | 168535.72 |  | CONTRACT |  |  |  |  | 960035.71
261 | *10710030-030-0098 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Manghakayhakay, Brgy. Villasol | Villasol | 600000 | 2017-12-16 | 2018-03-31 | 100% | 560025.05 |  | Physically completed |  |  |  |  | 39974.95
383 |  | 2017 |  | Purchase of 50 KVA Transformer for BCTLDC |  | 500000 |  |  |  | 0 | [6 empty] | 500000
385 |  | 2017 |  | Construction of City Health Office Building |  | 1000000 | [5 empty] | Materials Completely Delivered: No site available |  |  |  |  | 1000000
331 | no obligation | 2017 |  | Construction of Workshop Area for Bayawan City Technology & Livelihood Development Center (BCTLDC) |  | 3000000 | 2019-05-17 | 2019-10-31 | 100% | 2988556.83 |  | Contract: Physically Completed |  |  |  |  | 11443.17
332 |  | 2017 |  | Purchase of Workshop Tools and Equipment for BCTLDC: | [12 empty] | 0
333 |  |  |  | Furniture & Fixtures | [12 empty] | 0
334 |  | 2017 |  | 3 units Exhaust Fan |  | 4500 |  |  | 100% | 4500 | [6 empty] | 0
335 |  | 2017 |  | 3 units Industrial Fan |  | 19656 |  |  | 100% | 19656 | [6 empty] | 0
336 |  | 2017 |  | 4 units White Board with Movable Stand |  | 11000 |  |  | 100% | 11000 | [6 empty] | 0
337 |  | 2017 |  | 3 units White Board (4x8x3/4) |  | 9900 |  |  | 100% | 9900 | [6 empty] | 0
338 |  |  |  | Machinery | [12 empty] | 0
339 |  | 2017 |  | 18 units Arc Welding Machine AC/DC & Acc |  | 698040 |  |  | 100% | 698040 | [6 empty] | 0
340 |  |  |  | Communication Equipment | [12 empty] | 0
341 |  | 2017 |  | 1 unit LCD projector |  | 26000 |  |  | 100% | 22995 | [6 empty] | 3005
342 |  |  |  | Disaster Response & Rescue Equipment | [12 empty] | 0
343 |  | 2017 |  | 4 units Fire Extinguishers |  | 12364 |  |  | 100% | 12364 | [6 empty] | 0
344 |  |  |  | Military, Police & Security Equipment | [12 empty] | 0
345 |  | 2017 |  | 1 Set Security Equipment Access Control (CCTV) |  | 29845 |  |  | 100% | 29845 | [6 empty] | 0
346 |  |  |  | Other Machinery & Equipment | [12 empty] | 0
347 |  | 2017 |  | 6 units Work Bench w/ Bench Vice on 4 Corners |  | 204000 |  |  | 100% | 204000 | [6 empty] | 0
348 |  | 2017 |  | 25 sets Combination Spanner (6mm to 24 mm) |  | 80000 |  |  | 100% | 80000 | [6 empty] | 0
349 |  | 2017 |  | 12 units Blow Torch |  | 18000 |  |  | 100% | 18000 | [6 empty] | 0
350 |  | 2017 |  | 12 units Clamp on Meter |  | 36000 |  |  | 100% | 36000 | [6 empty] | 0
351 |  | 2017 |  | 6 units Portable Electric Drill |  | 30000 |  |  | 100% | 30000 | [6 empty] | 0
352 |  | 2017 |  | 6 units Portable Planer |  | 51600 |  |  | 100% | 51600 | [6 empty] | 0
353 |  | 2017 |  | 6 units Portable Circular Saw |  | 47220 |  |  | 100% | 47220 | [6 empty] | 0
354 |  | 2017 |  | 25 pcs Welding Positioners |  | 96250 |  |  | 100% | 96250 | [6 empty] | 0
355 |  | 2017 |  | 6 units Electrode Oven |  | 24000 |  |  | 100% | 24000 | [6 empty] | 0
356 |  | 2017 |  | 25 units Portable Disc Grinder |  | 78750 |  |  | 100% | 78750 | [6 empty] | 0
357 |  | 2017 |  | 6 units Pipe Threader 1/2-2" |  | 343200 |  |  | 100% | 343200 | [6 empty] | 0
358 |  | 2017 |  | 6 units Pipe Bender |  | 26400 |  |  | 100% | 26400 | [6 empty] | 0
359 |  | 2017 |  | 6 units Heat Gun 1200 watts |  | 18900 |  |  | 100% | 18900 | [6 empty] | 0
360 |  | 2017 |  | 6 units Bolt Cutter |  | 7680 |  |  | 100% | 7680 | [6 empty] | 0
361 |  | 2017 |  | 12 pcs Box Wrench |  | 58800 |  |  | 100% | 58800 | [6 empty] | 0
362 |  | 2017 |  | 12 pcs Wire Splicer |  | 25320 |  |  | 100% | 25320 | [6 empty] | 0
363 |  | 2017 |  | 12 pcs Wire Stripper |  | 25320 |  |  | 100% | 25320 | [6 empty] | 0
364 |  | 2017 |  | 12 units Electric Drill |  | 58800 |  |  | 100% | 58800 | [6 empty] | 0
365 |  | 2017 |  | 12 units Portable Grinder |  | 52500 |  |  | 100% | 52500 | [6 empty] | 0
366 |  | 2017 |  | 6 units Pipe Cutter (1/2"-1") |  | 31590 |  |  | 100% | 31590 | [6 empty] | 0
367 |  | 2017 |  | 3 units Manual Pipe Threader (1/2", 3/4", 1") |  | 33705 |  |  | 100% | 33705 | [6 empty] | 0
368 |  | 2017 |  | 3 units Fusion Machine (20mm-32mm) |  | 34020 |  |  | 100% | 34020 | [6 empty] | 0
369 |  | 2017 |  | 4 units Electric Grinder (4") |  | 20520 |  |  | 100% | 20520 | [6 empty] | 0
370 |  | 2017 |  | 12 units Angle Grinder |  | 61560 |  |  | 100% | 61560 | [6 empty] | 0
371 |  | 2017 |  | 2 units Labelling Machine |  | 2200 |  |  | 100% | 2200 | [6 empty] | 0
372 |  | 2017 |  | 6 units Insulation Resistance Tester |  | 9900 |  |  | 100% | 9900 | [6 empty] | 0
373 |  | 2017 |  | 6 units Earth Resistance Tester |  | 13200 |  |  | 100% | 13200 | [6 empty] | 0
374 |  | 2017 |  | 4 units Pedestal/Bench Grinding Machine |  | 9400 |  |  | 100% | 9400 | [6 empty] | 0
375 |  | 2017 |  | 10 units Panel Board with 70 amp main & 4 |  | 34450 |  |  | 100% | 34450 | [6 empty] | 0
376 |  | 2017 |  | 25 pcs Electrician Pliers |  | 66250 |  |  | 100% | 66250 | [6 empty] | 0
377 |  | 2017 |  | Other Property, Plant & Equipment | [12 empty] | 0
378 |  | 2017 |  | 3 units Wheelbarrow |  | 6600 |  |  | 100% | 6000 | [6 empty] | 600
379 |  | 2017 |  | 6 sets Oxy-Acetylene/Oxy-LPG Cutting Outfit |  | 72000 |  |  | 100% | 72000 | [6 empty] | 0
380 |  | 2017 |  | 6 units Plastic Drum (200 liters) |  | 10560 |  |  | 100% | 10560 | [6 empty] | 0
388 |  | 2018 |  | Purchase of Lot for Multi-Purpose Hall at Sitio Cambulo. Banga | Banga | 600000 |  |  |  | 0 | [6 empty] | 600000
425 | 10710020-002-0057 | 2018 |  | Water System Development at Bugay Proper | Bugay | 500000 | 2019-04-01 | 2020-12-31 | 30% | 148710.4 |  | Implemented by: BAWAD |  |  |  |  | 351289.6
426 | 10710020-002-0056 | 2018 |  | Development of Water System at Brgy. Villareal | Villareal | 1000000 | 2019-08-12 | 2020-11-30 | 30% | 327600 |  | Implemented by: BAWAD |  |  |  |  | 672400
427 | 10710020-001-0113 | 2018 |  | Installation of Street Lighting from Purok 1 to Purok IV, Brgy. Tayawan | Tayawan | 500000 | 2018-06-21 | 2020-12-31 | 33% | 166705.62 | [6 empty] | 333294.38
428 | 10710020-009-0001 | 2018 |  | Improvement of Barangay Plaza and Children's Park, Tayawan | Tayawan | 500000 | 2018-06-21 | 2020-12-31 | 85% | 193225.96 |  | Temporarily Stopped: Due to COA remarks |  |  |  |  | 306774.04
429 | 0 | 2018 |  | Establishment of Early Child Care Dev't Centers: | Bayawan City | [11 empty] | 0
430 | 10710030-002-0021 | 2018 |  | a. Brgy. Villareal | Villareal | 5000000 | 2018-06-21 | 2020-03-31 | 95% | 4422941.73 | [6 empty] | 577058.27
431 | 10710030-002-0022 | 2018 |  | b. Brgy. Malabugas | Malabugas | 5000000 | 2018-06-21 | 2019-11-15 | 100% | 4874380.13 |  | Physically Completed: COC Issued on 11/20/20 |  |  |  |  | 125619.87
432 | 10710030-002-0023 | 2018 |  | Construction of Day Care Center at Sitio Mantapi, Nangka | Nangka | 578571.43 | 2018-12-01 | 2020-12-01 | 56% | 325812.46 |  | C/O GSO; Materials delivered- 100% |  |  |  |  | 252758.97
433 | 0 | 2018 |  | Improvement of Barangay Health Center & Lying-In Clinic, Brgy. Malabugas | Malabugas | 1000000 |  |  |  | 406333.27 | [6 empty] | 593666.73
434 | 10710030-003-0008 | 2018 |  | Construction of Health Center at Sitio Mantapi, Nangka | Nangka | 500000 | 2019-11-12 | 2020-11-12 | 22% | 110023.07 |  | C/O GSO; Materials delivered- 100% |  |  |  |  | 389976.93
443 | 10710030-030-0138 | 2018 |  | Construction of Bleachers at Barangay Evacuation Center, Ali-is | Ali-is | 678571.43 | 2018-01-04 | 2019-04-30 | 100% | 555739.56 | [6 empty] | 122831.87
444 | 10710030-030-0146 | 2018 |  | Improvement of Barangay Multi-Purpose Building, Banaybanay | Banaybanay | 1000000 |  |  |  | 0 |  | Contract |  |  |  |  | 1000000
445 | 10710030-030-0150 | 2018 |  | Improvement of Barangay Multi-Purpose Hall, Brgy. Boyco | Boyco | 1678571.43 |  |  |  | 0 |  | Contract |  |  |  |  | 1678571.43
446 | 10710030-030-0144 | 2018 |  | Construction of Barangay Multi-Purpose Building, Cansumalig | Cansumalig | 1300000 | 2019-07-16 | 2020-07-16 | 75% | 973876.6 |  | Materials delivered - 96%; re-ad - 4% |  |  |  |  | 326123.4
447 | 10710030-002-0024 | 2018 |  | Construction of Feeding Center at Damig Elementary School, Brgy. Kalamtukan | Kalamtukan | 778571.43 |  |  |  | 0 | [6 empty] | 778571.43
448 | 10710030-030-0147 | 2018 |  | Improvement of Barangay Multi-Purpose Building, Maninihon | Maninihon | 1000000 | 2019-11-01 | 2020-08-15 | 70% | 361599.05 | [6 empty] | 638400.95
449 | 10710030-030-0155 | 2018 |  | Construction of Multi-Purpose Pavement at Sitio Mantapi, Nangka | Mantapi, Nangka | 600000 | 2018-01-07 | 2018-12-31 | 100% | 546309.58 | [6 empty] | 53690.42
450 | 10710030-030-0148 | 2018 |  | Construction of Barangay Multi-Purpose Building, Narra | Narra | 1000000 |  |  |  | 0 | [6 empty] | 1000000
451 | 10710010-002-0005 | 2018 |  | Construction of Concrete Perimeter Fence of Covered Court and Evacuation Center, Brgy. Pagatban | Pagatban | 100000 | 2018-01-07 | 2018-08-31 | 100% | 86496.06 | [6 empty] | 13503.94
452 | 10710030-030-0145 | 2018 |  | Construction of Multi-Purpose Building, Brgy. San Isidro (Phase 2) | San Isidro | 1078571.43 | 2019-01-08 | 2020-04-15 | 75% | 871730.03 |  | Materials delivered - 100% |  |  |  |  | 206841.4
453 | 10710030-030-0137 | 2018 |  | Construction of Children and Women's Crisis Center, Brgy. Suba | Suba | 600000 |  |  |  | 0 | [6 empty] | 600000
454 | 10710030-030-0153 | 2018 |  | Improvement of Multi-Purpose Hall, Brgy. Suba | Suba | 578571.43 |  |  |  | 0 | [6 empty] | 578571.43
455 | 10710030-030-0149 | 2018 |  | Construction of Multi-Purpose Hall, Brgy. Tinago | Tinago | 2278571.43 | 2019-07-01 | 2020-12-31 | 30% | 2961352.63 | [6 empty] | -682781.2
457 | 10710030-030-0152 | 2018 |  | Improvement of Multi-Purpose Hall, Banga | Banga | 2078571.43 |  |  |  | 0 | [6 empty] | 2078571.43
460 | 10710030-030-0151 | 2018 |  | Improvement of Barangay Multi-Purpose Hall, Manduao | Manduao | 600000 | 2019-05-24 | 2020-03-15 | 100% | 440893.31 | [6 empty] | 159106.69
|  |  |  | Total Projects for Social Development - Contg App |  | 145289603.64 |  |  |  | 80797385.75 | [6 empty] | 64492217.89
0
0
|  |  | ECONOMIC DEVELOPMENT | [13 empty] | 0
64 | 10710020-006-0003 | 2011 |  | Const. of Hanging Bridge at Sitio Tiki, Kalumboyan (Phase 3) | Kalumboyan | 700000 | 2011-07-01 | 2020-12-31 | 37% | 546410.34 |  | Project heavily damaged by typhoon - discontinued |  |  |  |  | 153589.66
65 | 10710030-005-0002 | 2012 |  | Construction of Slaughterhouse | Suba | 10000000 | 2016-09-16 | 2018-03-31 | 100% | 7818835.46 |  | 100% Completed as per POW: Materials delivered- 75%; cancelled- 25%(rectangular tube, CHB, plywood, floor/wall tiles, blind rivets, drill bits, electrical materials & steel plate - for re-P.R. (100-17-01-023 - |  |  |  |  | 2181164.54
72 | 0 | 2013 |  | Fabrication of Distillation Chamber for Essential Oil Production | Banga | 150000 |  |  |  | 0 | [6 empty] | 150000
73 | *10710020-001-0011 | 2014 |  | Construction of Bayawan City Boulevard/Phase 2 | Bayawan City | 1000000 | 2014-08-16 | 2014-10-30 | 100% | 936750.81 | [6 empty] | 63249.19
74 | *10710030-030-0031 | 2014 |  | Const. of Motorpool Building, Phase 1, Cabcabon | Cabcabon, Banga | 8483700 | 2015-07-06 | 09/31/17 | 100% | 7893686.98 | [6 empty] | 590013.02
76 | per saaob | 2014 |  | Major Repair - Construction & Heavy Equipment | Motorpool Area | 10000000 | 2014-06-11 | 2020-12-31 | 22.43% | 2242763 |  | Temporary Standby due to some equipments already deteriorated |  |  |  |  | 7757237
78 | 10710020-001-0039 | 2014 |  | Road Surfacing from Sitio Binanigan to Sitio Guintana-an, Brgy. Tayawan, Phase 1 | Tayawan | 500000 | 2016-03-16 | 2020-04-01 | 90% | 173183.68 |  | Temporary stopped: Need to look other quarry source, road not yet passable, no Backhoe available |  |  |  |  | 326816.32
80 | *10710020-002-0025 | 2014 |  | Construction of Water System-Crusher Kalumboyan |  | 212800 | 2015-06-01 | 2016-06-30 | 100% | 182582.35 | [6 empty] | 30217.65
86 | no obligation | 2015 |  | Purchase of Various Heavy Equipment |  | 3476406.99 |  |  |  | 0 | [6 empty] | 3476406.99
88 | *10710020-001-0019 | 2015 |  | Reblocking of Concrete Pavement at Villareal-Cansumalig-San Isidro FMR, Phase 2 | Bayawan City | 500000 | 2015-06-01 | 2015-06-30 | 100% | 457677.34 | [6 empty] | 42322.66
89 | 10710020-001-0013 | 2015 |  | Construction of Gomez Street Extension | Bayawan City | 3000000 | 2016-03-16 | 2018-06-30 | 100% | 1148517.88 | [6 empty] | 1851482.12
90 | *10710020-001-0016 | 2015 |  | Concreting of Road Shoulder of National Highway Fronting BNHS, | Bayawan City | 3000000 | 2016-02-09 | 2017-01-15 | 100% | 2935348.39 | [6 empty] | 64651.61
91 | *10710020-001-0017 | 2015 |  | Construction of Access Road at Bayawan East, | Bayawan City | 2053659.56 | 2015-04-01 | 2016-03-15 | 100% | 1967337.73 | [6 empty] | 86321.83
92 | 10710020-001-0040 | 2015 |  | Road Surfacing of Sitio Hag-um and Sitio Mambunot, Brgy. Tayawan, Phase 1 | Tayawan, Bayawan City | 500000 | 2016-03-16 | 2020-02-15 | 99% | 444447.41 |  | On-going |  |  |  |  | 55552.59
93 | *10710020-001-0022 | 2015 |  | Rehabilitation of FMR at Sitio Tubod, Brgy. Tabuan | Tubod, Tabuan | 100000 | 2015-10-01 | 2016-03-15 | 100% | 56654.12 | [6 empty] | 43345.88
94 | *10710020-001-0021 | 2015 |  | Rehabilitation of Pulangyuta-Lapay FMR | Bayawan City | 2014400 | 2015-09-16 | 2017-03-31 | 100% | 2008455.26 | [6 empty] | 5944.74
122 | 10710030-030-0076 | 2016 |  | Improvement of Agricultural Dev. Ctr. (ADC), Cansumalig, Phase 2 | Cansumalig | 400000 | 2017-06-01 | 2018-06-30 | 100% | 348687.17 | [6 empty] | 51312.83
141 | *10710020-002-0043 | 2016 |  | Const. of Rain Collector at Brgy. San Isidro | San Isidro | 150000 | 2017-12-16 | 2018-05-31 | 100% | 137210.67 | [6 empty] | 12789.33
142 | 0 | 2016 |  | Fish Farm Development Program |  | 900000 |  |  |  | 0 | [6 empty] | 900000
144 | 10710030-003-0009 | 2016 |  | Renovation of the Integrated Business Center(IBC) Building | Villareal | 8000000 | 2017-04-27 | 2020-02-15 | 100% | 7449981.63 |  | Physically Completed: COC Issued on 01/27/20 |  |  |  |  | 550018.37
145 | 10710030-030-0086 | 2016 |  | Pilot Livestock Silage Stocking Project |  | 2000000 |  |  |  | 1650821.2 | [6 empty] | 349178.8
147 | *10710030-004-0005 | 2016 |  | Establishment of Bayawan Farmers' Market in Dumaguete |  | 5000000 | 2018-02-05 | 2018-10-31 | 100% | 4994489.13 | [6 empty] | 5510.87
149 | per saaob | 2016 |  | Purchase of Agricultural & Forestry Equipment and Implements |  | 8800000 | 2018-01-02 | 2018-12-31 | 100% | 8400000 | [6 empty] | 400000
151 | no obligation |  |  |  |  | 250000 |  |  |  | 0 | [6 empty] | 250000
153 | *10710020-001-0031 | 2016 |  | Improvement of Nangka-Narra FMR | Bayawan City | 5000000 | 2016-06-16 | 2017-08-31 | 100% | 4454951.93 | [6 empty] | 545048.07
154 | *10710020-001-0041 | 2016 |  | Improvement of Maninihon-Cansumalig-San Isidro FMR | Bayawan City | 5000000 | 2016-06-16 | 2017-09-15 | 100% | 4785135.91 | [6 empty] | 214864.09
155 | *10710020-001-0053 | 2016 |  | Reblocking of Concrete Pavement at Villareal-Cansumalig-San Isidro FMR, Phase 3 | Bayawan City | 500000 | 2017-03-01 | 2017-07-31 | 100% | 470136.11 | [6 empty] | 29863.89
156 | *10710020-001-0043 | 2016 |  | Reblocking of Concrete Pavement Nangka- Narra FMR | Bayawan City | 500000 | 2017-02-16 | 2017-06-30 | 100% | 472475.09 | [6 empty] | 27524.91
157 | *10710020-001-0062 | 2016 |  | Reblocking of Concrete Pavement with Slope Protection at Malabugas-San Roque Route | Bayawan City | 500000 | 2017-05-01 | 2017-10-31 | 100% | 463375.74 |  |  | 459598.82 | 3776.92 |  | 463375.74 | 36624.26
158 | *10710020-001-0052 | 2016 |  | Reblocking of Concrete Pavement with Slope Protection at Tabuan-Banay-banay Route | Bayawan City | 500000 | 2017-05-01 | 2017-10-31 | 100% | 463537.29 | [6 empty] | 36462.71
159 | *10710020-001-0049 | 2016 |  | Concreting of Road Approaching Upper Baican Box Culvert with Slope Protection | Bugay | 1000000 | 2016-10-16 | 2017-06-30 | 100% | 974648.99 | [6 empty] | 25351.01
160 | *10710020-001-0048 | 2016 |  | Concreting of Road Approaching Nayabaan Box Culvert with Slope Protection | Bugay | 1000000 | 2016-09-16 | 2017-07-15 | 100% | 908111.85 | [6 empty] | 91888.15
161 | *10710020-001-0063 | 2016 |  | Concreting of Road Approaching Cagayon Box Culvert with Slope Protection | Banaybanay | 1000000 | 2017-01-01 | 2017-10-31 | 100% | 922836.09 |  |  | 905886.26 | 16949.83 |  | 922836.09 | 77163.91
162 | *10710020-001-0061 | 2016 |  | Concreting of Road Approaching Cabigohan Box Culvert with Slope Protection | Dawis | 1000000 | 2017-05-01 | 2017-10-15 | 100% | 947426.51 |  |  | 930476.68 | 16949.83 |  | 947426.51 | 52573.49
163 | 10710020-030-0001 | 2016 |  | Installation of Guardrails at Kalumboyan Bridge Approaches | Kalumboyan | 2000000 | 2017-08-01 | 2018-06-30 | 100% | 1716619.15 |  |  | 1710926.68 | 5692.47 |  | 1716619.15 | 283380.85
164 | *10710020-006-0008 | 2016 |  | Const. Tiki Footbridge, Phase 2 Brgy. Kalumboyan | Kalumboyan | 700000 | 2017-04-16 | 2018-02-28 | 100% | 685551.67 | [6 empty] | 14448.33
165 | 10710020-001-0025 | 2016 |  | Const. of Urban Roads (Gomez to Kabankalan Road) | City Proper | 8000000 | 2017-06-01 | 2018-12-31 | 100% | 5854241.79 | [6 empty] | 2145758.21
166 | 10710020-001-0032 | 2016 |  | Rehab of FMR at So. Pag-awitan, Ali-is | Ali-is | 500000 | 2018-05-16 | 2018-12-31 | 100% | 296371.2 | [6 empty] | 203628.8
167 | 10710020-001-0036 | 2016 |  | Road Opening at Sitio Palasanon, Cansinacao, Guintalasan Mangharaw & Guinhamogan, Brgy Cansumalig | Cansumalig | 500000 | 2018-02-16 | 2020-06-30 | 50% | 114051.44 |  | Temporarily Stopped: Road no longer passable & no available heavy equipment |  |  |  |  | 385948.56
168 | 10710020-001-0033 | 2016 |  | Road Rehabilitation at so. Camague, Brgy Dawis | Villareal | 500000 | 11/31/2019 | 2020-07-31 | 15% | 82591.46 |  | Materials Completely Delivered; No available H.E. and Road not yet passable |  |  |  |  | 417408.54
169 | 10710020-001-0035 | 2016 |  | Road surfacing at Manduao-Bucao, Brgy Manduao | Manduao | 500000 | 2016-03-16 | 2020-12-31 | 5% | 167283.93 |  | Temporarily stopped: road not yet passable & no available heavy equipment |  |  |  |  | 332716.07
170 | *10710020-006-0009 | 2016 |  | Const. of Steel Bridge Connecting So. Malampa to So. Tab-ang, Brgy Pagatban | Pagatban | 500000 | 2017-06-16 | 2018-01-31 | 100% | 408032.04 |  |  | 360828.1 | 47203.94 |  | 408032.04 | 91967.96
171 | *10710020-001-0060 | 2016 |  | Const. or Road from Gov't. Ctr. To sitio Buli-buli/Phase 2 | Banga | 2000000 | 2017-01-01 | 11-31-17 | 100% | 1680955.01 |  |  | 1670978.21 | 9976.8 |  | 1680955.01 | 319044.99
172 | 10710020-001-0064 | 2016 |  | Improvement of Road Along Bayawan CIP Main Canal | Bayawan City | 190000 | 2019-08-16 | 2020-05-15 | 47% | 90000 | [6 empty] | 100000
173 | *10710020-006-0010 | 2016 |  | Const. of Footbridge at Sitio Lower Baican, Brgy Villasol | Baican, Villasol | 220000 | 2018-02-01 | 2018-06-30 | 100% | 221204.91 |  |  | 189061.91 | 32143 |  | 221204.91 | -1204.91
179 | *10710020-003-0004 | 2016 |  | Rehabilitation of Bayawan Communal Irrigation System | Pagatban | 500000 | 2016-08-16 | 2016-12-31 | 100% | 458455.32 | [6 empty] | 41544.68
180 | 10710020-003-0005 | 2016 |  | Const. of Small Scale Irrigation Project at Sitio Magsulay | Narra | 1000000 | 2016-08-16 | 2019-12-31 | 100% | 1031939.62 | [6 empty] | -31939.62
184 | *10710020-004-0011 | 2016 |  | Const. of Box Culvert in So. Candalaga, Brgy Nangka | Nangka | 500000 | 2017-03-16 | 2017-06-30 | 100% | 413628.17 |  |  | 381385.53 | 32242.64 |  | 413628.17 | 86371.83
185 | *10710020-002-0042 | 2016 |  | Construction of Spring Box at Upper Talao, San Isidro | San Isidro | 500000 | 2018-04-15 | 2019-03-31 | 100% | 261148.49 |  |  | 253922.18 | 7226.31 |  | 261148.49 | 238851.51
186 | *10710020-004-0016 | 2016 |  | Const. of 1 unit Single Box Culvert Phase 1 at So, Magsakang, brgy Tayawan | Tayawan | 500000 | 2018-01-16 | 2018-05-15 | 100% | 410379.87 | [6 empty] | 89620.13
211 | 10710030-030-0049 | 2017 |  | Construction of Pigpens |  | 400000 | 2019-12-01 | 2020-12-01 | 1% | 3301.01 | [6 empty] | 396698.99
212 | 0 | 2017 |  | Construction of 2 Units Small Scale Rubber Processing Plant with Shed |  | 300000 |  |  |  | 0 | [6 empty] | 300000
213 | budget data | 2017 |  | Purchase of Breeding Stocks | Bayawan City | 1944000 |  |  |  | 0 | [6 empty] | 1944000
214 | 0 | 2017 |  | Improvement of Brgy. Dawis Livestock Auction Market | Dawis | 150000 |  |  |  | 0 | [6 empty] | 150000
215 | *10710030-030-0091 | 2017 |  | Fabrication of Portable Batching Plant |  | 500000 | 2017-10-16 | 2018-05-31 | 100% | 325671.05 | [6 empty] | 174328.95
216 | *10710030-001-0004 | 2017 |  | Construction of CEO Multi-Purpose Building | Cabcabon | 2000000 | 2017-04-16 | 2019-04-30 | 100% | 1744342.36 | [6 empty] | 255657.64
217 | 10710030-030-0088 | 2017 |  | Construction of Motorpool Building at Cabcabon | Cabcabon | 8000000 | 2017-05-16 | 2019-12-15 | 99.5% | 6670246.05 | [6 empty] | 1329753.95
218 | no obligation | 2017 |  | Lot Acquisition |  | 500000 |  |  |  | 0 | [6 empty] | 500000
219 | 0 | 2017 |  | Establishment of Livestock Auction Market |  | 2000000 |  |  |  | 0 | [6 empty] | 2000000
220 | 0 | 2017 |  | Improvement of Public Market Water System | Bayawan City | 500000 |  |  |  | 0 | [6 empty] | 500000
221 | *10710020-001-0076 | 2017 |  | Construction of Slope Protection at Narra-Duyanduyan FMR, Sito Duyan-duyan, Brgy. Narra | Bayawan City | 1000000 | 2017-10-16 | 2018-05-31 | 100% | 895097.05 | [6 empty] | 104902.95
225 | no obligation | 2017 |  | Purchase of Various Agricultural Equipment | Bayawan City | 4000000 |  |  |  | 0 | [6 empty] | 4000000
291 | *10710020-001-0080 | 2017 |  | Slope Protection at Barangay Proper, San Isidro | San Isidro | 50000 | 2017-11-16 | 2018-01-31 | 100% | 48807.67 | [6 empty] | 1192.33
227 | 10710020-006-0012 | 2017 |  | Construction of Flat Slab Bridge at Brgy. Proper, Banaybanay | Banaybanay | 600000 | 2018-01-16 | 2018-09-30 | 100% | 583108.44 | [6 empty] | 16891.56
228 | 0 | 2017 |  | Improvement of FMR at Sitio Cangcawit, Banaybanay | Banaybanay | 1078571.43 |  |  | 72% | 171610.35 |  | On- Going |  |  |  |  | 906961.08
229 | 10710030-030-0189 | 2017 |  | Improvement of Covered Court & Evacuation Center, Brgy. Banga | Banga | 500000 | 2019-03-16 | 2019-10-30 | 100% | 358699.53 |  | Physically Completed: Materials delivered - 93%; cancelled - 7% |  |  |  |  | 141300.47
230 | *10710020-001-0079 | 2017 |  | Improvement of FMR at Sitio Cansig-id, Brgy. Banga | Banga | 500000 | 2017-12-01 | 2018-01-31 | 100% | 455034 | [6 empty] | 44966
231 | 0 | 2017 |  | Improvement of FMR from Brgy. Proper to Sitio Aya, Brgy. Bugay | Bugay | 839286.43 |  |  |  | 0 | [6 empty] | 839286.43
232 | 0 | 2017 |  | Improvement of FMR from Brgy Proper to Sitio Canlantang,Brgy. Bugay | Bugay | 839285 |  |  |  | 0 | [6 empty] | 839285
236 | 264-009-1711-g0597 | 2017 |  | Construction of Satellite Farmers' Market, Brgy. Dawis | Dawis | 1000000 |  |  |  | 0 | [6 empty] | 1000000
238 | 10710020-001-0115 | 2017 |  | Improvement of FMR at Brgy. Dawis | Dawis | 150000 | 2018-06-01 | 2019-02-22 | 100% | 146687.65 | [6 empty] | 3312.35
239 | 10710020-001-0081 | 2017 |  | Improvement of Road from Barangay Proper to Kalamtukan Elementary School, Brgy. Kalamtukan | Kalamtukan | 1178571.43 | 2017-10-16 | 2018-06-15 | 100% | 1083384.59 | [6 empty] | 95186.84
241 | 0 | 2017 |  | Improvement of FMR at Brgy. Proper, Manduao | Manduao | 500000 |  |  |  | 116567.5 |  | Pending: Road not yet passable |  |  |  |  | 383432.5
246 | *10710020-001-0114 | 2017 |  | Improvement of FMR at Brgy. Minaba | Minaba | 678571.43 | 2018-05-16 | 2019-01-31 | 100% | 532636.79 | [6 empty] | 145934.64
247 | 10710020-001-0075 | 2017 |  | Improvement of FMR at Sitio Kasla, Brgy. Nangka | Nangka | 1000000 | 2017-12-01 | 2018-07-31 | 100% | 910370.06 |  | Completed: COC Issued on 07/01/19 Materials Delivered - 96%; cancelled - 4% |  |  |  |  | 89629.94
249 | 10710020-001-0085 | 2017 |  | Improvement of FMR at Sitios Terong, Palongpong, Canggabi and Cadal-ugan, Brgy. Narra | Narra | 1000000 | 2018-05-16 | 2020-08-01 | 35% | 246842 |  | On- Going |  |  |  |  | 753158
250 | 10710020-001-0072 | 2017 |  | Road Opening at Brgy. Narra Proper | Narra | 678571.43 | 2018-06-16 | 2019-12-31 | 90% | 301799.59 |  | On- Going; Delivered - 100% |  |  |  |  | 376771.84
252 | 0 | 2017 |  | Construction of Barangay Public Market, Brgy. San Jose | San Jose | 1678571.43 |  |  |  | 0 | [6 empty] | 1678571.43
253 | 0 | 2017 |  | Construction of Cloning Chamber at San Roque BADC | San Roque | 50000 |  |  |  | 0 | [6 empty] | 50000
255 | 10710020-006-0013 | 2017 |  | Improvement of Flat Slab Bridge at Sitio Magsakang, Brgy Tayawan | Tayawan | 500000 | 2019-02-16 | 2019-10-31 | 100% | 359123.07 |  | Physically Completed: COC Issued 01/23/2020 |  |  |  |  | 140876.93
256 | 10710020-001-0074 | 2017 |  | Improvement of Binanigan-Guintanaan FMR, Tayawan | Tayawan | 678571.43 | 2019-10-15 | 2020-07-31 | 96% | 24776.18 |  | On- Going |  |  |  |  | 653795.25
257 | 10710020-001-0073 | 2017 |  | Improvement of Binanigan-Napo FMR, Brgy. Tayawan | Tayawan | 500000 | 2019-01-10 | 2020-03-16 | 95% | 363640.42 |  | On-Going: Delivered - 100% |  |  |  |  | 136359.58
260 | 10710020-006-0014 | 2017 |  | Construction of Flat Slab Bridge Connecting Barangay Proper to Purok Malinong, Brgy. Villasol | Villasol | 1078571.43 | 2018-02-15 | 2019-04-30 | 100% | 1023638.83 |  | Completed: COC Issued on 07/01/9; Materials Delivered - 100% |  |  |  |  | 54932.6
288 | 0 | 2017 |  | Improvement of FMR at Brgy. Banaybanay | Banaybanay | 100000 |  |  |  | 0 | [6 empty] | 100000
295 | 10710020-001-0078 | 2017 |  | Improvement of FMR at Sitio Napit-an, Brgy. Maninihon | Maninihon | 220000 | 2018-04-01 | 2018-07-31 | 100% | 189414.53 | [6 empty] | 30585.47
297 | 10710020-001-0082 | 2017 |  | Improvement of FMR at Sitio Ondol, Brgy. Nangka | Nangka | 100000 | 2018-04-01 | 2018-08-31 | 100% | 95011 | [6 empty] | 4989
299 | *10710020-001-0077 | 2017 |  | Road Improvement at Brgy. Ubos | Ubos | 170000 | 2018-01-01 | 2018-02-15 | 100% | 148954.81 | [6 empty] | 21045.19
300 | *10710020-030-0002 | 2017 |  | Construction of Pathway to Banay-Banay Proper | Banay-Banay | 100000 | 2017-10-16 | 2018-02-28 | 100% | 90879.07 | [6 empty] | 9120.93
302 | 10710020-001-0084 | 2017 |  | Road Opening from National Highway to Purok 1 Pasil, Brgy. Malabugas | Malabugas | 150000 | 2019-09-15 | 2020-09-16 | 50% | 70424.49 |  | No ROW |  |  |  |  | 79575.51
305 | 10710020-001-0083 | 2017 |  | Improvement of FMR at Sitio San Ramon, Brgy. Poblacion | Poblacion | 150000 | 2018-04-01 | 2018-08-31 | 100% | 143423.48 | [6 empty] | 6576.52
313 | 10710020-001-0070 | 2017 |  | Rehabilitation of Farm to Market Road from Sitio Bosque to Tavera, Barangay Nangka | Nangka | 1000000 | 2019-06-12 | 2020-06-10 | 80% | 447997.6 |  | Materials delivered- 100% (aggregate sub-base course) |  |  |  |  | 552002.4
316 | no obligation | 2017 |  | Purchase of Lot(Road Right of Way for Various Road Projects) |  | 2980124.07 |  |  |  | 0 | [6 empty] | 2980124.07
193 | 10710010-001-0003 | 2017 |  | Development of Danapa Eco Park | Nangka | 18000000 | 2017-12-06 | 2020-02-29 | 98% | 16778685.58 |  | Pending: Punch list not yet rectify & Subject For Termination |  |  |  |  | 1221314.42
194 | 10710020-030-0003 | 2017 |  | Development of Narra Water Park | Narra | 16000000 | 2017-09-12 | 2018-09-30 | 100% | 15993892.48 |  | Physically Completed: COC Issued 07/03/18 |  |  |  |  | 6107.52
315 | budget data | 2017 |  | Purchase of Livestock Breeding Stocks |  | 533460 | 2017-05-31 | 11/31/2019 | 100% | 515555.56 | [6 empty] | 17904.44
386 |  | 2018 |  | Loan Amortization |  | 9809031.89 |  |  |  | 0 | [6 empty] | 9809031.89
387 |  | 2018 |  | Lot Acquisition for Development Projects |  | 1754285.71 |  |  |  | 0 | [6 empty] | 1754285.71
389 | 10710020-001-0112 | 2018 |  | Widening of Malabugas-San Roque Road |  | 3500000 | 2019-01-09 | 2019-12-31 | 85% | 2178790.09 |  | Materials delivered - 97%; cancelled - 3% |  |  |  |  | 1321209.91
390 | 10710020-001-0095 | 2018 |  | Concreting of Road Approaching Lapay Box Culvert with Slope Protection, Dawis | Bayawan Creek, Dawis | 1000000 | 2018-04-01 | 2018-08-31 | 100% | 747445.26 |  | Completed: COC Issued on 07/01/9; Materials delivered- 97%; partial delivery - 3% | 747362.76 | 82.5 |  | 747445.26 | 252554.74
391 | 10710020-001-0094 | 2018 |  | Concreting of Road Approaching Candalaga Box Culvert with Slope Protection, Nangka | Nangka | 1000000 | 2018-04-01 | 2018-11-30 | 100% | 871727.74 |  | Completed: COC Issued on 07/01/9; Materials delivered- 97%; Partial delivery - 3% | 871645.24 | 82.5 |  | 871727.74 | 128272.26
392 | 10710020-001-0098 | 2018 |  | Concreting of Road Approaching Pusi-on Box Culvert with Slope Protection, Maninihon | Maninihon | 1000000 | 2018-04-01 | 2019-02-28 | 100% | 853186.46 |  | Completed: COC Issued on 07/01/9; Materials delivered- 97%; Partial delivery - 3% | 853103.96 | 82.5 |  | 853186.46 | 146813.54
393 | 10710020-001-0093 | 2018 |  | Concreting of Road Approaching Camandagan Box Culvert with Slope Protection, Maninihon | Maninihon | 1000000 | 2018-04-01 | 2018-09-30 | 100% | 788542.62 |  | Completed: COC Issued on 07/01/9; Materials delivered- 100% |  |  |  |  | 211457.38
394 | 10710020-001-0091 | 2018 |  | Concreting of Road Approaching Balao Box Culvert with Slope Protection, San Miguel | San Miguel | 1000000 | 2018-04-01 | 2018-10-30 | 100% | 829699.91 |  | Completed: COC Issued on 07/01/9; Materials delivered- 97%; Partial delivery - 3% | 829617.41 | 82.5 |  | 829699.91 | 170300.09
395 | 10710020-001-0096 | 2018 |  | Concreting of Road Approaching Magsakang Box Culvert with Slope Protection, Tayawan | Tayawan | 1000000 | 2018-04-01 | 2019-07-31 | 100% | 852527.64 |  | Physically Completed: Materials delivered- 97%; Partial delivery - 3% |  |  |  |  | 147472.36
396 | 10710020-006-0016 | 2018 |  | Completion of Magsakang Flat Slab Bridge, Tayawan | Tayawan | 1000000 | 2018-04-01 | 2019-04-30 | 100% | 954259.8 |  | Physically Completed: Materials delivered- 95%; for delivery- 5% |  |  |  |  | 45740.2
397 | 10710020-001-0097 | 2018 |  | Concreting of Road Approaching Pamuat Box Culvert with Slope Protection, San Isidro | San Isidro | 1000000 | 2018-04-01 | 2019-06-30 | 100% | 929512.72 |  | Physically Completed: Materials delivered - 100% |  |  |  |  | 70487.28
398 | 10710020-001-0092 | 2018 |  | Concreting of Road Approaching Binanigan Box Culvert with Slope Protection, Tayawan | Tayawan | 1000000 | 2018-04-01 | 2018-09-30 | 100% | 761723.42 |  | Completed: COC Issued on 07/01/9; Materials delivered- 100% |  |  |  |  | 238276.58
399 | *10710020-001-0086 | 2018 |  | Concreting of Road at Purok 7, Barangay Tinago | Tinago | 2000000 | 2018-02-16 | 2018-08-31 | 100% | 1717211.49 | [6 empty] | 282788.51
400 | 10710020-001-0088 | 2018 |  | Concreting of Dawis-Lapay FMR | Bayawan City | 5500000 | 2018-04-01 | 2019-07-31 | 100% | 4539005.09 |  | Physically Completed: Materials delivered- 96%; re-bid- 4% |  |  |  |  | 960994.91
401 | 10710020-001-0087 | 2018 |  | Concreting of Banga-San Roque-Minaba-San Miguel-Tayawan FMR | Bayawan City | 5872000 | 2018-04-01 | 2019-06-30 | 100% | 5221497.1 |  | Physically Completed: Materials delivered- 96%; Partial delivery- 2%; for delivery- 2% |  |  |  |  | 650502.9
402 | 10710020-001-0090 | 2018 |  | Concreting of Nangka-Narra FMR | Bayawan City | 5500000 | 2018-04-01 | 2019-05-31 | 100% | 4539901.35 |  | Completed: COC Issued on 07/01/9; Materials delivered- 96%; re-bid- 4% |  |  |  |  | 960098.65
403 | 10710020-001-0105 | 2018 |  | Concreting of Tabuan- Banaybanay-Lapay-Bugay-San Jose-Manduao FMR | Bayawan City | 28340000 | 2019-05-29 | 43716 | 100% | 28213392.75 | [6 empty] | 126607.25
404 | 10710020-001-0103 | 2018 |  | Concreting of Road from Sitio Balastro to Sitio Candulion to Pulangyuta, Barangay Kalamtukan | Kalamtukan | 10500000 | 2018-01-08 | 2019-08-31 | 99% | 7874648.88 |  | On-Going: Materials delivered- 96%; partial delivery- 2%; for delivery- 2% |  |  |  |  | 2625351.12
405 | 10710020-001-0104 | 2018 |  | Concreting of Road with Drainage Canal at Upper Napit-an, Maninihon | Maninihon | 300000 | 2018-04-01 | 2018-07-31 | 100% | 175615.88 | [6 empty] | 124384.12
406 | 10710020-001-0102 | 2018 |  | Concreting of Road from Highway Intersection to Minaba Elem. School, Brgy. Minaba | Bayawan City | 1000000 | 2018-04-01 | 2018-09-30 | 100% | 703131.2 |  | Completed: COC Issued on 07/01/9; Materials delivered- 100% |  |  |  |  | 296868.8
407 | 10710020-001-0099 | 2018 |  | Concreting of Road at Sitio Kasla, Brgy. Nangka | Nangka | 850000 | 2018-04-01 | 2018-09-30 | 100% | 653409.03 | [6 empty] | 196590.97
408 | 10710020-006-0020 | 2018 |  | Construction of Flat Slab Bridge at Sitio Terong, Narra | Narra | 600000 | 2018-04-01 | 2019-06-30 | 100% | 520886.82 |  | Physically Completed: Materials delivered- 100% |  |  |  |  | 79113.18
409 | 10710020-001-0107 | 2018 |  | Road Concreting from Proper Narra to Purok III, Brgy. Narra | Narra | 500000 | 2018-04-01 | 2018-10-16 | 100% | 394052.4 |  | Physically Completed: Materials delivered- 88%; Partial delivery - 4%; For delivery- 8% |  |  |  |  | 105947.6
410 | 10710020-001-0089 | 2018 |  | Concreting of FMR from National Highway to Sitio Lapacon, Brgy. Pagatban | Bayawan City | 500000 | 2018-04-01 | 2018-08-31 | 100% | 394562.39 |  | Physically Completed: Materials delivered- 87%; partial delivery - 5%; For delivery- 8% |  |  |  |  | 105437.61
411 | 10710020-001-0100 | 2018 |  | Concreting of Road at Sitio Upper Pamu-at, San Isidro | San Isidro | 500000 | 2018-04-01 | 2020-03-16 | 92.5% | 266044 |  | Temporarily Stopped: Road not yet passable |  |  |  |  | 233956
412 | 10710020-001-0101 | 2018 |  | Concreting of Road at Upper Talao, San Isidro | San Isidro | 600000 | 2018-10-01 | 2019-03-31 | 100% | 514849.54 |  | Completed: COC Issued on 07/01/19Consolidated Materials delivered- 94%; rebid- 3% [plywood]; cancelled-3% [sack cloth][sack cloth] |  |  |  |  | 85150.46
413 | 10710020-001-0108 | 2018 |  | Road Shouldering Along Zamora St., Brgy. Ubos | Ubos | 500000 | 2018-06-16 | 2018-11-30 | 100% | 428565.85 |  | Completed: COC Issued on 07/01/9; Materials delivered- 98%; partial delivery- 2% |  |  |  |  | 71434.15
414 | 10710020-001-0110 | 2018 |  | Road Surfacing from Barangay Proper to Sitio Gawgaw to Sitio Aya, Brgy. Bugay | Bugay | 839286.43 | 2019-03-01 | 2020-12-31 | 20% | 286294.33 |  | Temporarily Stopped: due to road not passable; Pending: Materials delivered- 97%; re-bid- 3%: No H.E Available |  |  |  |  | 552992.1
415 | 10710020-001-0111 | 2018 |  | Road Surfacing from Barangay Proper to Sitio Mambuy-og to Sitio Canlantang, Brgy. Bugay | Bugay | 839285 | 2019-01-04 | 2019-12-31 | 97.5% | 568855.08 |  | On-Going Materials delivered- 97%; re-bid- 3%: No H.E Available |  |  |  |  | 270429.92
416 | 10710020-001-0109 | 2018 |  | Road Surfacing at Barangay Cansumalig | Cansumalig | 1078571.43 |  |  |  | 468635.45 | [6 empty] | 609935.98
418 | 10710020-004-0017 | 2018 |  | Installation of Cylindrical Culvert with Riprap at Proper Narra | Narra | 578571.43 | 2018-06-16 | 2019-08-31 | 100% | 497818.65 | [6 empty] | 80752.78
420 | 0 | 2018 |  | Construction of Small Scale Irrigation Projects (SSIP): | Bayawan City | [11 empty] | 0
421 | 10710020-003-0007 | 2018 |  | a. Purok Mangga, Brgy. Manduao | Manduao | 800000 | 2018-06-01 | 2020-04-30 | 74% | 593670.45 |  | Materials delivered- 95%; re-ad - 5% C/O D.A |  |  |  |  | 206329.55
422 | 10710020-003-0008 | 2018 |  | b. Sitio Dita, Brgy. Tabuan | Tabuan | 800000 | 2018-06-01 | 2020-04-30 | 37% | 299129.89 |  | Materials delivered- 95%; re-ad - 5% C/O D.A |  |  |  |  | 500870.11
423 | 10710020-003-0009 | 2018 |  | c. Upper Canlinte, Brgy Ali-is | Ali-is | 800000 | 2018-06-01 | 2020-04-30 | 54% | 458771.33 |  | Materials delivered- 95%; re-ad - 5% C/O D.A |  |  |  |  | 341228.67
424 | 10710020-003-0010 | 2018 |  | Rehabilitation of Irrigation Canal at Brgy. Tabuan | Tabuan | 915000 | 2019-03-01 | 2020-03-10 | 95% | 773915.66 | [6 empty] | 141084.34
435 | 0 | 2018 |  | Construction of Barangay Public Market, Ali-is (Phase 1) | Bayawan City | 1000000 |  |  |  | 0 | [6 empty] | 1000000
436 | 10710030-005-0001 | 2018 |  | Completion of Minaba Mini Slaughterhouse Phase III | Minaba | 500000 | 2018-10-16 | 2019-07-31 | 100% | 419375.96 | [6 empty] | 80624.04
437 |  | 2018 |  | Construction of Rainwater Harvesting Systems for Nurseries: | [12 empty] | 0
438 | 10710020-002-0075 | 2018 |  | a. Brgy. San Miguel | San Miguel | 250000 | 2018-10-01 | 2018-11-30 | 100% | 193602.58 | [6 empty] | 56397.42
439 | 10710020-002-0076 | 2018 |  | b. Brgy. Tayawan | Tayawan | 250000 | 2018-10-16 | 2019-05-31 | 100% | 190464.82 | [6 empty] | 59535.18
440 | 10710020-002-0077 | 2018 |  | c. Brgy. Cansumalig | Cansumalig | 250000 | 2018-10-16 | 2019-06-30 | 100% | 189960.28 | [6 empty] | 60039.72
441 | 10710020-002-0078 | 2018 |  | d. Brgy. Manduao | Manduao | 250000 | 2018-10-16 | 2020-05-31 | 60% | 158504.74 | [6 empty] | 91495.26
442 | 10710020-002-0079 | 2018 |  | e. Brgy. Kalamtukan | Kalamtukan | 250000 | 2018-10-16 | 2020-05-31 | 73% | 183871.5 | [6 empty] | 66128.5
456 | 10710030-030-0159 | 2018 |  | Construction of Fish Processing Center @ Brgy. Suba | Suba | 2500000 | 2019-04-01 | 2019-12-31 | 80% | 1940773.71 | [6 empty] | 559226.29
458 | 10710030-030-0161 | 2018 |  | Major Repair of Narra Barangay Agricultural Development Center (BADC) | Narra | 520000 | 2018-09-30 | 2020-03-31 | 69% | 435302.67 |  | C/O GSO; Materials delivered- 100% |  |  |  |  | 84697.33
459 | 10710030-030-0160 | 2018 |  | Major Repair of Manduao Barangay Agricultural Development Center (BADC) | Manduao | 290000 | 2018-09-30 | 2020-03-31 | 78% | 227443.68 |  | C/O GSO; Materials delivered- 97%; for delivery- 3% |  |  |  |  | 62556.32
461 | no obligation | 2018 |  | Purchase of Boom Truck | Bayawan City | 1600000 |  |  |  | 0 | [6 empty] | 1600000
462 |  | 2018 |  | Purchase of 1 Unit Backhoe for Barangay Tayawan | Tayawan | 1678571.43 |  |  |  | 0 | [6 empty] | 1678571.43
464 | 10701010-001-0129 | 2018 |  | Purchase of Lot for Agricultural Research Center | Maninihon | 16000000 | 2018-12-01 | 2019-12-31 | 100% | 15710989 | [6 empty] | 289011
465 | 0 | 2018 |  | Establishment of Agricultural Research Center | Maninihon | 6895568.71 |  |  |  | 0 | [6 empty] | 6895568.71
466 | 10710020-001-0125 | 2018 |  | Improvement of Bugay-San Jose-Manduao FMR | Bayawan City | 3000000 | 2018-10-15 | 2019-01-06 | 100% | 2959185.3 | [6 empty] | 40814.7
467 | 10710020-001-0127 | 2018 |  | Concreting of Urban Roads with Drainage System (GomeZ St.) | Poblacion | 12885436.16 | 2019-01-16 | 2020-02-29 | 80% | 10465121.94 |  | Materials delivered- 57%; for delivery- 15%; cancelled- 1%; re-bid- 27%; Pending waiting for electrical materials delivery |  |  |  |  | 2420314.22
|  |  |  | Total Projects for Economic Development - Contg App |  | 323572730.25 |  |  |  | 234334429.37 | [6 empty] | 89238300.88
0
0
|  |  | ENVIRONMENTAL MANAGEMENT | [13 empty] | 0
61 |  | 2004 |  | Sanitary Landfill (Land Acquisition) 2004 | Maninihon | 1000000 |  |  |  | 8311 | [6 empty] | 991689
62 |  | 2001 |  | Sanitary Landfill - Dumpsite Acquisition | Maninihon | 500000 |  |  |  | 0 | [6 empty] | 500000
71 | *10710020-007-0002 | 2013 |  | Construction of Drainage Canal with Cover Along City Streets | Bayawan City | 606779.6 | 2014-06-02 | 2014-11-30 | 100% | 544360.59 | [6 empty] | 62419.01
182 | *10710020-007-0010 | 2016 |  | Construction of Drainage City Streets - Zamora, Teologio Sts, Subd Area | Zamora, Teologio & Subd Area | 3000000 | 2017-01-01 | 2017-09-15 | 100% | 2461029.39 | [6 empty] | 538970.61
183 | *10710020-005-0008 | 2016 |  | Rehabilitation of River Bank Protection at Sitio Ebuan | Nangka | 2000000 | 2017-03-16 | 2018-12-31 | 100% | 1451778.7 | [6 empty] | 548221.3
187 | *10710020-007-0011 | 2016 |  | Const. of Drainage Canal at along Burgos St. & AlongBollos St. Brgy Ubos | Ubos | 500000 | 2017-02-01 | 2017-06-30 | 100% | 442668.24 | [6 empty] | 57331.76
189 | *10710020-005-0007 | 2016 |  | Rehabilitation of Riverbank @ Brgy. Nangka | Nangka | 1000000 | 2018-05-16 | 2018-12-31 | 100% | 1013905.35 | [6 empty] | -13905.35
259 | 10710020-007-0017 | 2017 |  | Concreting of Drainage Canal Cover Along National Highway, Brgy. Villareal | Villareal | 678571.43 | 2017-11-16 | 2019-12-31 | 90% | 491510.65 |  | Pending: Due to transfer of site location, Barangay & SP resolution on process; Materials Delivered - 92%: cancelled- 8% |  |  |  |  | 187060.78
307 | *10710020-007-0016 | 2017 |  | Construction of Concrete Covered Canals, Brgy. Tinago | Tinago | 50000 | 2017-10-01 | 2017-10-31 | 100% | 46908.05 | [6 empty] | 3091.95
308 | *10710020-007-0019 | 2017 |  | Construction of Concrete Covered Canals, Brgy. Ubos | Ubos | 100000 | 2017-10-16 | 2017-11-30 | 100% | 84467.6 | [6 empty] | 15532.4
311 | *10710020-007-0015 | 2017 |  | Construction of Concrete Covered Canal, Brgy. Suba | Suba | 400000 | 2017-08-16 | 2018-01-31 | 100% | 360752.64 |  |  | 360021.69 | 730.95 |  | 360752.64 | 39247.36
223 | 10710020-007-0022 | 2017 |  | Construction of Drainage at Cabugcabugan Creek, Brgy. Poblacion, Phase 4 | Poblacion | 1356746.77 | 2017-11-16 | 2020-08-31 | 83% | 1197855.77 |  | Pending: Awaits Consultation( BMAKBI, Eldie Tinapao) |  |  |  |  | 158891
320 | *10710020-007-0020 | 2017 |  | Construction of Concrete Covered Canal at Zamora St. Brgy Suba |  | 173060.9 | 2017-08-16 | 2018-01-31 | 100% | 170642.5 | [6 empty] | 2418.4
321 | *10710020-007-0021 | 2017 |  | Construction of Concrete Canal Cover Along Rizat St. Brgy Tinago |  | 1000000 | 2017-11-16 | 2018-03-31 | 100% | 862393.35 |  |  | 678776.75 | 183616.6 |  | 862393.35 | 137606.65
224 | 10710020-005-0010 | 2017 |  | Construction of Riverbank Protection at Camayaan Creek,Brgy. Malabugas | Malabugas | 1000000 | 2018-01-16 | 2018-10-16 | 100% | 898258.82 |  | Physically Completed: Materials Delivered - 100% |  |  |  |  | 101741.18
222 | 10710020-008-0006 | 2017 |  | Flood Control Project at Brgy. Malabugas, Phase 2 | Malabugas | 1500000 | 2017-09-01 | 2018-06-30 | 100% | 1331896.08 |  | Completed: COC Issued on 07/01/19 Materials Delivered - 100% |  |  |  |  | 168103.92
417 | 10710020-007-0026 | 2018 |  | Construction of Drainage Canal from Upper Napit-an to Lower Napit-an, Brgy. Maninihon | Maninihon | 650000 | 2018-06-01 | 2018-09-30 | 100% | 546606.01 |  | Completed: COC Issued on 07/01/9; Materials delivered- 100% |  |  |  |  | 103393.99
419 | 10710020-007-0025 | 2018 |  | Covering of Drainage Canals along Gomez St., Brgy. Ubos | Ubos | 1078571.43 | 2018-08-12 | 2020-03-31 | 100% | 823890.36 |  | C/O GSO; Materials delivered- 100% |  |  |  |  | 254681.07
463 |  | 2018 |  | Purchase of Garbage Compactor Truck | Bayawan City | 1500000 |  |  |  | 0 | [6 empty] | 1500000
|  |  |  | Total Projects for Environmental Management - Contg App |  | 18093730.13 |  |  |  | 12737235.1
|  | TOTAL EDF CONTINUING APPROPRIATION |  |  |  | 486956064.02 |  |  |  | 327869050.22
|  | TOTAL EDF - CURRENT & CONTINUING APPROPRIATION |  |  |  | 709782492.37 |  |  |  | 411754287.81
|  |  |  | CORAZON P. LIRAZAN, CPA | [5 empty] | HON. PRYDE HENRY A. TEVES
|  |  |  | City Accountant | [5 empty] | City Mayor

## 20% Component
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION REPORT
As of March 31, 2020
CITY OF BAYAWAN
|  | Year | Program/Project |  | Location | Total Cost (per Budget Approp) | Target Start Date | Target Completion Date | Project Status |  | No. of Ext., if any | Remarks
1 | Project Code | [7 empty] | % of Completion | Total Cost Incurred (per Acctg)
3 |  | CURRENT APPROPRIATION
SOCIAL DEVELOPMENT
|  | 2020 |  | Water System Development for Sitio Balastro-Pulang Yuta-Tower, Brgy. Kalamtukan | Kalamtukan | 1678571.43 | [5 empty] | 3rd Quarter - For Implementation
|  | 2020 |  | Water System Development at Sitio Calumpang, Kalumboyan | Kalumboyan | 500000 | [5 empty] | -do-
7 |  | 2020 |  | Installation of Water Supply System at Sitios Bantolinao, Patag and Proper I, Brgy. Tabuan | Tabuan | 500000 | [5 empty] | -do-
23 | 0 | 2020 |  | Installation of Streetlighting System at Bulibuli, Banga | Banga | 500000 | [5 empty] | -do-
28 | 10710030-002-0028 | 2020 |  | Barangay Electrification Project, San Jose | San Jose | 858571.43 | [5 empty] | -do-
25 | 0 | 2020 |  | Construction of Bunker Silo | Bayawan City | 1000000 | [5 empty] | 4th Quarter - For Implementation
33 | 10710010-002-0011 | 2020 |  | Construction of Barangay Multi-Purpose Hall (Phase II), Cansumalig | Cansumalig | 1678571.43 | [5 empty] | 3rd Quarter - For Implementation
34 | 10710010-002-0013 | 2020 |  | Construction of Multi-Purpose Hall at Niludhan, Dawis | Dawis | 700000 | [5 empty] | -do-
35 | 10710010-002-0012 | 2020 |  | Construction of Barangay Nangka Multi-Purpose Hall (Phase II) | Bayawan City | 2478571.43 | [5 empty] | 4th Quarter - For Implementation
38 | 10710010-002-0015 | 2020 |  | Construction of Multi-Purpose Building (Phase II), Brgy. Poblacion | Poblacion | 1678571.43 | [5 empty] | 3rd Quarter - For Implementation
40 | 10710010-002-0010 | 2020 |  | Construction of Multi-Purpose Building at Sitio Bia-as, San Miguel | San Miguel | 700000 | [5 empty] | -do-
32 | 10710030-030-0198 | 2020 |  | Construction of Multi-Purpose Hall, Brgy. San Miguel (Phase V) | San Miguel | 500000 | [5 empty] | -do-
36 | 10710030-030-0211 | 2020 |  | Improvement of Barangay Multi-Purpose Building, Suba | Suba | 1678571.43 | [5 empty] | 4th Quarter - For Implementation
37 | 10710030-030-0209 | 2020 |  | Construction of Barangay Multi-Purpose Hall, Tinago (Phase 4) | Tinago | 3878571.43 | [5 empty] | -do-
39 | 10710030-001-0012 | 2020 |  | Construction of Multi-Purpose Hall, Brgy. Ubos (Phase 1) | Ubos | 2080000 | [5 empty] | -do-
|  |  |  | Total Projects for Social Development - Current Appropriation |  | 20410000.01 |  |  |  | 0
ECONOMIC DEVELOPMENT
|  | 2020 |  | Loan Amortization | Bayawan City | 66500000 |  |  |  | 43714550.5 |  | Per SAAOB as of March 31, 2020
|  | 2020 |  | Purchase of Lot for Relocation Site, Brgy. Manduao | Manduao | 1000000
|  | 2020 |  | Purchase of Lot for Barangay Multi-Purpose Hall Extension, Banga | Banga | 1678571.43 | [5 empty] | 3rd Quarter - For Implementation
|  | 2020 |  | Lot Acquisition for Informal Settlers | Bayawan City | 1574365.84
|  | 2020 |  | Completion of Urban Road (Gomez Ext.) | Bayawan City | 6000000 | 2020-01-15 |  | 85% | 0 |  | On going
|  | 2020 |  | Concreting of Inland Aquaculture Road Network | Bayawan City | 7500000 | [5 empty] | 4th Quarter - For Implementation
|  | 2020 |  | Improvement of Farm to Market Road at Sitio Dita, Ali-is | Ali-is | 1078571.43 | [5 empty] | 3rd Quarter - For Implementation
|  | 2020 |  | Concreting of Tower-Baong Road, Kalamtukan | Kalamtukan | 500000 | [5 empty] | 4th Quarter - For Implementation
|  | 2020 |  | Concreting of Manduao-Bucao Farm to Market Road | Manduao | 1000000 | [5 empty] | -do-
|  | 2020 |  | Road Concreting at Sitio Ondol, Nangka | Nangka | 500000 | [5 empty] | -do-
|  | 2020 |  | Road Concreting at Talaptap-Narra Proper | Narra | 500000 | [5 empty] | -do-
|  | 2020 |  | Road Concreting at Purok Pagkakaisa, Villareal | Villareal | 800000 | [5 empty] | -do-
|  | 2020 |  | Construction of Barangay Public Market, Banaybanay | Banaybanay | 500000 | [5 empty] | 3rd Quarter - For Implementation
|  | 2020 |  | Construction of Public Market Building, Maninihon | Maninihon | 2378571.43 | [5 empty] | 4th Quarter - For Implementation
|  | 2020 |  | Construction of Perimeter & Divisional Fences for Cattle at Sitio Cabcabon, Brgy. Banga | Banga | 800000 | [5 empty] | -do-
|  | 2020 |  | Construction of Cattle Shed at Sitio Cabcabon, Barangay Banga | Banga | 1200000 | [5 empty] | 4th Quarter - For Implementation
|  | 2020 |  | Construction & Heavy Equipment
|  | 2020 |  | 6 Units Dump Truck |  | 30000000
|  | 2020 |  | 1 Unit Motor Grader |  | 14000000
|  | 2020 |  | 1 Unit Backhoe (1 cu.m) |  | 10000000
|  | 2020 |  | 2 Units Payloader |  | 23000000
5 |  | 2020 |  | 2 Units Vibratory Roller |  | 12000000
8 |  | 2020 |  | 1 Unit Transit Mixer (5 cu.m) |  | 4000000
9 |  | 2020 |  | 1 Unit Water Tanker |  | 4000000
11 | 10710020-001-0135 | 2020 |  | 1 Unit Backhoe (0.5 cu.m) |  | 3000000
12 | 10710020-002-0088 | 2020 |  | 1 Unit Mini-Dumptruck - DA |  | 1500000
13 | 10710020-001-0136 | 2020 |  | Purchase of Mini-Dumptruck for Barangay Boyco |  | 1678571.43
14 | 10710020-001-0134 | 2020 |  | Purchase of Mini-Dumptruck for Barangay Minaba |  | 1200000
15 | 10710020-001-0137 | 2020 |  | Purchase of 1 Unit Dump Truck for Barangay Tabuan |  | 1000000
|  |  |  | Total Projects for Economic Development - Current Appropriation |  | 198888651.56 |  |  |  | 43714550.5
ENVIRONMENTAL MANAGEMENT
19 | 10710020-007-0030 | 2020 |  | Construction of Foot Bridge at Sitio Omod, Maninihon | Maninihon | 500000 | [5 empty] | 4th Quarter - For Implementation
|  | 2020 |  | Construction of Foot Bridge at Purok Ipil-ipil, San Roque | San Roque | 500000 | [5 empty] | 3rd Quarter - For Implementation
|  | 2020 |  | Construction of Concrete Canal Cover at Barangay Suba | Suba | 500000 | [5 empty] | 4th Quarter - For Implementation
|  | 2020 |  | Construction of Flat Slab Bridge at Magtangis Creek in Sitio Guintana-an, Brgy. Tayawan | Tayawan | 1678571.43 | [5 empty] | -do-
|  | 2020 |  | Construction of New Central Materials Recovery Facility | Bayawan City | 2500000 | 2020-02-01 |  | 15% | 0 |  | On going
|  | 2020 |  | Construction of Toxic and Hazardous Waste Vault Phase 2 | Bayawan City | 800000
|  | 2020 |  | Construction of 10 Units Residual Waste Containment for Upland Barangays | Bayawan City | 2000000 | [5 empty] | 3rd Quarter - For Implementation
|  |  |  | Total Projects for Environmental Management - Current Appropriation |  | 8478571.43 |  |  |  | 0
53 |  |  | TOTAL DF - CURRENT APPROPRIATION |  |  | 227777223 |  |  |  | 43714550.5
54
56 |  | CONTINUING APPROPRIATION
SOCIAL DEVELOPMENT
63 |  | 2011 |  | Renovation of BDH Canteen | BDH, Ubos | 114000 | 2011-06-01 | 2012-12-31 | 100% | 80418
66 | *10710030-030-0023 | 2012 |  | Improvement of Bayawan City Boulevard (Landscaping fronting GK Village) | Villareal | 535115.83 | 2013-08-01 | 2014-03-15 | 100% | 495907.52
67 | *10710030-030-0021 | 2013 |  | Construction of Sports Center and Children's Playground, Phase 3 | Suba | 3000000 | 2013-03-18 | 2015-05-30 | 100% | 2668470.08
68 | *10710030-030-0024 | 2013 |  | Construction of Covered Court at BCsTEC, Phase II | Cabcabon, Banga | 3008100 | 2013-10-01 | 2017-06-30 | 100% | 2783489.42
69 | 10710030-030-0025 | 2013 |  | Rehabilitation of GK Septic Tanks | Villareal | 3104400 | 2013-11-18 | 2020-12-31 | 2% | 77968.68 |  | Pending: sub-standard Fiber Glass septic Tank delivered by supplier not accepted by LGU
70 | *10710020-002-0036 | 2013 |  | Improvement of Water System for 21 Rural Barangays | Bayawan City | 568710 | 2016-07-01 | 2017-07-31 | 100% | 468013.78
82 | 10710030-030-0058 | 2015 |  | Construction of Evacuation Center, Brgy. San Miguel | San Miguel | 800000 | 2016-01-02 | 2019-10-31 | 100% | 753942.58
83 | *10710030-030-0059 | 2015 |  | Construction of Portable Toilet | Bayawan City | 770000 | 2016-01-15 | 2018-03-31 | 100% | 542396.04
84 | 10710010-002-0003 | 2015 |  | Const. of GK Village Perimeter Fence | Villareal | 2000000 | 2019-01-10 | 2020-12-31 | 95% | 1716184.88
96 | 10710020-002-0037 | 2015 |  | Water System Development @ Sitio Camague to Cabiguhan, Brgy Banaybanay | Banaybanay | 303389.8 | 2017-02-16 | 2020-12-31 | 50% | 206913.03 |  | Pending: Declared site has no water source
98 | 10710030-003-0001 | 2016 |  | Rehabilitation of Health Center & Const. of Lying-in Facility, Brgy. Poblacion, Phase 2 | Poblacion | 500000 | 2016-09-16 | 2017-06-30 | 100% | 320188.77
106 | 10710030-002-0010 | 2016 |  | Construction of Day Care Centers in Nangka and Napit-an/Rehabilitation of Day Care Centers in Minaba, Narra, Purok 4 Tayawan | Nangka, Napit-an, Minaba, Narra, Tayawan | 2000000 | 2017-01-06 | 2020-12-31 | 52% | 1593541.55 |  | Pending: 4 Units Completed, 1 unit not yet started due to no lot available
107 | *10710030-030-0079 | 2016 |  | Improvement of CICL Center Faciltities | Banga | 975000 | 2017-11-16 | 2019-03-31 | 100% | 810122.28
108 | *10710030-030-0081 | 2016 |  | Completion of Paglaum Center at Cabcabon | Cabcabon | 500000 | 2016-10-16 | 2018-05-31 | 100% | 374922.29
109 | *10710030-030-0069 | 2016 |  | Completion of Women's Multi-purpose Center | Boyco | 1000000 | 2016-12-01 | 2018-11-30 | 100% | 832656.5
110 | 10710030-030-0078 | 2016 |  | Construction of Women's Detention Cell | Banga | 400000 | 2019-07-29 | 2019-10-30 | 53% | 223432.29 |  | Cancelled as per instruction from DSWD
111 | 10710030-030-0067 | 2016 |  | Construction of Women's Facilities in Evacuation Center | Var. Brgys | 200000 | 2019-07-16 | 2020-03-31 | 98% | 168303.43 |  | Pending: Material estimates is inadequate
112 | *10710030-002-0009 | 2016 |  | Construction of Day Care Center at Brgy. Proper, Brgy,. San Miguel | San Miguel | 500000 | 2016-08-16 | 2017-05-31 | 100% | 447026.94
113 | 10710030-030-0073 | 2016 |  | Const. of Bleachers & CRs @ Existing Gyms for evacuation (Tinago, Boyco, Suba,Poblacion, Banga, Malabugas, Villareal, BNHS) | Various Brgys | 6000000 | 2019-07-30 | 2019-07-31 | 100% | 5105050.96
114 |  |  |  | a. Tinago
115 |  |  |  | b. Boyco
116 |  |  |  | c. Suba
117 |  |  |  | d. Poblacion
118 |  |  |  | e. Banga
119 |  |  |  | f. Malabugas
120 |  |  |  | g.Villareal
121 |  |  |  | h. BNHS
123 | *10710030-030-0074 | 2016 |  | Const. of Comfort Rooms in 13 Evacuation Ctrs. | Var Brgys | 1054174.83 | 2019-04-30 | 2018-02-28 | 100% | 1056488.39 |  | Excess cost due to of inventory averaging of eNGAS
124 |  |  |  | a. Banga Central School
125 |  |  |  | b. BCSTEC Elementary & Highschool
126 |  |  |  | c. Malabugas Highschool
127 |  |  |  | d. Nangka Elementary School
128 |  |  |  | e. Guisocon Elementary School
129 |  |  |  | f. Atilano Cabangal Memorial Highschool
130 |  |  |  | g. Tavera Elementary School
131 |  |  |  | h. Dean Felix Gaudiel Memorial Elementary School
132 |  |  |  | i. H. Bido Jordan Elementary School
133 |  |  |  | j. Bayawan National Highschool
134 |  |  |  | k. Maninihon Elementary & Highschool
135 |  |  |  | l. H. Bido Jordan Highschool School
136 |  |  |  | m. SLGTMES
137 | *10710030-030-0072 | 2016 |  | Improvement of Covered Court/Evacuation Ctr., Bry. Banga | Banga | 500000 | 2019-03-16 | 2020-03-31 | 100% | 435324.84
138 | 10710030-030-0071 | 2016 |  | Const. of Evacuation Ctr., Brgy. San Roque | San Roque | 500000 | 2017-06-16 | 2019-06-30 | 100% | 361521.48
139 | *10710030-030-0070 | 2016 |  | Const. of Covered Court/Evacuation Ctr., Bry. Suba | Suba | 500000 | 2016-12-16 | 2017-05-31 | 100% | 454964.53
140 | *10710030-030-0082 | 2016 |  | Const. of Multi-Purpose Bldg. for Evacuation Ctr., Brgy Villareal | Villareal | 500000 | 2019-01-05 | 2018-11-30 | 100% | 436829.46
143 | *10710030-030-0084 | 2016 |  | Establishment of Youth Development Center |  | 5000000 | 2017-06-15 | 2018-09-01 | 100% | 4000896.6
175 | 10710020-002-0041 | 2016 |  | Rehabilitation of San Isidro Water Supply System | San Isidro | 350000 | 2019-05-15 | 2020-06-30 | 54% | 189138.38 |  | On going
176 | *10710030-030-0085 | 2016 |  | Const. of Water Tank & Pipeline at Tabuan Brgy Proper | Tabuan | 500000 | 2017-05-01 | 2018-05-31 | 99.5% | 424113.31
177 | 10710020-002-0039 | 2016 |  | Construction of Tayawan Water System | Tayawan | 300000 | 2017-01-06 | 2020-02-29 | 95% | 267009.23 |  | Pending: Remaing work is installation of RCPC at the water source
100 | *10710030-006-0010 | 2016 |  | Installation of Electrical System (Sitio Napit-an, Brgy Maninihon & Zamora Streets, Brgy. Suba) - | Suba | 1500000 | 2016-11-15 | 2018-08-31 | 100% | 1439250.62
101 | *264-005-1606-G0056 | 2016 |  | Purchase of Transforments & Primary Metering @ New Gov't. Center | Banga | 2545000 | 2016-11-24 | 2016-11-29 | 100% | 2540000
102 | *10710030-006-0009 | 2016 |  | Installation of Secondary Line Feeder @ New Gov't. Center | Banga | 800000 | 2016-02-13 | 2018-07-15 | 100% | 669519.56
103 | 10710020-001-0044 | 2016 |  | Establishment of Street Lighting Facilities - 2016 | Var. Brgys. | 400000 | 2019-03-15 | 2020-04-15 | 100% | 314630
104 | *10710020-001-0065 | 2016 |  | Installation of Street Lightings at Brgy Proper, Villasol | Villasol | 140000 | 2017-10-02 | 2017-10-30 | 100% | 133422.04
190 |  | 2017 |  | Establishment of Montessori-Type Early Child Care Development Centers | Various Brgys
191 | 10710030-002-0011 | 2017 |  | a. Establishment of Montessori-Type Early Child Care Development Centers Phase 2 | Boyco | 2289000 | 2017-12-16 | 2020-02-10 | 99% | 1310863.71 |  | On going
192 | 10710030-002-0014 | 2017 |  | b. Establishment of Montessori-Type Early Child Care Development Centers | Poblacion | 1211000 | 2018-01-01 | 2018-11-30 | 100% | 742624.7
195 | 10710020-009-0003 | 2017 |  | Development of Tabuan People's Park | Tabuan | 2000000 | 2018-12-31 | 2020-04-20 | 100% | 1991861.08
196 | *10710030-030-0128/0129/0130 | 2017 |  | Construction of Coastal Park Comfort Rooms | Coastal Road | 4500000 | 2018-02-15 | 2018-05-27 | 100% | 4497336
198 | 10710030-003-0016 | 2017 |  | Improvement of Barangay Health Center Lying-In Clinic, Brgy. Malabugas | Malabugas | 678571.43 | 2019-01-10 | 2020-12-31 | 92% | 406333.27 |  | On going
199 | 264-004-1711-G0033 | 2017 |  | Improvement of Barangay Health Center & Lying-in Clinic, Brgy. Manduao | Manduao | 100000 |  |  |  | 0
200 | 10710030-030-0132 | 2017 |  | Construction of Covered Court and Evacuation Center, Brgy. Pagatban | Pagatban | 1728571.43 |  |  |  | 0
201 | 10710030-030-0135 | 2017 |  | Improvement of Evacuation Center and Multi-Purpose Building, Brgy. Poblacion | Poblacion | 878571.43 | 2020-03-15 |  | 30% | 0 |  | On going
202 | 10710030-002-0019 | 2017 |  | Construction of New Day Care Center at Brgy. Poblacion | Poblacion | 800000 |  |  |  | 0
203 | 10710030-003-0015 | 2017 |  | Construction of Lying-In Clinic, Brgy. San Isidro | San Isidro | 1178571.43 | 2019-02-24 | 2019-12-15 | 99.5% | 1177768.28
204 | 10710030-003-0006 | 2017 |  | Improvemen of Health Center and Lying-in Clinic, Brgy.San Roque | San Roque | 1678571.43 |  |  |  | 0
205 | 0 | 2017 |  | Improvement of Barangay Health Center, Brgy. Tinago | Tinago | 600000 |  |  |  | 0
206 | 10710030-030-0131 | 2017 |  | Construction of Children's Playground with Facilities, Brgy. Villareal | Villareal | 500000 |  |  |  | 0
207 | 0 | 2017 |  | Construction of Multi-Purpose Center for Senior Citizens, Brgy. Villasol | Bayawan City | 50000 |  |  |  | 0
208 | 10710030-003-0005 | 2017 |  | Improvement of Barangay Health Center, Brgy. San Jose | San Jose | 60000 |  |  |  | 0
209 | 10710030-003-0007 | 2017 |  | Renovation of Barangay Health Center at Brgy. Tayawan | Tayawan | 150000 |  |  |  | 0
210 | 10710030-002-0020 | 2017 |  | Renovation of Day Care Center, Brgy. Tayawan | Tayawan | 100000 |  |  |  | 0
244 | 10710020-002-0052 | 2017 |  | Water System Development Project at Sitio Upper Camandagan, Brgy. Maninihon | Maninihon | 1000000 | 2019-05-01 | 2020-10-31 | 65% | 647344.67 |  | On going
242 | 10710020-002-0047 | 2017 |  | Construction of Water System at Proper Manduao | Manduao | 678571.43 | 2019-08-03 | 2019-12-31 | 99.8% | 485410.54
245 | 264-009-1712-g0606 | 2017 |  | Improvement of Multi-Purpose Gymnasium and Evacuation Center, Brgy. Maninihon | Maninihon | 678571.43 | 2019-01-25 | 2020-02-15 | 100% | 588793.99
248 | 0 | 2017 |  | Establishment of Barangay Water Refilling Station, Brgy. Nangka | Nangka | 678571.43 |  |  |  | 0
254 | 10710030-030-0134 | 2017 |  | Improvement of Covered Court for Evacuation Center, Brgy Suba | Suba | 1678571.43 |  |  |  | 0
262 | 10710020-002-0050 | 2017 |  | Improvement/Rehabilitation of Water Systems for Various Barangays | Various Brgys | 934500 | 2019-01-31 | 2020-05-31 | 100% | 575402.78
263 | 10710030-030-0195 | 2017 |  | Installation of Water Refilling Stations at Various Barangays | Various Brgys | 2200000 | 2019-01-21 | 6/31/2020 | 48% | 1054599.9 |  | Pending: Building is not yet ready
264 | 10710030-030-0094 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Bolo, Brgy. Villasol | Villasol | 600000 | 2018-02-16 | 2018-06-30 | 100% | 563174.77
265 | 264-009-1712-g0605 | 2017 |  | Construction of Multi-Purpose Building in Barangay Tayawan | Tayawan | 900000 |  |  |  | 0
266 | 0 | 2017 |  | Construction of Multi-Purpose Building in Barangay San Jose | San Jose | 900000 |  |  |  | 0
268 | *10710020-007-0018 | 2017 |  | Construction of Drainage Canal at Cansumalig High School | Cansumalig | 150000 | 2017-12-16 | 2018-03-30 | 100% | 126833.17
269 | 10710010-002-0004 | 2017 |  | Construction of Perimeter Fence of Multi-Purpose Building, Brgy. San Miguel | San Miguel | 100000 |  |  |  | 0
270 | 10710020-002-0086 | 2017 |  | Improvement of Water Systems of Guintanaan Tayawan | Tayawan | 100000 | 2018-06-15 | 2020-12-31 | 3% | 3058 |  | On going
271 | 10710020-002-0046 | 2017 |  | Improvement of Water Systems at Manduao | Manduao | 110000 | 2019-07-20 | 2020-12-31 | 14% | 16811.66 |  | On going
272 | 0 | 2017 |  | Installation of Solar-Driven Water System for Catumbalan, Minaba | Minaba | 100000 |  |  |  | 0 |  | Pending: PR was cancelled
273 | 10710030-006-0015 | 2017 |  | Installation of Solar-Driven Water System for Oban-Oban, Brgy. Kalumboyan | Kalumboyan | 50000 | 2019-08-15 | 2020-04-05 | 27% | 13835.24 |  | On going
274 | 0 | 2017 |  | Installation of Solar-Driven Water Systems for Napo, Brgy. Tayawan | Tayawan | 50000 |  |  |  | 0
275 | 0 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Upper Manlubid, Ali-is | Ali-is | 50000 |  |  |  | 0
276 | *10710030-030-0095 | 2017 |  | Construction of Multi-Purpose Pavement at Inner Canabuan, Minaba | Minaba | 300000 | 2018-02-16 | 2018-06-30 | 100% | 286328.7
277 | 269-001-1712-g0052 | 2017 |  | Improvement of Water System at Sitio Pag-awitan, Brgy. Ali-is | Ali-is | 50000 | 2018-11-16 | 2020-04-30 | 70% | 35325 |  | On going
278 | 10710020-002-0089 | 2017 |  | Rehabilitation and Improvement of Water System at Brgy. Banaybanay | Banaybanay | 220000 | 2019-03-26 | 2020-06-30 | 61% | 135396.8 |  | On going
279 | 10710030-004-0004 | 2017 |  | Improvement of Barangay Public Market, Brgy. Malabugas | Malabugas | 50000 |  |  |  | 0
280 | 10710030-006-0016 | 2017 |  | Installation of Electrical System in Sitio Buli-buli, Brgy. Banga | Banga | 60000 | 2019-01-02 | 2019-02-28 | 100% | 43514.9
281 | 0 | 2017 |  | Installation of Electrical System in Brgy. Kalamtukan | Kalamtukan | 60000 | 2019-06-16 |  |  | 0
282 | 10710030-006-0014 | 2017 |  | Installation of Electrical System in Brgy. Kalumboyan | Kalumboyan | 70000 | 2019-06-16 | 2019-07-31 | 100% | 54252.49
283 | 269-001-1801-g0057 | 2017 |  | Improvement of Water System, Brgy. San Roque | San Roque | 70000 | 2019-10-25 | 2020-05-01 | 67% | 64349.22 |  | On going
284 | *10710020-002-0054 | 2017 |  | Improvement of Water System, Brgy. Ubos | Ubos | 145000 | 2018-01-06 | 2018-06-15 | 100% | 136216.2
285 | 0 | 2017 |  | Improvement of Water System at Brgy. Villasol | Villasol | 70000 | 2019-08-31 | 2020-02-29 | 89% | 62346 |  | On going
286 | 10710030-030-0096 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Ponong, Brgy. Villasol | Villasol | 100000 | 2019-07-31 | 2020-05-31 | 62% | 73715.89 |  | Pending: Road not yet passable
287 | *10710030-006-0012 | 2017 |  | Installation of Electrical System at Sitio Malampa, Brgy. Pagatban | Pagatban | 50000 | 2018-01-06 | 2018-06-30 | 100% | 44857.31
289 | *10710030-006-0013 | 2017 |  | Installation of Electrical System in Brgy. Malabugas | Malabugas | 50000 | 2018-03-16 | 2018-04-30 | 100% | 46024.73
290 | 10710020-002-0051 | 2017 |  | Improvement of Canabuan Water System, Brgy. Minaba | Minaba | 200000 | 6/31/2018 | 2020-12-31 | 30% | 62827.91 |  | On going
292 | 264-009-1711-g0596 | 2017 |  | Improvement of Barangay Multi-Purpose Hall, Brgy. Ali-is | Ali-is | 200000 |  |  |  | 0
293 | 10710030-030-0097 | 2017 |  | Construction of Multi-Purpose Pavement at Purok 2, Brgy. Kalamtukan | Kalamtukan | 250000 | 2018-01-16 | 2018-06-30 | 100% | 224233.82
294 | *10710020-001-0071 | 2017 |  | Installation of Street Lights at Purok 4, Cansilong, Brgy. Malabugas | Malabugas | 100000 | 2018-03-16 | 2018-05-31 | 100% | 90521.66
296 | 0 | 2017 |  | Improvement of Water System, Brgy. Minaba | Minaba | 110000 | 2018-02-01 | 2020-02-20 | 84% | 93457 |  | On going
298 | 0 | 2017 |  | Installation of Electrical System for Purok Ipil-Ipil, Brgy. San Roque | San Roque | 200000 |  |  |  | 0
267 | *10710030-006-0018 | 2017 |  | Electrification Project for Various Barangays | Various Brgys | 10000 | 2018-01-06 | 2018-06-15 | 100% | 9060.49
303 | 10710020-002-0048 | 2017 |  | Installation of Deep Well at Atilano Cabangal High School, Brgy. Nangka | Nangka | 250000 | 2018-11-15 | 2020-12-31 | 4% | 10606.87 |  | Pending: re-PR magsaysay type deepwell not available anymore in the market
304 | 10710020-002-0081 | 2017 |  | Installation of Water System at Brgy. Pagatban | Pagatban | 50000 | 2018-03-16 | 2019-06-30 | 100% | 41977.04
251 | *10710020-002-0053 | 2017 |  | Installation of Water System at Brgy. Poblacion | Poblacion | 70000 | 2018-03-01 | 2018-03-15 | 100% | 28933.33
306 | *10710020-002-0045 | 2017 |  | Improvement of Water System at Purok Dol-Dol, Brgy. San Roque | San Roque | 100000 | 2017-11-16 | 2018-01-31 | 100% | 69781.89
309 | 264-009-1712-g0607 | 2017 |  | Improvement of Multi-Purpose Gym & Evacuation Center, Brgy. San Isidro | San Isidro | 495000 |  |  |  | 0
310 | *10710030-030-0092 | 2017 |  | Construction of Multi-Purpose Pavement, Brgy. Dawis | Dawis | 340000 | 2017-11-01 | 2018-02-28 | 100% | 327529.86
312 | 264-009-1712-g0604 | 2017 |  | Construction of Multi-Purpose Building at Relocation Site, Brgy. San Miguel | San Miguel | 500000 |  |  |  | 0
314 | 10710030-030-0193 | 2017 |  | Construction of CICL at BADC Magsulay, Barangay Narra | Narra | 1000000 | 2018-10-09 | 2020-05-31 | 60% | 0 |  | Contract: Temporary suspended need supplemental budget
317 | 0 | 2017 |  | Const. of Livelihood Center for Women at Brgy Villasol Proper |  | 100000 |  |  |  | 0
318 | 10710030-030-0104 | 2017 |  | Construction of Multi-purpose Pavement at Sitio Kaayahan (Phase 1) |  | 100000 | 2017-07-31 | 2020-03-31 | 100% | 79896.46
319 | *10710030-030-0103 | 2017 |  | Completion of Multi-purpose Pavement at Sitio Tangistangisan |  | 330000 | 2018-01-02 | 2018-06-30 | 100% | 306358.29
323 | 10710020-002-0082 | 2017 |  | Development of Water System at Sitio Tavera, Nangka |  | 5700000 | 2019-03-01 | 2020-03-01 | 83% | 2785304.59 |  | On going
324 | *10710020-002-0087 | 2017 |  | Improvement of Cabatangan-Tavera Water System |  | 154784.58 | 2019-01-16 | 2019-03-31 | 100% | 133057.22
326 | 0 | 2017 |  | Improvement of Sports Center and Children's Playground, Boulevard |  | 1000000 |  |  |  | 0
328 | 10710030-002-0018 | 2017 |  | Establishment of Early Child Development Center |  | 2300000 | 2018-03-31 | 2019-12-31 | 99.79% | 2107332.3
226 | 10710030-030-0101 | 2017 |  | Construction of Multi-Purpose Pavement at Brgy. Ali-is | Ali-is | 580000 | 2017-12-16 | 2018-06-30 | 100% | 549090.35
234 | *10710030-030-0093 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Guinhamogan, Brgy. Cansumalig | Cansumalig | 559523.81 | 2018-04-18 | 2018-07-31 | 100% | 519399.55
235 | 10710030-030-0099 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Punong, Brgy. Cansumalig | Cansumalig | 559523.81 | 2018-03-16 | 2019-08-31 | 100% | 505035.42
233 | 10710030-030-0090 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Guintalasan, Brgy. Cansumalig | Cansumalig | 559523.81 | 2018-09-15 | 2020-09-15 | 52% | 293908.16 |  | Pending : No Road of Way
237 | 264-009-1711-g0595 | 2017 |  | Improvement of Multi-Purpose Building at Brgy. Dawis | Dawis | 678571.43 |  |  |  | 0
240 | 10710030-030-0100 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Cogon, Brgy. Kalamtukan | Kalamtukan | 500000 | 2018-01-16 | 2018-06-30 | 100% | 471707.38
243 | 10710030-030-0089 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Bocaw, Manduao | Manduao | 500000 | 2019-01-01 | 2019-07-31 | 100% | 463687.64
258 | 264-009-1711-g0602 | 2017 |  | Improvement of Multi-Purpose Building, Brgy. Tinago | Tinago | 1128571.43 | 2018-03-16 | 2020-12-31 | 15% | 168535.72
261 | *10710030-030-0098 | 2017 |  | Construction of Multi-Purpose Pavement at Sitio Manghakayhakay, Brgy. Villasol | Villasol | 600000 | 2017-12-16 | 2018-03-31 | 100% | 560025.05
383 |  | 2017 |  | Purchase of 50 KVA Transformer for BCTLDC |  | 500000 |  |  |  | 0
385 |  | 2017 |  | Construction of City Health Office Building |  | 1000000 |  |  |  | 0 |  | Pending: No site available
331 | no obligation | 2017 |  | Construction of Workshop Area for Bayawan City Technology & Livelihood Development Center (BCTLDC) |  | 3000000 | 2019-05-17 | 2019-10-31 | 100% | 2988556.83
332 |  | 2017 |  | Purchase of Workshop Tools and Equipment for BCTLDC:
333 |  |  |  | Furniture & Fixtures
334 |  | 2017 |  | 3 units Exhaust Fan |  | 4500 |  |  | 100% | 4500
335 |  | 2017 |  | 3 units Industrial Fan |  | 19656 |  |  | 100% | 19656
336 |  | 2017 |  | 4 units White Board with Movable Stand |  | 11000 |  |  | 100% | 11000
337 |  | 2017 |  | 3 units White Board (4x8x3/4) |  | 9900 |  |  | 100% | 9900
338 |  |  |  | Machinery
339 |  | 2017 |  | 18 units Arc Welding Machine AC/DC & Acc |  | 698040 |  |  | 100% | 698040
340 |  |  |  | Communication Equipment
341 |  | 2017 |  | 1 unit LCD projector |  | 26000 |  |  | 100% | 22995
342 |  |  |  | Disaster Response & Rescue Equipment
343 |  | 2017 |  | 4 units Fire Extinguishers |  | 12364 |  |  | 100% | 12364
344 |  |  |  | Military, Police & Security Equipment
345 |  | 2017 |  | 1 Set Security Equipment Access Control (CCTV) |  | 29845 |  |  | 100% | 29845
346 |  |  |  | Other Machinery & Equipment
347 |  | 2017 |  | 6 units Work Bench w/ Bench Vice on 4 Corners |  | 204000 |  |  | 100% | 204000
348 |  | 2017 |  | 25 sets Combination Spanner (6mm to 24 mm) |  | 80000 |  |  | 100% | 80000
349 |  | 2017 |  | 12 units Blow Torch |  | 18000 |  |  | 100% | 18000
350 |  | 2017 |  | 12 units Clamp on Meter |  | 36000 |  |  | 100% | 36000
351 |  | 2017 |  | 6 units Portable Electric Drill |  | 30000 |  |  | 100% | 30000
352 |  | 2017 |  | 6 units Portable Planer |  | 51600 |  |  | 100% | 51600
353 |  | 2017 |  | 6 units Portable Circular Saw |  | 47220 |  |  | 100% | 47220
354 |  | 2017 |  | 25 pcs Welding Positioners |  | 96250 |  |  | 100% | 96250
355 |  | 2017 |  | 6 units Electrode Oven |  | 24000 |  |  | 100% | 24000
356 |  | 2017 |  | 25 units Portable Disc Grinder |  | 78750 |  |  | 100% | 78750
357 |  | 2017 |  | 6 units Pipe Threader 1/2-2" |  | 343200 |  |  | 100% | 343200
358 |  | 2017 |  | 6 units Pipe Bender |  | 26400 |  |  | 100% | 26400
359 |  | 2017 |  | 6 units Heat Gun 1200 watts |  | 18900 |  |  | 100% | 18900
360 |  | 2017 |  | 6 units Bolt Cutter |  | 7680 |  |  | 100% | 7680
361 |  | 2017 |  | 12 pcs Box Wrench |  | 58800 |  |  | 100% | 58800
362 |  | 2017 |  | 12 pcs Wire Splicer |  | 25320 |  |  | 100% | 25320
363 |  | 2017 |  | 12 pcs Wire Stripper |  | 25320 |  |  | 100% | 25320
364 |  | 2017 |  | 12 units Electric Drill |  | 58800 |  |  | 100% | 58800
365 |  | 2017 |  | 12 units Portable Grinder |  | 52500 |  |  | 100% | 52500
366 |  | 2017 |  | 6 units Pipe Cutter (1/2"-1") |  | 31590 |  |  | 100% | 31590
367 |  | 2017 |  | 3 units Manual Pipe Threader (1/2", 3/4", 1") |  | 33705 |  |  | 100% | 33705
368 |  | 2017 |  | 3 units Fusion Machine (20mm-32mm) |  | 34020 |  |  | 100% | 34020
369 |  | 2017 |  | 4 units Electric Grinder (4") |  | 20520 |  |  | 100% | 20520
370 |  | 2017 |  | 12 units Angle Grinder |  | 61560 |  |  | 100% | 61560
371 |  | 2017 |  | 2 units Labelling Machine |  | 2200 |  |  | 100% | 2200
372 |  | 2017 |  | 6 units Insulation Resistance Tester |  | 9900 |  |  | 100% | 9900
373 |  | 2017 |  | 6 units Earth Resistance Tester |  | 13200 |  |  | 100% | 13200
374 |  | 2017 |  | 4 units Pedestal/Bench Grinding Machine |  | 9400 |  |  | 100% | 9400
375 |  | 2017 |  | 10 units Panel Board with 70 amp main & 4 |  | 34450 |  |  | 100% | 34450
376 |  | 2017 |  | 25 pcs Electrician Pliers |  | 66250 |  |  | 100% | 66250
377 |  | 2017 |  | Other Property, Plant & Equipment
378 |  | 2017 |  | 3 units Wheelbarrow |  | 6600 |  |  | 100% | 6000
379 |  | 2017 |  | 6 sets Oxy-Acetylene/Oxy-LPG Cutting Outfit |  | 72000 |  |  | 100% | 72000
380 |  | 2017 |  | 6 units Plastic Drum (200 liters) |  | 10560 |  |  | 100% | 10560
388 |  | 2018 |  | Purchase of Lot for Multi-Purpose Hall at Sitio Cambulo. Banga | Banga | 600000 |  |  |  | 0
425 | 10710020-002-0057 | 2018 |  | Water System Development at Bugay Proper | Bugay | 500000 | 2019-04-01 | 2020-12-31 | 30% | 148710.4 |  | On going
426 | 10710020-002-0056 | 2018 |  | Development of Water System at Brgy. Villareal | Villareal | 1000000 | 2019-08-12 | 2020-11-30 | 30% | 327600 |  | On going
427 | 10710020-001-0113 | 2018 |  | Installation of Street Lighting from Purok 1 to Purok IV, Brgy. Tayawan | Tayawan | 500000 | 2018-06-21 | 2020-12-31 | 33% | 166705.62 |  | Pending: Materials not yet delivered
428 | 10710020-009-0001 | 2018 |  | Improvement of Barangay Plaza and Children's Park, Tayawan | Tayawan | 500000 | 2018-06-21 | 2020-12-31 | 85% | 193225.96 |  | Temporarily Stopped: Due to COA's remarks in POW
429 | 0 | 2018 |  | Establishment of Early Child Care Dev't Centers: | Bayawan City
430 | 10710030-002-0021 | 2018 |  | a. Brgy. Villareal | Villareal | 5000000 | 2018-06-21 | 2020-03-31 | 95% | 4422941.73
431 | 10710030-002-0022 | 2018 |  | b. Brgy. Malabugas | Malabugas | 5000000 | 2018-06-21 | 2019-11-15 | 100% | 4874380.13
432 | 10710030-002-0023 | 2018 |  | Construction of Day Care Center at Sitio Mantapi, Nangka | Nangka | 578571.43 | 2018-12-01 | 2020-12-01 | 56% | 325812.46 |  | On going
433 | 0 | 2018 |  | Improvement of Barangay Health Center & Lying-In Clinic, Brgy. Malabugas | Malabugas | 1000000 |  |  |  | 406333.27
434 | 10710030-003-0008 | 2018 |  | Construction of Health Center at Sitio Mantapi, Nangka | Nangka | 500000 | 2019-11-12 | 2020-11-12 | 22% | 110023.07 |  | On going
443 | 10710030-030-0138 | 2018 |  | Construction of Bleachers at Barangay Evacuation Center, Ali-is | Ali-is | 678571.43 | 2018-01-04 | 2019-04-30 | 100% | 555739.56
444 | 10710030-030-0146 | 2018 |  | Improvement of Barangay Multi-Purpose Building, Banaybanay | Banaybanay | 1000000 |  |  |  | 0
445 | 10710030-030-0150 | 2018 |  | Improvement of Barangay Multi-Purpose Hall, Brgy. Boyco | Boyco | 1678571.43 |  |  |  | 0
446 | 10710030-030-0144 | 2018 |  | Construction of Barangay Multi-Purpose Building, Cansumalig | Cansumalig | 1300000 | 2019-07-16 | 2020-07-16 | 75% | 973876.6 |  | On going
448 | 10710030-030-0147 | 2018 |  | Improvement of Barangay Multi-Purpose Building, Maninihon | Maninihon | 1000000 | 2019-11-01 | 2020-08-15 | 70% | 361599.05 |  | On going
449 | 10710030-030-0155 | 2018 |  | Construction of Multi-Purpose Pavement at Sitio Mantapi, Nangka | Mantapi, Nangka | 600000 | 2018-01-07 | 2018-12-31 | 100% | 546309.58
450 | 10710030-030-0148 | 2018 |  | Construction of Barangay Multi-Purpose Building, Narra | Narra | 1000000 |  |  |  | 0
451 | 10710010-002-0005 | 2018 |  | Construction of Concrete Perimeter Fence of Covered Court and Evacuation Center, Brgy. Pagatban | Pagatban | 100000 | 2018-01-07 | 2018-08-31 | 100% | 86496.06
452 | 10710030-030-0145 | 2018 |  | Construction of Multi-Purpose Building, Brgy. San Isidro (Phase 2) | San Isidro | 1078571.43 | 2019-01-08 | 2020-04-15 | 75% | 871730.03 |  | On going
453 | 10710030-030-0137 | 2018 |  | Construction of Children and Women's Crisis Center, Brgy. Suba | Suba | 600000 |  |  |  | 0
454 | 10710030-030-0153 | 2018 |  | Improvement of Multi-Purpose Hall, Brgy. Suba | Suba | 578571.43 |  |  |  | 0
455 | 10710030-030-0149 | 2018 |  | Construction of Multi-Purpose Hall, Brgy. Tinago | Tinago | 2278571.43 | 2019-07-01 | 2020-12-31 | 30% | 2961352.63 |  | Excess cost: Budget of Multi Purpose of Tinago (CY 2018 = 2,278,571.43 & CY2019 = 1,678,571.43) were consolidated in POW
457 | 10710030-030-0152 | 2018 |  | Improvement of Multi-Purpose Hall, Banga | Banga | 2078571.43 |  |  |  | 0
460 | 10710030-030-0151 | 2018 |  | Improvement of Barangay Multi-Purpose Hall, Manduao | Manduao | 600000 | 2019-05-24 | 2020-03-15 | 100% | 440893.31
|  | 2019 |  | Construction of Multi-Purpose Pavement at Sitio -Upper Pinangimnan | San Jose | 839285.7 | 2020-04-15 |  | 20% | 0 |  | On going
|  | 2019 |  | Construction of Multi-Purpose Pavement at Sitio Pitogo 1 | San Jose | 839285.73 | 2020-04-15 |  | 20% | 0 |  | On going
|  | 2019 |  | Lot Acquisition for Dita Relocation | Tabuan | 5000000
|  | 2019 |  | Construction & Installation of Water Supply Systems for Barangays Malabugas, San Roque, Minaba, San Miguel and Tayawan | Various Brgys | 11000000 |  |  |  | 0
|  | 2019 |  | Construction of Day Care Center, Brgy San Miguel | Bayawan City | 400000 | 2019-07-16 | 2019-09-30 | 100% | 258202.4
|  | 2019 |  | Electrification Project at Purok Ipil-Ipil, San Roque | San Roque | 600000 |  |  |  | 0
|  | 2019 |  | Construction of Concrete Fence of Minaba Elementary School | Minaba | 500000 | 2019-05-16 | 2020-03-31 | 90% | 206871.98 |  | On going
|  | 2019 |  | Construction of Concrete Fence of Canabuan Elementary School | Minaba | 500000 | 2019-01-06 | 2020-03-31 | 90% | 222376.86 |  | On going
|  | 2019 |  | Construction of Concrete Fence of Minaba High School | Minaba | 678571.43 | 2019-01-06 | 2020-03-31 | 90% | 191587.41 |  | On going
|  | 2019 |  | Construction of Concrete Fence of Bolirocon Elementary School, San Isidro | Bolirocon, San Isidro | 278571.43 | 2019-01-08 | 2020-03-31 | 100% | 188217
|  | 2019 |  | Construction of Perimeter Fence at San Roque Elementary School | San Roque | 578571.43 | 2019-01-06 | 2020-03-31 | 90% | 180751.8 |  | On going
|  | 2019 |  | Completion of Lapay Multi-Purpose Pavement | Dawis | 360000 | 2019-06-16 | 2019-08-31 | 100% | 211987.95
|  | 2019 |  | Construction of Barangay Multi-Purpose Building, Nangka | Nangka | 1678571.43 | 2019-06-30 | 2020-04-30 | 15% | 860544.88 |  | On going
|  | 2019 |  | Construction of 2-Storey Multi-Purpose Building, Brgy. Poblacion | Poblacion | 1678571.43 | 2019-06-30 | 2020-06-30 | 30% | 961005.84 |  | On going
|  | 2019 |  | Construction of Multi-Purpose Building, Barangay San Isidro (Phase 3) | San Roque | 1000000 | 2019-09-30 | 2020-07-31 | 8% | 169435.96 |  | On going
|  | 2019 |  | Construction of Barangay Multi-Purpose Building, Tinago (Phase 3) | Tinago | 1678571.43 | 2020-03-01 |  | 30% | 0 |  | On going
|  |  |  | Total Projects for Social Development - Continuing Appropriation |  | 155210032.22 |  |  |  | 84188367.83
ECONOMIC DEVELOPMENT
64 | 10710020-006-0003 | 2011 |  | Const. of Hanging Bridge at Sitio Tiki, Kalumboyan (Phase 3) | Kalumboyan | 700000 | 2011-07-01 | 2020-12-31 | 37% | 546410.34 |  | Project heavily damaged by typhoon - discontinued
65 | 10710030-005-0002 | 2012 |  | Construction of Slaughterhouse | Suba | 10000000 | 2016-09-16 | 2018-03-31 | 100% | 7818835.46
72 | 0 | 2013 |  | Fabrication of Distillation Chamber for Essential Oil Production | Banga | 150000 |  |  |  | 0
73 | *10710020-001-0011 | 2014 |  | Construction of Bayawan City Boulevard/Phase 2 | Bayawan City | 1000000 | 2014-08-16 | 2014-10-30 | 100% | 936750.81
74 | *10710030-030-0031 | 2014 |  | Const. of Motorpool Building, Phase 1, Cabcabon | Cabcabon, Banga | 8483700 | 2015-07-06 | 09/31/17 | 100% | 7893686.98
76 | per saaob | 2014 |  | Major Repair - Construction & Heavy Equipment | Motorpool Area | 10000000 | 2014-06-11 | 2020-12-31 | 22% | 2242763 |  | Pending : Some equipments already deteriorated
78 | 10710020-001-0039 | 2014 |  | Road Surfacing from Sitio Binanigan to Sitio Guintana-an, Brgy. Tayawan, Phase 1 | Tayawan | 500000 | 2016-03-16 | 2020-04-01 | 90% | 173183.68 |  | Pending: Need to look other quarry source, road not yet passable
80 | *10710020-002-0025 | 2014 |  | Construction of Water System-Crusher Kalumboyan |  | 212800 | 2015-06-01 | 2016-06-30 | 100% | 182582.35
86 | no obligation | 2015 |  | Purchase of Various Heavy Equipment |  | 3476406.99 |  |  |  | 0
88 | *10710020-001-0019 | 2015 |  | Reblocking of Concrete Pavement at Villareal-Cansumalig-San Isidro FMR, Phase 2 | Bayawan City | 500000 | 2015-06-01 | 2015-06-30 | 100% | 457677.34
89 | 10710020-001-0013 | 2015 |  | Construction of Gomez Street Extension | Bayawan City | 3000000 | 2016-03-16 | 2018-06-30 | 100% | 1148517.88
90 | *10710020-001-0016 | 2015 |  | Concreting of Road Shoulder of National Highway Fronting BNHS, | Bayawan City | 3000000 | 2016-02-09 | 2017-01-15 | 100% | 2935348.39
91 | *10710020-001-0017 | 2015 |  | Construction of Access Road at Bayawan East, | Bayawan City | 2053659.56 | 2015-04-01 | 2016-03-15 | 100% | 1967337.73
92 | 10710020-001-0040 | 2015 |  | Road Surfacing of Sitio Hag-um and Sitio Mambunot, Brgy. Tayawan, Phase 1 | Tayawan, Bayawan City | 500000 | 2016-03-16 | 2020-02-15 | 99% | 444447.41 |  | On going
93 | *10710020-001-0022 | 2015 |  | Rehabilitation of FMR at Sitio Tubod, Brgy. Tabuan | Tubod, Tabuan | 100000 | 2015-10-01 | 2016-03-15 | 100% | 56654.12
94 | *10710020-001-0021 | 2015 |  | Rehabilitation of Pulangyuta-Lapay FMR | Bayawan City | 2014400 | 2015-09-16 | 2017-03-31 | 100% | 2008455.26
122 | 10710030-030-0076 | 2016 |  | Improvement of Agricultural Dev. Ctr. (ADC), Cansumalig, Phase 2 | Cansumalig | 400000 | 2017-06-01 | 2018-06-30 | 100% | 348687.17
141 | *10710020-002-0043 | 2016 |  | Const. of Rain Collector at Brgy. San Isidro | San Isidro | 150000 | 2017-12-16 | 2018-05-31 | 100% | 137210.67
142 | 0 | 2016 |  | Fish Farm Development Program |  | 900000 |  |  |  | 0
144 | 10710030-003-0009 | 2016 |  | Renovation of the Integrated Business Center(IBC) Building | Villareal | 8000000 | 2017-04-27 | 2020-02-15 | 100% | 7449981.63
145 | 10710030-030-0086 | 2016 |  | Pilot Livestock Silage Stocking Project |  | 2000000 |  |  |  | 1650821.2
147 | *10710030-004-0005 | 2016 |  | Establishment of Bayawan Farmers' Market in Dumaguete |  | 5000000 | 2018-02-05 | 2018-10-31 | 100% | 4994489.13
149 | per saaob | 2016 |  | Purchase of Agricultural & Forestry Equipment and Implements |  | 8800000 | 2018-01-02 | 2018-12-31 | 100% | 8400000
|  | 2016 |  | Purchase of Digital Weighing Scale |  | 250000 |  |  |  | 0
153 | *10710020-001-0031 | 2016 |  | Improvement of Nangka-Narra FMR | Bayawan City | 5000000 | 2016-06-16 | 2017-08-31 | 100% | 4454951.93
154 | *10710020-001-0041 | 2016 |  | Improvement of Maninihon-Cansumalig-San Isidro FMR | Bayawan City | 5000000 | 2016-06-16 | 2017-09-15 | 100% | 4785135.91
155 | *10710020-001-0053 | 2016 |  | Reblocking of Concrete Pavement at Villareal-Cansumalig-San Isidro FMR, Phase 3 | Bayawan City | 500000 | 2017-03-01 | 2017-07-31 | 100% | 470136.11
156 | *10710020-001-0043 | 2016 |  | Reblocking of Concrete Pavement Nangka- Narra FMR | Bayawan City | 500000 | 2017-02-16 | 2017-06-30 | 100% | 472475.09
157 | *10710020-001-0062 | 2016 |  | Reblocking of Concrete Pavement with Slope Protection at Malabugas-San Roque Route | Bayawan City | 500000 | 2017-05-01 | 2017-10-31 | 100% | 463375.74
158 | *10710020-001-0052 | 2016 |  | Reblocking of Concrete Pavement with Slope Protection at Tabuan-Banay-banay Route | Bayawan City | 500000 | 2017-05-01 | 2017-10-31 | 100% | 463537.29
159 | *10710020-001-0049 | 2016 |  | Concreting of Road Approaching Upper Baican Box Culvert with Slope Protection | Bugay | 1000000 | 2016-10-16 | 2017-06-30 | 100% | 974648.99
160 | *10710020-001-0048 | 2016 |  | Concreting of Road Approaching Nayabaan Box Culvert with Slope Protection | Bugay | 1000000 | 2016-09-16 | 2017-07-15 | 100% | 908111.85
161 | *10710020-001-0063 | 2016 |  | Concreting of Road Approaching Cagayon Box Culvert with Slope Protection | Banaybanay | 1000000 | 2017-01-01 | 2017-10-31 | 100% | 922836.09
162 | *10710020-001-0061 | 2016 |  | Concreting of Road Approaching Cabigohan Box Culvert with Slope Protection | Dawis | 1000000 | 2017-05-01 | 2017-10-15 | 100% | 947426.51
163 | 10710020-030-0001 | 2016 |  | Installation of Guardrails at Kalumboyan Bridge Approaches | Kalumboyan | 2000000 | 2017-08-01 | 2018-06-30 | 100% | 1716619.15
164 | *10710020-006-0008 | 2016 |  | Const. Tiki Footbridge, Phase 2 Brgy. Kalumboyan | Kalumboyan | 700000 | 2017-04-16 | 2018-02-28 | 100% | 685551.67
165 | 10710020-001-0025 | 2016 |  | Const. of Urban Roads (Gomez to Kabankalan Road) | City Proper | 8000000 | 2017-06-01 | 2018-12-31 | 100% | 5854241.79
166 | 10710020-001-0032 | 2016 |  | Rehab of FMR at So. Pag-awitan, Ali-is | Ali-is | 500000 | 2018-05-16 | 2018-12-31 | 100% | 296371.2
167 | 10710020-001-0036 | 2016 |  | Road Opening at Sitio Palasanon, Cansinacao, Guintalasan Mangharaw & Guinhamogan, Brgy Cansumalig | Cansumalig | 500000 | 2018-02-16 | 2020-06-30 | 50% | 114051.44 |  | Pending: Road no longer passable
168 | 10710020-001-0033 | 2016 |  | Road Rehabilitation at so. Camague, Brgy Dawis | Villareal | 500000 | 11/31/2019 | 2020-07-31 | 15% | 82591.46 |  | Pending: Road no longer passable
169 | 10710020-001-0035 | 2016 |  | Road surfacing at Manduao-Bucao, Brgy Manduao | Manduao | 500000 | 2016-03-16 | 2020-12-31 | 5% | 167283.93 |  | Pending: Road no longer passable
170 | *10710020-006-0009 | 2016 |  | Const. of Steel Bridge Connecting So. Malampa to So. Tab-ang, Brgy Pagatban | Pagatban | 500000 | 2017-06-16 | 2018-01-31 | 100% | 408032.04
171 | *10710020-001-0060 | 2016 |  | Const. or Road from Gov't. Ctr. To sitio Buli-buli/Phase 2 | Banga | 2000000 | 2017-01-01 | 11-31-17 | 100% | 1680955.01
172 | 10710020-001-0064 | 2016 |  | Improvement of Road Along Bayawan CIP Main Canal | Bayawan City | 190000 | 2019-08-16 | 2020-05-15 | 47% | 90000
173 | *10710020-006-0010 | 2016 |  | Const. of Footbridge at Sitio Lower Baican, Brgy Villasol | Baican, Villasol | 220000 | 2018-02-01 | 2018-06-30 | 100% | 221204.91 |  | Excess cost due to of inventory averaging of eNGAS
179 | *10710020-003-0004 | 2016 |  | Rehabilitation of Bayawan Communal Irrigation System | Pagatban | 500000 | 2016-08-16 | 2016-12-31 | 100% | 458455.32
180 | 10710020-003-0005 | 2016 |  | Const. of Small Scale Irrigation Project at Sitio Magsulay | Narra | 1000000 | 2016-08-16 | 2019-12-31 | 100% | 1031939.62 |  | For adjustment: Erroneous charging of materials
184 | *10710020-004-0011 | 2016 |  | Const. of Box Culvert in So. Candalaga, Brgy Nangka | Nangka | 500000 | 2017-03-16 | 2017-06-30 | 100% | 413628.17
185 | *10710020-002-0042 | 2016 |  | Construction of Spring Box at Upper Talao, San Isidro | San Isidro | 500000 | 2018-04-15 | 2019-03-31 | 100% | 261148.49
186 | *10710020-004-0016 | 2016 |  | Const. of 1 unit Single Box Culvert Phase 1 at So, Magsakang, brgy Tayawan | Tayawan | 500000 | 2018-01-16 | 2018-05-15 | 100% | 410379.87
211 | 10710030-030-0049 | 2017 |  | Construction of Pigpens |  | 400000 | 2019-12-01 | 2020-12-01 | 1% | 3301.01
212 | 0 | 2017 |  | Construction of 2 Units Small Scale Rubber Processing Plant with Shed |  | 300000 |  |  |  | 0
213 | budget data | 2017 |  | Purchase of Breeding Stocks | Bayawan City | 1944000 |  |  |  | 0
214 | 0 | 2017 |  | Improvement of Brgy. Dawis Livestock Auction Market | Dawis | 150000 |  |  |  | 0
215 | *10710030-030-0091 | 2017 |  | Fabrication of Portable Batching Plant |  | 500000 | 2017-10-16 | 2018-05-31 | 100% | 325671.05
216 | *10710030-001-0004 | 2017 |  | Construction of CEO Multi-Purpose Building | Cabcabon | 2000000 | 2017-04-16 | 2019-04-30 | 100% | 1744342.36
217 | 10710030-030-0088 | 2017 |  | Construction of Motorpool Building at Cabcabon | Cabcabon | 8000000 | 2017-05-16 | 2019-12-15 | 99.5% | 6670246.05
218 | no obligation | 2017 |  | Lot Acquisition |  | 500000 |  |  |  | 0
220 | 0 | 2017 |  | Improvement of Public Market Water System | Bayawan City | 500000 |  |  |  | 0
221 | *10710020-001-0076 | 2017 |  | Construction of Slope Protection at Narra-Duyanduyan FMR, Sito Duyan-duyan, Brgy. Narra | Bayawan City | 1000000 | 2017-10-16 | 2018-05-31 | 100% | 895097.05
225 | no obligation | 2017 |  | Purchase of Various Agricultural Equipment | Bayawan City | 4000000 |  |  |  | 0
291 | *10710020-001-0080 | 2017 |  | Slope Protection at Barangay Proper, San Isidro | San Isidro | 50000 | 2017-11-16 | 2018-01-31 | 100% | 48807.67
227 | 10710020-006-0012 | 2017 |  | Construction of Flat Slab Bridge at Brgy. Proper, Banaybanay | Banaybanay | 600000 | 2018-01-16 | 2018-09-30 | 100% | 583108.44
228 | 0 | 2017 |  | Improvement of FMR at Sitio Cangcawit, Banaybanay | Banaybanay | 1078571.43 |  |  | 72% | 171610.35 |  | On going
229 | 10710030-030-0189 | 2017 |  | Improvement of Covered Court & Evacuation Center, Brgy. Banga | Banga | 500000 | 2019-03-16 | 2019-10-30 | 100% | 358699.53
230 | *10710020-001-0079 | 2017 |  | Improvement of FMR at Sitio Cansig-id, Brgy. Banga | Banga | 500000 | 2017-12-01 | 2018-01-31 | 100% | 455034
231 | 0 | 2017 |  | Improvement of FMR from Brgy. Proper to Sitio Aya, Brgy. Bugay | Bugay | 839286.43 |  |  |  | 0
232 | 0 | 2017 |  | Improvement of FMR from Brgy Proper to Sitio Canlantang,Brgy. Bugay | Bugay | 839285 |  |  |  | 0
236 | 264-009-1711-g0597 | 2017 |  | Construction of Satellite Farmers' Market, Brgy. Dawis | Dawis | 1000000 |  |  |  | 0
238 | 10710020-001-0115 | 2017 |  | Improvement of FMR at Brgy. Dawis | Dawis | 150000 | 2018-06-01 | 2019-02-22 | 100% | 146687.65
239 | 10710020-001-0081 | 2017 |  | Improvement of Road from Barangay Proper to Kalamtukan Elementary School, Brgy. Kalamtukan | Kalamtukan | 1178571.43 | 2017-10-16 | 2018-06-15 | 100% | 1083384.59
241 | 0 | 2017 |  | Improvement of FMR at Brgy. Proper, Manduao | Manduao | 500000 |  |  |  | 116567.5 |  | Pending: Road not yet passable
246 | *10710020-001-0114 | 2017 |  | Improvement of FMR at Brgy. Minaba | Minaba | 678571.43 | 2018-05-16 | 2019-01-31 | 100% | 532636.79
247 | 10710020-001-0075 | 2017 |  | Improvement of FMR at Sitio Kasla, Brgy. Nangka | Nangka | 1000000 | 2017-12-01 | 2018-07-31 | 100% | 910370.06
249 | 10710020-001-0085 | 2017 |  | Improvement of FMR at Sitios Terong, Palongpong, Canggabi and Cadal-ugan, Brgy. Narra | Narra | 1000000 | 2018-05-16 | 2020-08-01 | 35% | 246842 |  | On going
250 | 10710020-001-0072 | 2017 |  | Road Opening at Brgy. Narra Proper | Narra | 678571.43 | 2018-06-16 | 2019-12-31 | 90% | 301799.59 |  | On going
252 | 0 | 2017 |  | Construction of Barangay Public Market, Brgy. San Jose | San Jose | 1678571.43 |  |  |  | 0
253 | 0 | 2017 |  | Construction of Cloning Chamber at San Roque BADC | San Roque | 50000 |  |  |  | 0
255 | 10710020-006-0013 | 2017 |  | Improvement of Flat Slab Bridge at Sitio Magsakang, Brgy Tayawan | Tayawan | 500000 | 2019-02-16 | 2019-10-31 | 100% | 359123.07
256 | 10710020-001-0074 | 2017 |  | Improvement of Binanigan-Guintanaan FMR, Tayawan | Tayawan | 678571.43 | 2019-10-15 | 2020-07-31 | 96% | 24776.18 |  | On going
257 | 10710020-001-0073 | 2017 |  | Improvement of Binanigan-Napo FMR, Brgy. Tayawan | Tayawan | 500000 | 2019-01-10 | 2020-03-16 | 95% | 363640.42 |  | On going
260 | 10710020-006-0014 | 2017 |  | Construction of Flat Slab Bridge Connecting Barangay Proper to Purok Malinong, Brgy. Villasol | Villasol | 1078571.43 | 2018-02-15 | 2019-04-30 | 100% | 1023638.83
288 | 0 | 2017 |  | Improvement of FMR at Brgy. Banaybanay | Banaybanay | 100000 |  |  |  | 0
295 | 10710020-001-0078 | 2017 |  | Improvement of FMR at Sitio Napit-an, Brgy. Maninihon | Maninihon | 220000 | 2018-04-01 | 2018-07-31 | 100% | 189414.53
297 | 10710020-001-0082 | 2017 |  | Improvement of FMR at Sitio Ondol, Brgy. Nangka | Nangka | 100000 | 2018-04-01 | 2018-08-31 | 100% | 95011
299 | *10710020-001-0077 | 2017 |  | Road Improvement at Brgy. Ubos | Ubos | 170000 | 2018-01-01 | 2018-02-15 | 100% | 148954.81
300 | *10710020-030-0002 | 2017 |  | Construction of Pathway to Banay-Banay Proper | Banay-Banay | 100000 | 2017-10-16 | 2018-02-28 | 100% | 90879.07
302 | 10710020-001-0084 | 2017 |  | Road Opening from National Highway to Purok 1 Pasil, Brgy. Malabugas | Malabugas | 150000 | 2019-09-15 | 2020-09-16 | 50% | 70424.49 |  | Pending: No Right Of Way
305 | 10710020-001-0083 | 2017 |  | Improvement of FMR at Sitio San Ramon, Brgy. Poblacion | Poblacion | 150000 | 2018-04-01 | 2018-08-31 | 100% | 143423.48
313 | 10710020-001-0070 | 2017 |  | Rehabilitation of Farm to Market Road from Sitio Bosque to Tavera, Barangay Nangka | Nangka | 1000000 | 2019-06-12 | 2020-06-10 | 80% | 447997.6 |  | On going
316 | no obligation | 2017 |  | Purchase of Lot(Road Right of Way for Various Road Projects) |  | 2980124.07 |  |  |  | 0
193 | 10710010-001-0003 | 2017 |  | Development of Danapa Eco Park | Nangka | 18000000 | 2017-12-06 | 2020-02-29 | 98% | 16778685.58 |  | Pending: Punch list not yet rectify & Subject For Termination
194 | 10710020-030-0003 | 2017 |  | Development of Narra Water Park | Narra | 16000000 | 2017-09-12 | 2018-09-30 | 100% | 15993892.48
315 | budget data | 2017 |  | Purchase of Livestock Breeding Stocks |  | 533460 | 2017-05-31 | 11/31/2019 | 100% | 515555.56
386 |  | 2018 |  | Loan Amortization |  | 9809031.89 |  |  |  | 0
387 |  | 2018 |  | Lot Acquisition for Development Projects |  | 1754285.71 |  |  |  | 0
389 | 10710020-001-0112 | 2018 |  | Widening of Malabugas-San Roque Road |  | 3500000 | 2019-01-09 | 2019-12-31 | 85% | 2178790.09 |  | On going
390 | 10710020-001-0095 | 2018 |  | Concreting of Road Approaching Lapay Box Culvert with Slope Protection, Dawis | Bayawan Creek, Dawis | 1000000 | 2018-04-01 | 2018-08-31 | 100% | 747445.26
391 | 10710020-001-0094 | 2018 |  | Concreting of Road Approaching Candalaga Box Culvert with Slope Protection, Nangka | Nangka | 1000000 | 2018-04-01 | 2018-11-30 | 100% | 871727.74
392 | 10710020-001-0098 | 2018 |  | Concreting of Road Approaching Pusi-on Box Culvert with Slope Protection, Maninihon | Maninihon | 1000000 | 2018-04-01 | 2019-02-28 | 100% | 853186.46
393 | 10710020-001-0093 | 2018 |  | Concreting of Road Approaching Camandagan Box Culvert with Slope Protection, Maninihon | Maninihon | 1000000 | 2018-04-01 | 2018-09-30 | 100% | 788542.62
394 | 10710020-001-0091 | 2018 |  | Concreting of Road Approaching Balao Box Culvert with Slope Protection, San Miguel | San Miguel | 1000000 | 2018-04-01 | 2018-10-30 | 100% | 829699.91
395 | 10710020-001-0096 | 2018 |  | Concreting of Road Approaching Magsakang Box Culvert with Slope Protection, Tayawan | Tayawan | 1000000 | 2018-04-01 | 2019-07-31 | 100% | 852527.64
396 | 10710020-006-0016 | 2018 |  | Completion of Magsakang Flat Slab Bridge, Tayawan | Tayawan | 1000000 | 2018-04-01 | 2019-04-30 | 100% | 954259.8
397 | 10710020-001-0097 | 2018 |  | Concreting of Road Approaching Pamuat Box Culvert with Slope Protection, San Isidro | San Isidro | 1000000 | 2018-04-01 | 2019-06-30 | 100% | 929512.72
398 | 10710020-001-0092 | 2018 |  | Concreting of Road Approaching Binanigan Box Culvert with Slope Protection, Tayawan | Tayawan | 1000000 | 2018-04-01 | 2018-09-30 | 100% | 761723.42
399 | *10710020-001-0086 | 2018 |  | Concreting of Road at Purok 7, Barangay Tinago | Tinago | 2000000 | 2018-02-16 | 2018-08-31 | 100% | 1717211.49
400 | 10710020-001-0088 | 2018 |  | Concreting of Dawis-Lapay FMR | Bayawan City | 5500000 | 2018-04-01 | 2019-07-31 | 100% | 4539005.09
401 | 10710020-001-0087 | 2018 |  | Concreting of Banga-San Roque-Minaba-San Miguel-Tayawan FMR | Bayawan City | 5872000 | 2018-04-01 | 2019-06-30 | 100% | 5221497.1
402 | 10710020-001-0090 | 2018 |  | Concreting of Nangka-Narra FMR | Bayawan City | 5500000 | 2018-04-01 | 2019-05-31 | 100% | 4539901.35
403 | 10710020-001-0105 | 2018 |  | Concreting of Tabuan- Banaybanay-Lapay-Bugay-San Jose-Manduao FMR | Bayawan City | 28340000 | 2019-05-29 | 2019-09-08 | 100% | 28213392.75
404 | 10710020-001-0103 | 2018 |  | Concreting of Road from Sitio Balastro to Sitio Candulion to Pulangyuta, Barangay Kalamtukan | Kalamtukan | 10500000 | 2018-01-08 | 2019-08-31 | 99% | 7874648.88 |  | On going
405 | 10710020-001-0104 | 2018 |  | Concreting of Road with Drainage Canal at Upper Napit-an, Maninihon | Maninihon | 300000 | 2018-04-01 | 2018-07-31 | 100% | 175615.88
406 | 10710020-001-0102 | 2018 |  | Concreting of Road from Highway Intersection to Minaba Elem. School, Brgy. Minaba | Bayawan City | 1000000 | 2018-04-01 | 2018-09-30 | 100% | 703131.2
407 | 10710020-001-0099 | 2018 |  | Concreting of Road at Sitio Kasla, Brgy. Nangka | Nangka | 850000 | 2018-04-01 | 2018-09-30 | 100% | 653409.03
408 | 10710020-006-0020 | 2018 |  | Construction of Flat Slab Bridge at Sitio Terong, Narra | Narra | 600000 | 2018-04-01 | 2019-06-30 | 100% | 520886.82
409 | 10710020-001-0107 | 2018 |  | Road Concreting from Proper Narra to Purok III, Brgy. Narra | Narra | 500000 | 2018-04-01 | 2018-10-16 | 100% | 394052.4
410 | 10710020-001-0089 | 2018 |  | Concreting of FMR from National Highway to Sitio Lapacon, Brgy. Pagatban | Bayawan City | 500000 | 2018-04-01 | 2018-08-31 | 100% | 394562.39
411 | 10710020-001-0100 | 2018 |  | Concreting of Road at Sitio Upper Pamu-at, San Isidro | San Isidro | 500000 | 2018-04-01 | 2020-03-16 | 92.5% | 266044 |  | Pending: Road not yet passable
412 | 10710020-001-0101 | 2018 |  | Concreting of Road at Upper Talao, San Isidro | San Isidro | 600000 | 2018-10-01 | 2019-03-31 | 100% | 514849.54
413 | 10710020-001-0108 | 2018 |  | Road Shouldering Along Zamora St., Brgy. Ubos | Ubos | 500000 | 2018-06-16 | 2018-11-30 | 100% | 428565.85
414 | 10710020-001-0110 | 2018 |  | Road Surfacing from Barangay Proper to Sitio Gawgaw to Sitio Aya, Brgy. Bugay | Bugay | 839286.43 | 2019-03-01 | 2020-12-31 | 20% | 286294.33 |  | Pending: Road not passable
415 | 10710020-001-0111 | 2018 |  | Road Surfacing from Barangay Proper to Sitio Mambuy-og to Sitio Canlantang, Brgy. Bugay | Bugay | 839285 | 2019-01-04 | 2019-12-31 | 97% | 568855.08 |  | On going
416 | 10710020-001-0109 | 2018 |  | Road Surfacing at Barangay Cansumalig | Cansumalig | 1078571.43 |  |  |  | 468635.45 |  | On going
418 | 10710020-004-0017 | 2018 |  | Installation of Cylindrical Culvert with Riprap at Proper Narra | Narra | 578571.43 | 2018-06-16 | 2019-08-31 | 100% | 497818.65
420 | 0 | 2018 |  | Construction of Small Scale Irrigation Projects (SSIP): | Bayawan City
421 | 10710020-003-0007 | 2018 |  | a. Purok Mangga, Brgy. Manduao | Manduao | 800000 | 2018-06-01 | 2020-04-30 | 74% | 593670.45 |  | On going
422 | 10710020-003-0008 | 2018 |  | b. Sitio Dita, Brgy. Tabuan | Tabuan | 800000 | 2018-06-01 | 2020-04-30 | 37% | 299129.89 |  | On going
423 | 10710020-003-0009 | 2018 |  | c. Upper Canlinte, Brgy Ali-is | Ali-is | 800000 | 2018-06-01 | 2020-04-30 | 54% | 458771.33 |  | On going
424 | 10710020-003-0010 | 2018 |  | Rehabilitation of Irrigation Canal at Brgy. Tabuan | Tabuan | 915000 | 2019-03-01 | 2020-03-10 | 95% | 773915.66 |  | On going
435 | 0 | 2018 |  | Construction of Barangay Public Market, Ali-is (Phase 1) | Bayawan City | 1000000 |  |  |  | 0
436 | 10710030-005-0001 | 2018 |  | Completion of Minaba Mini Slaughterhouse Phase III | Minaba | 500000 | 2018-10-16 | 2019-07-31 | 100% | 419375.96
437 |  | 2018 |  | Construction of Rainwater Harvesting Systems for Nurseries:
438 | 10710020-002-0075 | 2018 |  | a. Brgy. San Miguel | San Miguel | 250000 | 2018-10-01 | 2018-11-30 | 100% | 193602.58
439 | 10710020-002-0076 | 2018 |  | b. Brgy. Tayawan | Tayawan | 250000 | 2018-10-16 | 2019-05-31 | 100% | 190464.82
440 | 10710020-002-0077 | 2018 |  | c. Brgy. Cansumalig | Cansumalig | 250000 | 2018-10-16 | 2019-06-30 | 100% | 189960.28
441 | 10710020-002-0078 | 2018 |  | d. Brgy. Manduao | Manduao | 250000 | 2018-10-16 | 2020-05-31 | 100% | 158504.74
442 | 10710020-002-0079 | 2018 |  | e. Brgy. Kalamtukan | Kalamtukan | 250000 | 2018-10-16 | 2020-05-31 | 100% | 183871.5
456 | 10710030-030-0159 | 2018 |  | Construction of Fish Processing Center @ Brgy. Suba | Suba | 2500000 | 2019-04-01 | 2019-12-31 | 80% | 1940773.71
458 | 10710030-030-0161 | 2018 |  | Major Repair of Narra Barangay Agricultural Development Center (BADC) | Narra | 520000 | 2018-09-30 | 2020-03-31 | 69% | 435302.67 |  | On going
459 | 10710030-030-0160 | 2018 |  | Major Repair of Manduao Barangay Agricultural Development Center (BADC) | Manduao | 290000 | 2018-09-30 | 2020-03-31 | 78% | 227443.68 |  | On going
461 | no obligation | 2018 |  | Purchase of Boom Truck | Bayawan City | 1600000 |  |  |  | 0
462 |  | 2018 |  | Purchase of 1 Unit Backhoe for Barangay Tayawan | Tayawan | 1678571.43 |  |  |  | 0
464 | 10701010-001-0129 | 2018 |  | Purchase of Lot for Agricultural Research Center | Maninihon | 16000000 | 2018-12-01 | 2019-12-31 | 100% | 15710989
465 | 0 | 2018 |  | Establishment of Agricultural Research Center | Maninihon | 6895568.71 |  |  |  | 0
466 | 10710020-001-0125 | 2018 |  | Improvement of Bugay-San Jose-Manduao FMR | Bayawan City | 3000000 | 2018-10-15 | 2019-01-06 | 100% | 2959185.3
467 | 10710020-001-0127 | 2018 |  | Concreting of Urban Roads with Drainage System (Gomez St.) | Poblacion | 12885436.16 | 2019-01-16 | 2020-02-29 | 80% | 10465121.94 |  | Pending: Waiting for electrical materials delivery
|  | 2019 |  | Supply & Installation of Hog & Cattle Slaughterhouse Equipment for Bayawan City AA Slaughterhouse Plant | Bayawan City | 16478571.43 |  |  |  | 0
|  | 2019 |  | Construction of Dawis Public Market (Phase 2) | Dawis | 2000000 |  |  |  | 0
|  | 2019 |  | Loan Amortization |  | 4338835.57 |  |  |  | 0
|  | 2019 |  | Lot Acquisition for Road Right of Way | Villareal | 500000 |  |  |  | 0
|  | 2019 |  | Lot Acquisition for Agricultural Development Center (Tan-ayan) | Tan-ayan | 2500000 |  |  |  | 0
|  | 2019 |  | Wayang Access Road Development | Nangka | 20000000 | 2019-02-16 | 2020-04-30 | 75% | 11084614.23 |  | On going
|  | 2019 |  | Construction of Ondol-Napit-an FMR | Bayawan City | 20000000 | 2019-03-15 | 2020-08-31 | 40% | 9678023.68 |  | On going
|  | 2019 |  | Concreting of Access Road from National Highway to Palongpong Agricultural Development Center | Bayawan City | 9000000 | 2019-01-04 | 2020-03-31 | 99% | 4299985.96 |  | On going
|  | 2019 |  | Improvement of Road Leading to Danapa Inland Aquaculture Facility | Nangka | 2000000 | 2019-03-16 | 2019-12-31 | 100% | 1240696.65
|  | 2019 |  | Concreting of Perimeter Road at BCWMEC | Maninihon | 2000000 | 2019-01-06 | 2020-02-15 | 100% | 1596679.95
|  | 2019 |  | Concreting of Urban Roads with Drainage System (Gomez St.) | Poblacion | 3000000 | 2019-07-16 | 2020-03-31 | 80% | 1363098.11 |  | On going
|  | 2019 |  | Improvement of Maninihon-Cansumalig-San Isidro FMR |  | 2387650.49 |  |  |  | 0
|  | 2019 |  | Construction of Public Market Stalls in Omod, Maninihon (Phase 1) | Bayawan City | 1678571.43 | 2019-06-16 | 2020-05-31 | 80% | 1340463.01 |  | On going
|  | 2019 |  | Establishment of Agricultural Research Center |  | 10877134.99 |  |  |  | 0
Purchase of Construction & Heavy Equipment:
|  |  |  | 1 unit Bulldozer |  | 15000000 |  |  |  | 14988000
|  |  |  | 1 unit Backhoe |  | 12000000 |  |  |  | 0
|  |  |  | 1 unit Trailer Mounted DW100-T Drilling Rig with Accessories |  | 3594500 |  |  |  | 0
|  |  |  | 2 units 6-Wheeler Dump Truck |  | 4400000 |  |  |  | 0
|  | 2019 |  | Purchase of Livestock Breeding Stocks |  | 2000000 |  |  |  | 1530000
|  |  |  | Total Projects for Economic Development - Continuing Appropriation |  | 455327994.16 |  |  |  | 281455990.96
ENVIRONMENTAL MANAGEMENT
61 |  | 2004 |  | Sanitary Landfill (Land Acquisition) 2004 | Maninihon | 1000000 |  |  |  | 8311
62 |  | 2001 |  | Sanitary Landfill - Dumpsite Acquisition | Maninihon | 500000 |  |  |  | 0
71 | *10710020-007-0002 | 2013 |  | Construction of Drainage Canal with Cover Along City Streets | Bayawan City | 606779.6 | 2014-06-02 | 2014-11-30 | 100% | 544360.59
182 | *10710020-007-0010 | 2016 |  | Construction of Drainage City Streets - Zamora, Teologio Sts, Subd Area | Zamora, Teologio & Subd Area | 3000000 | 2017-01-01 | 2017-09-15 | 100% | 2461029.39
183 | *10710020-005-0008 | 2016 |  | Rehabilitation of River Bank Protection at Sitio Ebuan | Nangka | 2000000 | 2017-03-16 | 2018-12-31 | 100% | 1451778.7
187 | *10710020-007-0011 | 2016 |  | Const. of Drainage Canal at along Burgos St. & AlongBollos St. Brgy Ubos | Ubos | 500000 | 2017-02-01 | 2017-06-30 | 100% | 442668.24
189 | *10710020-005-0007 | 2016 |  | Rehabilitation of Riverbank @ Brgy. Nangka | Nangka | 1000000 | 2018-05-16 | 2018-12-31 | 100% | 1013905.35 |  | Excess cost due to of inventory averaging of eNGAS
259 | 10710020-007-0017 | 2017 |  | Concreting of Drainage Canal Cover Along National Highway, Brgy. Villareal | Villareal | 678571.43 | 2017-11-16 | 2019-12-31 | 90% | 491510.65 |  | Pending: Due to transfer of site location
307 | *10710020-007-0016 | 2017 |  | Construction of Concrete Covered Canals, Brgy. Tinago | Tinago | 50000 | 2017-10-01 | 2017-10-31 | 100% | 46908.05
308 | *10710020-007-0019 | 2017 |  | Construction of Concrete Covered Canals, Brgy. Ubos | Ubos | 100000 | 2017-10-16 | 2017-11-30 | 100% | 84467.6
311 | *10710020-007-0015 | 2017 |  | Construction of Concrete Covered Canal, Brgy. Suba | Suba | 400000 | 2017-08-16 | 2018-01-31 | 100% | 360752.64
223 | 10710020-007-0022 | 2017 |  | Construction of Drainage at Cabugcabugan Creek, Brgy. Poblacion, Phase 4 | Poblacion | 1356746.77 | 2017-11-16 | 2020-08-31 | 83% | 1197855.77 |  | Pending: Awaits consultation ( BMAKBI, Eldie Tinapao)
320 | *10710020-007-0020 | 2017 |  | Construction of Concrete Covered Canal at Zamora St. Brgy Suba |  | 173060.9 | 2017-08-16 | 2018-01-31 | 100% | 170642.5
321 | *10710020-007-0021 | 2017 |  | Construction of Concrete Canal Cover Along Rizat St. Brgy Tinago |  | 1000000 | 2017-11-16 | 2018-03-31 | 100% | 862393.35
224 | 10710020-005-0010 | 2017 |  | Construction of Riverbank Protection at Camayaan Creek,Brgy. Malabugas | Malabugas | 1000000 | 2018-01-16 | 2018-10-16 | 100% | 898258.82
222 | 10710020-008-0006 | 2017 |  | Flood Control Project at Brgy. Malabugas, Phase 2 | Malabugas | 1500000 | 2017-09-01 | 2018-06-30 | 100% | 1331896.08
417 | 10710020-007-0026 | 2018 |  | Construction of Drainage Canal from Upper Napit-an to Lower Napit-an, Brgy. Maninihon | Maninihon | 650000 | 2018-06-01 | 2018-09-30 | 100% | 546606.01
419 | 10710020-007-0025 | 2018 |  | Covering of Drainage Canals along Gomez St., Brgy. Ubos | Ubos | 1078571.43 | 2018-08-12 | 2020-03-31 | 100% | 823890.36
463 |  | 2018 |  | Purchase of Garbage Compactor Truck | Bayawan City | 1500000 |  |  |  | 0
|  | 2019 |  | Construction of Drainage Canal at Magsulay Agricultural Development Center | Narra | 400000 | 2019-07-16 | 2020-03-31 | 97% | 328396.65 |  | On going
|  | 2019 |  | Concreting of Drainage Canals at Barangay Proper, San Isidro | Bayawan City | 400000 | 2019-01-06 | 2019-08-31 | 100% | 335921.21
|  | 2019 |  | Purchase of Garbage Compactor Truck |  | 5000000 |  |  |  | 0
|  | 2019 |  | Purchase of Vacuum Declogger Truck |  | 2000000 |  |  |  | 0
|  |  |  | Total Projects for Environmental Management - Continuing Appropriation |  | 25893730.13 |  |  |  | 13401552.96
|  | TOTAL EDF CONTINUING APPROPRIATION |  |  |  | 636431756.51 |  |  |  | 379045911.75
|  | TOTAL EDF - CURRENT & CONTINUING APPROPRIATION |  |  |  | 864208979.51 |  |  |  | 422760462.25
|  |  |  | CORAZON P. LIRAZAN, CPA | [5 empty] | HON. PRYDE HENRY A. TEVES
|  |  |  | City Accountant | [5 empty] | City Mayor