## 1st qtr (2)
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FIRST QUARTER , CY 2020
Province, City or Municipality: Bayawan City, Negros Oriental
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of | Remarks
[5 empty] | % of | Total Cost Incurred | Extensions, if
[5 empty] | Completion | to Date | any
Bayawan Agroforestry Project - GTZ EnRD - LGU Equity | Selected barangay in Bayawan City with classified forestland | 1700120 |  |  | 89.52% | 1521988 |  | last transaction 12/31/16
Sta. Bayabas - Common Health Fund | Bayawan City | 4273432.37 |  |  |  | 315913.88
Establishment of Community-Based Instant Complementary Food Processing Center Towards Sustaining Siglang Pinoy Project of the DOST-Food & Nutrition | Barangay Nangka | 347250 |  |  | 95.72% | 332394.25
LGU Equity for the Renovation of Public Market | Bayawan City | 437865 |  |  |  | 0
Financial Assistance to Bayawan City for Various Electrification Projects from Province of Negros Oriental | Bayawan City | 100000 |  |  |  | 0
MNCHN Grant | 28 Barangay | 817794.28 |  |  | 98.01% | 801486.04
Rubber Tree Reforestation Project | Bayawan City | 1500000 |  |  | 76.05% | 1140693.79
page 1 of 5
Rubber Tree Reforestation Project (Nursery Expansion) | Barangay. Banaybanay & Dawis | 500000 |  |  | 78.78% | 393887
DA & LGU Equity to Improvement of Organic Fertilizer Plant & Establishment of Nurseries for the provisions of chemical-free seeds to farmers using greenhouse technology | Barangay Maninihon | 2000000 |  |  |  | 1028400
DA R7 for Organic Fetilizer Production & Marketing (Construction of OFRAB Building & Installation of Electrical & Plumbing of OFPRAB Building) | Sitio Omod, Barangay Maninihon | 805110 |  |  |  | 373471.6
DA R7 for Building & Machine for Food Processing of Fruits, Vegetables, Fish, Grains and Meat |  | 1300000 |  |  |  | 824757.34
DA & LGU Equity to Rehabilitation & Extension of Line Canal for Mantapi - Cansigid Irrigation System (BUB) | Mantapi - Cansigid, Banga | 8000000 | 2018-06-01 |  | 81.18% | 6043908.58
DA & LGU Equity to Mechanical Dryer with Storage Facility for Bugay, Ohot-Narra, Tayawan (BUB-DA) | Bugay, Ohot-Narra; Mantapi | 2500000 |  |  |  | 0
DA & LGU Equity for Small Water Impounding (BUB) | Bayawan City | 4000000 | 2018-04-16 |  | 94.53% | 2839535.22
DA & LGU Equity for Upgrading of Slaughter House Double " A " | Sitio Bulibuli, Brgy. Banga | 30000000 | 2018-03-16 |  | 99.2% | 22169865.91
DA to Acquisition of Palay Reaper(cutter) and Post Harvest Facilities and Equipment for SAAD FY 2017 | Bayawan City | 1040000 |  |  |  | 832000
page 2 of 5
DOLE & LGU Equity to Stainless Steel Equipment for Food Processing | Barangay Nangka | 120000 |  |  |  | 93840
DOLE & LGU Equity to Motorized Fishing Banca & Accessories | Barangay Suba | 502502.4 |  |  |  | 338441.44
DOLE & LGU Equity to Bag Making Project | Cambolo | 345547.6 |  |  |  | 339120
DENR & LGU Equity to On-Farm Wood Lot Production & Agro Forestry Project (BUB) | Brgy Kalamtukan, Tayawan & Narra | 300000 |  |  |  | 0 |  | - No funds received from DENR yet
DOE & LGU Equity to Solar Electification 5 Sitios (BUB) | Tabuan; Manduao; Kalamtukan; Banaybanay & Villasol | 600000 |  |  |  | 0 |  | - No funds received from DOE yet
Construction of Senior Citizen Center (DSWD) | Barangay Boyco | 1000000 |  |  |  | 0
LGU Equity toTech 4ED Project | Bayawan City | 400000 |  |  |  | 0
LGU Equity to Department of Agriculture for High Valued Crops Development | Bayawan City | 656500 |  |  |  | 0
DA to Acquisition of Palay Reaper(cutter) and Post Harvest Facilities and Equipment for SAAD FY 2017 | Bayawan City | 1040000 |  |  |  | 832000
page 3 of 5
DENR to National Greening Program/Comprehesive Site Development (CSD) | Bayawan City | 1583000 |  |  |  | 1226025
DENR to Enhance National Greening Program-Seedling Production & Seedling Maintenance activities of its Rubber | Bayawan City | 2000000 |  |  |  | 115400
DENR to Enhance National Greening Program-Green Rubber Budding, Care and Maintenance of Budded Seedlings of the Rubber | Bayawan City | 1000000 |  |  |  | 0
DOH to Completion of Tabuan Barangay Health Station | Barangay Tabuan | 500000 |  |  |  | 0
DOH to Completion of Minaba Barangay Health Station | Barangay Minaba | 500000 | 2019-10-21 |  | 90% | 127841.74
DOH Completion/Expansion of Boyco Birthing Facility (BHS)) | Barangay Boyco | 300000 |  |  |  | 0
DOH Completion/Expansion of Poblacion Birthing Facility (BHS)) | Barangay Poblacion | 200000 |  |  |  | 0
DOH to Construction/Completion/Expansion of Tayawan Birthing Facility (BHS) | Barangay Tayawan | 750000 | 2020-03-02 | 2020-07-31 | 25% | 221953.12 |  | on going
DOH Construction/Completion/Expansion of Binanigan Birthing Facility (BHS) | Barangay Tayawan | 750000 | 2020-03-02 | 2020-07-31 | 25% | 221953.12 |  | on going
DOH to Construction/Completion/Expansion of Malabugas Birthing Facility (BHS) | Barangay Malabugas | 500000 | 2020-02-21 | 2020-08-04 | 20% | 0 |  | on going
DBM Development of Bayawan City Waterfront Park (Green Green Program) | Coastal Road, Bayawan City | 26865678 |  |  |  | 0
page 4 of 5
LGU Equity to National Housing Authority for Slope Protection at Enzo Town Homes (Phase I) |  | 8776192.5 |  |  |  | 0
NORSU & LGU Equity to Bayawan-NORSU Sports Complex |  | 50000000 |  |  |  | 0
TOTAL |  | 158010992.15 |  |  |  | 42134876.03
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
CORAZON P. LIRAZAN, CPA MBA | [5 empty] | PRYDE HENRY A. TEVES
Local Accountant | [5 empty] | Local Chief Executive
[5 empty] | . |  |  | page 5 of 5
1370213.01
Note on A3: bdtrayvilla1: