## 2nd qtr
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES | [8 empty] | per CPL instruction dated 4/18/18 @ 3: 15 pm the Total cost is equal to the total budget of a certain project received or not received.
SECOND QUARTER , CY 2020
Province, City or Municipality: Bayawan City, Negros Oriental | [8 empty] | new form: SAME FORM EXCEPT SIGNATUR BELOW
Accomplished FU dated 4/16/20 but Donald - work at homeSend to Donald soft copy 4/21/20 ( 4/20/20 - berns & Donald - work at home )
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of | Remarks
[5 empty] | % of | Total Cost Incurred | Extensions, if
[5 empty] | Completion | to Date | any
DA R7 Installation of Electrical & Plumbing of OFPRAB Building | Sitio Omod, Barangay Maninihon | 20000 |  |  |  | 11571 |  |  | CIP (10710030-030-0003) - 177,354.10 + PPE /MOOE = 89,267.50 = 259,617.50 as of 3/31/19 416 ( 20201050-004-000023 ) = 805,110.00
DA R7 Installation of Water System of OFPRAB Building | Sitio Omod, Barangay Maninihon | 40000 |  |  |  | 24221.6
DA R7 for Construction of Food Processing Building |  | 1000000 |  |  |  | 824757.34 |  |  | 416 (20201050-004-000053) = 1,300,000.00 CIP - 10710030-030-0186
DA & LGU Equity to Rehabilitation & Extension of Line Canal for Mantapi - Cansigid Irrigation System (BUB) | Mantapi - Cansigid, Banga | 8000000 |  |  |  | 6043908.58 |  |  | CIP - (10710020-003-0011) 416 (20201050-004-000025) = 1,956,000.00 + 418 ( 20201070-005-034) = 4,088,000.00
DA & LGU Equity for Small Water Impounding (BUB) | Bayawan City | 4000000 |  |  |  | 2839535.22 |  |  | CIP (10710020-003-0002) earth canal = 1,411,713.63 + CIP (10710020-003-0003) diversion dam = 1,427,821.59. TOTAL = 2,839,535.22 416 (20201050-004-000024) = 1,600,000.00 + 418 (20201070-005-036) = 800,000.00
DA & LGU Equity for Upgrading of Slaughter House Double " A " | Sitio Bulibuli, Brgy. Banga | 30000000 | 2018-03-16 |  |  | 22169865.91 |  |  | 10710030-005-0003 = Grant = 14,999,411.19 + LGU = 7,270,304.72. TOTAL = 22,269,715.91 (Note: ENGA's = 22,169,865.91 + PPE = 99,850.00. TOTAL = 22,269,715.91).
page 1 of 3
Construction of Senior Citizen Center (DSWD) | Barangay Boyco | 1000000 |  |  |  | 0
DOH to Completion of Tabuan Barangay Health Station | Barangay Tabuan | 500000 |  |  |  | 0
DOH to Completion of Minaba Barangay Health Station | Barangay Minaba | 500000 |  |  |  | 133399.39
DOH Completion/Expansion of Boyco Birthing Facility (BHS)) | Barangay Boyco | 300000 |  |  |  | 152259.83
DOH Completion/Expansion of Poblacion Birthing Facility (BHS)) | Barangay Poblacion | 200000 |  |  |  | 0
DOH to Construction/Completion/Expansion of Tayawan Birthing Facility (BHS) | Barangay Tayawan | 750000 |  |  |  | 0
DOH Construction/Completion/Expansion of Binanigan Birthing Facility (BHS) | Barangay Tayawan | 750000 |  |  |  | 0
DOH to Construction/Completion/Expansion of Malabugas Birthing Facility (BHS) | Barangay Malabugas | 500000 |  |  |  | 0
DBM Development of Bayawan City Waterfront Park (Green Green Program) Phase I | Coastal Road, Bayawan City | 26865678 |  |  |  | 0
LGU Equity to National Housing Authority for Slope Protection at Enzo Town Homes (Phase I) |  | 8776192.5 |  |  |  | 0
NORSU & LGU Equity to "Bayawan LGU-NORSU" Joint Venture for Sports Complex Project |  | 50000000 |  |  |  | 0
page 2 of 3
DBM Development of Bayawan City Waterfront Park (Green Green Program) Phase II |  | 14694897 |  |  |  | 0
TOTAL |  | 147896767.5 |  |  |  | 32199518.87
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
Prepared by: | [5 empty] | Approved by:
[5 empty] | . |  |  | page 3 of 3
1370213.01
Note on A3: bdtrayvilla1: