## 2nd
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
SECOND QUARTER , CY 2021
Province, City or Municipality: Bayawan City, Negros Oriental
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of | Remarks
[5 empty] | % of | Total Cost Incurred | Extensions, if
[5 empty] | Completion | to Date | any
Sta. Bayabas - Common Health Fund | Bayawan City | 5502173.66 |  |  |  | 910517.16 |  | on going
Financial Assistance to Bayawan City for Various Electrification Projects from Province of Negros Oriental | Bayawan City | 100000 |  |  |  | 0 |  | received 1/11/2011, . not yet implemented
Rubber Tree Reforestation Project | Bayawan City | 1500000 |  |  |  | 1140693.79 |  | per DA: balance to . be used in CY 2021
DA & LGU Equity to Improvement of Organic Fertilizer Plant & Establishment of Nurseries for the provisions of chemical-free seeds to farmers using greenhouse technology | Barangay Maninihon | 2000000 |  |  |  | 1028400 |  | per DA: for re-PR due . to price increase
DA R7 for Organic Fetilizer Production & Marketing (Construction of OFRAB Building & Installation of Electrical & Plumbing of OFPRAB Building) | Sitio Omod, Barangay Maninihon | 805110 | 2020-07-01 | 2020-09-30 |  | 521336.6 |  | - Building: completed ……….per COC …- Administrative cost: ….....on going
DA R7 for Building & Machine for Food Processing of Fruits, Vegetables, Fish, Grains and Meat (Construction of Food Processing Building | Sitio Palongpong, Narra | 1300000 | 2020-01-16 | 2020-03-06 |  | 824757.34 |  | - Building: completed ……….per COC …- Machine: for ….....procurement
DA & LGU Equity to Rehabilitation & Extension of Line Canal for Mantapi - Cansigid Irrigation System (BUB) | Mantapi - Cansigid, Banga | 8000000 |  |  | 81.18% | 6043908.58 |  | - awaiting 50% . unreleased fund . P1,956,000.00
page 1 of 3
DA & LGU Equity to Mechanical Dryer with Storage Facility for Bugay, Ohot-Narra, Tayawan (BUB-DA) | Bugay, Ohot-Narra; Mantapi | 2500000 |  |  |  | 0 |  | per DA: for re-PR due . to price increase
DA & LGU Equity for Small Water Impounding (BUB) Earth Canal | SitioTab-ang, Pagatban | 2000000 | 2018-04-16 |  | 94.53% | 1411713.63 |  | awaiting 50% unreleased . . fund of P800,000.00
DA & LGU Equity for Small Water Impounding (BUB) - Small Diversion Dam | Sitio Cambanoy, Banay-banay | 2000000 | 2018-04-16 |  | 94.81% | 1427821.59 |  | awaiting 50% unreleased . fund of P800,000.00
DA & LGU Equity for Upgrading of Slaughter House Double " A " | Sitio Bulibuli, Brgy. Banga | 30000000 | 2018-03-16 |  | 99.2% | 22839533.59 |  | per CEO: temporarily . stopped; waiting for the . . Remaining 5,000.00 to be . Release
DOLE & LGU Equity to Motorized Fishing Banca & Accessories | Barangay Suba | 502502.4 |  |  |  | 422191.44 |  | on going
Construction of Senior Citizen Center (DSWD) | Barangay Boyco | 1000000 |  |  |  | 0 |  | per CEO: not yet started; procurement process (c/o BAC)
LGU Equity toTech 4ED Project | Bayawan City | 400000 |  |  |  | 0 |  | LGU Equity transferred . from GF (1/26/17)
LGU Equity to Department of Agriculture for High Valued Crops Development | Bayawan City | 656500 |  |  |  | 0 |  | for implementation by DA
DENR to National Greening Program/Comprehesive Site Development (CSD) | Bayawan City | 1242012.49 |  |  |  | 1226025 |  | on going
DENR to Enhance National Greening Program - Seedling Production & Seedling Maintenance activities of its Rubber | Bayawan City | 1675000 |  |  |  | 599137 |  | on going
DENR to Enhance National Greening Program-Green Rubber Budding, Care and Maintenance of Budded Seedlings of the Rubber | Bayawan City | 837500 |  |  |  | 0 |  | for implementation by DA
page 2 of 3
DOH to Completion of Tabuan Barangay Health Station | Barangay Tabuan | 1000000 |  |  |  | 0 |  | per CEO: no site location; no POW
DOH to Completion of Minaba Barangay Health Station | Barangay Minaba | 1000000 | 2019-11-01 |  | 90.52% | 133399.39 |  | per CEO: temporary stopped no roofing materials
DOH Completion/Expansion of Boyco Birthing Facility (BHS)) | Barangay Boyco | 600000 | 2020-04-15 |  | 55% | 280804.22 |  | per CEO: on-going to be recommended for termination
DOH Completion/Expansion of Poblacion Birthing Facility (BHS)) | Barangay Poblacion | 400000 |  |  |  | 0 |  | per CEO: recommended for project termination
DOH to Construction/Completion/ Expansion of Tayawan Birthing Facility (BHS) | Barangay Tayawan | 1500000 | 2020-03-28 |  | 97% | 1256222.26 |  | per CEO: on-going: punchlist (correction of defects)
DOH Construction/Completion/Expansion of Binanigan Birthing Facility (BHS) | Barangay Tayawan | 1500000 | 2020-03-02 |  | 97% | 1245722.02 |  | per CEO: on-going: punchlist (correction of defects)
DOH to Construction/Completion/Expansion of Malabugas Birthing Facility (BHS) | Barangay Malabugas | 1000000 | 2020-03-28 |  | 64% | 505323.83 |  | per CEO: on-going; recommended for project termination
DBM Development of Bayawan City Waterfront Park (Green Green Program) - Phase I | Coastal Road, Bayawan City | 26865678 | 2020-09-17 |  | 58.5% | 11196593.65 |  | on going
NORSU & LGU Equity to "Bayawan LGU-NORSU" Joint Venture for Sports Complex Project | Bayawan City - NORSU | 173900000 | 2020-09-09 |  | 28.12% | 88349672.52 |  | on going
DBM Development of Bayawan City Waterfront Park (Green Green Program) - Phase II | Barangay Suba | 14694897 |  |  |  | 0 |  | No POW
TOTAL |  | 284481373.55 |  |  |  | 141363773.61
568962747.1
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
CORAZON P. LIRAZAN, CPA MBA | [5 empty] | PRYDE HENRY A. TEVES
Local Accountant | [5 empty] | Local Chief Executive
page 3 of 3
.
1370213.01