## sept final
CITY OF BAYAWAN
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION REPORT
As of September 30, 2021
Year |  | Location | Total Cost (per Budget Approp) | Target Start Date | Target Completion Date | Project Status |  | Remarks
[6 empty] | % of Completion | Total Cost Incurred (per Acctg)
CURRENT APPROPRIATION
SOCIAL DEVELOPMENT
2021 | Improvement of Communal Irrigation Systems | Bayawan City | 10305205.13 |  |  |  | 0 | For Implementation
2021 | Development of Water Supply System for Bayawan City "AA" Slaughterhouse & Poultry Dressing Plant | Bayawan City | 6000000 |  |  |  | 0 | -do-
2021 | Development of Water System at Upper Lumantao, Ali-is | Ali-is | 300000 |  |  |  | 0 | -do-
2021 | Development of Barangay Minaba Water System | Minaba | 500000 |  |  |  | 0 | -do-
2021 | Development of Potable Water System at Sitios Guisocon, Bosque and Milagrosa, Brgy. Nangka | Nangka | 1200000 |  |  |  | 0 | -do-
2021 | Water System Development at Sitio Kaayahan, Brgy. San Jose | San Jose | 500000 |  |  |  | 0 | -do-
2021 | Streetlighting Project at Sitio Cansig-id to Buli-buli, Barangay Banga | Banga | 700000 |  |  |  | 0 | -do-
2021 | Solar Streetlighting Project in Purok 1-Lower, Purok 2-Lower and Purok 4-Upper and Lower Cansilong, Brgy. Malabugas | Malabugas | 500000 |  |  |  | 0 | -do-
2021 | Installation of Solar-Powered Streetlighting System at Sitio Kalamungay, Maninhon | Maninihon | 500000 |  |  |  | 0 | -do-
2021 | Installation of Solar-Powered Streetlighting System at Dayhagan to Proper Minaba | Minaba | 300000 |  |  |  | 0 | -do-
2021 | Sitio Electrification Project, Brgy. San Jose | San Jose | 2778571.43 |  |  |  | 0 | -do-
2021 | Installation of Streetlights at Brgy. Ubos | Ubos | 400000 |  |  |  | 0 | -do-
2021 | Construction of 2nd Floor of BCTLDC Workshop Area | Bayawan City | 3500000 |  |  |  | 0 | -do-
2021 | Construction of Health Center at Lower Napit-an, Maninihon | Maninihon | 1178571.43 |  |  |  | 0 | -do-
2021 | Improvement of Barangay Health Center, Suba | Suba | 300000 |  |  |  | 0 | -do-
2021 | Improvement of Barangay Health Center, Tinago | Tinago | 600000 |  |  |  | 0 | -do-
2021 | Improvement of Barangay Health Substation at Pulangyuta, Kalamtukan | Kalamtukan | 500000 |  |  |  | 0 | -do-
2021 | Improvement of Tabuan Health Center | Tabuan | 400000 |  |  |  | 0 | -do-
2021 | Fabrication of Steel Scaffolding and Home Building System | Bayawan City | 5000000 |  |  |  | 0 | -do-
2021 | Construction of Barangay Livelihood Training Center, Cansumalig | Casumalig | 300000 |  |  |  | 0 | -do-
2021 | Construction of Barangay Gymnasium and Evacuation Center, Dawis (Phase 2) | Dawis | 1678571.43 | 2021-07-01 | 2021-08-31 |  | 1320 | On going
2021 | Construction of Multi-Purpose Building, Brgy. Minaba | Minaba | 4800000 |  |  |  | 0 | For Implementation
2021 | Construction of Barangay Multi-Purpose Building, San Jose | San Jose | 1000000 |  |  |  | 0 | -do-
2021 | Construction of Multi-Purpose Hall, Brgy. Tayawan (Phase 4) | Tayawan | 1678571.43 |  |  |  | 0 | -do-
2021 | Improvement of Barangay Multi-Purpose Hall (Phase 1), San Roque | San Roque | 1000000 |  |  |  | 0 | -do-
2021 | Construction of Barangay Multi-Purpose Hall (Phase III), Cansumalig | Casumalig | 1678571.43 |  |  |  | 0 | -do-
2021 | Construction of Multi-Purpose Hall at Niludhan, Dawis | Dawis | 500000 | 2021-07-01 | 2021-08-15 |  | 36629.92 | On going
2021 | Construction of Multi-Purpose Building (Phase III), Brgy. Poblacion | Poblacion | 1678571.43 |  |  |  | 0 | For Implementation
2021 | Construction of Multi-Purpose Hall at Niludhan, Dawis | Dawis | 600000 |  |  |  | 0 | -do-
| Total Projects for Social Development - Current Appropriation |  | 50376633.71 |  |  |  | 37949.92
ECONOMIC DEVELOPMENT
2021 | Loan Amortization |  | 60000000 |  |  |  | 58459969.81 | Per SAAOB
2021 | Lot Acquisition for Auction Market |  | 500000 |  |  |  | 0 | For Implementation
2021 | Concreting of Maninihon-Cansumalig-San Isidro FMR | Bayawan City | 10000000 |  |  |  | 0 | -do-
2021 | Concreting of Gamao-Ohot-Duyanduyan FMR | Narra | 10000000 |  |  |  | 0 | -do-
2021 | Concreting of Pulangyuta-Lapay FMR | Bayawan City | 10000000 |  |  |  | 0 | -do-
2021 | Concreting of Tabuan-Ali-is FMR | Bayawan City | 10000000 | 2021-05-01 | 2021-12-15 |  | 3875937.92 | On going
2021 | Concreting of Minaba-San Miguel FMR | Bayawan City | 10000000 |  |  |  | 0 | For Implementation
2021 | Concreting of Minaba-Tayawan-Kalumboyan FMR | Bayawan City | 10000000 | 2021-04-01 | 2022-01-15 |  | 3767670.26 | On going
2021 | Concreting of Tabuan-Banaybanay-Lapay-Bugay FMR | Bayawan City | 10000000 |  |  |  | 0 | For Implementation
2021 | Concreting of San Roque-San Miguel FMR | Bayawan City | 11284948.4 |  |  |  | 0 | -do-
2021 | Road Concreting from Barangay Proper to Kalamtukan Elementary School | Kalamtukan | 1678571.43 | 2021-04-01 | 2021-06-14 |  | 789657.63 | On going
2021 | Rehabilitation of Farm to Market Roads in Various Sitios, Brgy. Kalumboyan | Kalumboyan | 1678571.43 |  |  |  | 0 | For Implementation
2021 | Construction of Farm to Market Road at Sitio Upper Pamu-at, Brgy. San Isidro | San Isidro | 500000 | 2021-05-01 | 2021-07-15 |  | 5304.57 | On going
2021 | Road Concreting Connecting Gabi 1 to Gabi 2, Brgy. Ubos | Ubos | 500000 | 2021-06-01 | 2021-06-30 |  | 104735.72 | -do-
2021 | Road Concreting along Refilling Station at Gomez St., Brgy. Ubos | Ubos | 500000 |  |  |  | 0 | For Implementation
2021 | Road Concreting at Purok Sampaguita, Barangay Villareal | Villareal | 1678571.43 | 2021-05-15 | 2021-07-30 |  | 1009719.51 | On going
2021 | Road Improvement from National Highway to Purok Balatong I and Purok Balatong II, Manduao | Manduao | 1900000 | 2021-04-01 | 2021-12-15 |  | 4978.6 | -do-
2021 | Concreting of Dawis-Lapay FMR | Bayawan City | 10000000 |  |  |  | 0 | For Implementation
2021 | Concreting of Nangka-Narra FMR | Bayawan City | 10000000 | 2021-10-01 | 2022-05-31 |  | 64132.5 | On going
2021 | Construction of Flat Slab Bridge at Sitio Upper Pamu-at, San Isidro | San Isidro | 1000000 | 2021-07-01 | 2021-10-15 |  | 594453.09 | -do-
2021 | Construction of Barangay Public Market Stalls (Phase 1), Brgy. Banaybanay | Banaybanay | 1000000 | 2021-07-01 | 2021-07-16 |  | 189924.98 | -do-
2021 | Purchase of 2 Units Rice-Corn Combine Harvester |  | 4600000 |  |  |  | 4300000
2021 | Fabrication of 4 Units Flatbed Dryer with Shed |  | 4800000 |  |  |  | 0
2021 | Purchase of 1 Unit Backhoe Loader |  | 10000000 |  |  |  | 0
| Total Projects for Economic Development - Current Appropriation |  | 191620662.69 |  |  |  | 73166484.59
ENVIRONMENTAL MANAGEMENT
2021 | Improvement of Drainage Canal at Amparo's Village, Brgy. Villareal | Villareal | 700000 | 2021-06-01 | 2021-08-30 |  | 226860.66 | On going
2021 | De-silting of Pagtigaon Creek at Barangay Maninihon | Maninihon | 500000 | 2021-07-01 | 2021-08-15 |  | 1497.09 | -do-
| Total Projects for Environmental Management - Current Appropriation |  | 1200000 |  |  |  | 228357.75
| TOTAL DF - CURRENT APPROPRIATION |  | 243197296.4 |  |  |  | 73432792.26
CONTINUING APPROPRIATION
SOCIAL DEVELOPMENT
2012 | Improvement of Bayawan City Boulevard (Landscaping fronting GK Village) | Villareal | 535115.83 | 2013-08-01 | 2014-03-15 | 100% | 495907.52
2013 | Construction of Sports Center and Children's Playground, Phase 3 | Suba | 3000000 | 2013-03-18 | 2015-05-30 | 100% | 2668470.08
2013 | Improvement of Water System for 21 Rural Barangays | Bayawan City | 568710 | 2016-07-01 | 2017-07-31 | 100% | 468013.78
2015 | Construction of Covered Court at BCsTEC, Phase II | Cabcabon, Banga | 3008100 | 2013-10-01 | 2017-06-30 | 100% | 2783489.42
2015 | Rehabilitation of GK Septic Tanks | Villareal | 3104400 | 2013-11-18 | 2020-12-31 | 2% | 77968.88
2015 | Construction of Evacuation Center, Brgy. San Miguel | San Miguel | 800000 | 2016-01-02 | 2019-10-31 | 100% | 753942.58
2015 | Const. of GK Village Perimeter Fence | Villareal | 2000000 | 2019-01-10 | 2020-12-31 | 100% | 1716184.88
2015 | Water System Development @ Sitio Camague to Cabiguhan, Brgy Banaybanay | Banaybanay | 303389.8 | 2017-02-16 | 2020-12-31 | 50% | 206913.03
2016 | Rehabilitation of Health Center & Const. of Lying-in Facility, Brgy. Poblacion, Phase 2 | Poblacion | 500000 | 2016-09-16 | 2017-06-30 | 100% | 320188.77
2016 | Construction of Day Care Centers in Nangka and Napit-an/Rehabilitation of Day Care Centers in Minaba, Narra, Purok 4 Tayawan | Nangka, Napit-an, Minaba, Narra, Tayawan | 5000000 | 2017-01-06 | 2020-12-31 | 52% | 1608791.55
2016 | Improvement of CICL Center Faciltities | Banga | 975000 | 2017-11-16 | 2019-03-31 | 100% | 810122.28
2016 | Completion of Paglaum Center at Cabcabon | Cabcabon | 500000 | 2016-10-16 | 2018-05-31 | 100% | 374922.29
2016 | Completion of Women's Multi-purpose Center | Boyco | 1000000 | 2016-12-01 | 2018-11-30 | 100% | 855347.45
2016 | Construction of Women's Detention Cell | Banga | 400000 | 2019-07-29 | 2019-10-30 | 53% | 223432.29
2016 | Construction of Women's Facilities in Evacuation Center | Various Brgys. | 200000 | 2019-07-16 | 2020-03-31 | 100% | 168303.43
2016 | Const. of Comfort Rooms in 13 Evacuation Ctrs. | Various Brgys. | 1054174.83 | 2019-04-30 | 2018-02-28 | 100% | 1056488.39
a. Banga Central School
b. BCSTEC Elementary & Highschool
c. Malabugas Highschool
d. Nangka Elementary School
e. Guisocon Elementary School
f. Atilano Cabangal Memorial Highschool
g. Tavera Elementary School
h. Dean Felix Gaudiel Memorial Elementary School
i. H. Bido Jordan Elementary School
j. Bayawan National Highschool
k. Maninihon Elementary & Highschool
l. H. Bido Jordan Highschool School
m. SLGTMES
2016 | Improvement of Covered Court/Evacuation Ctr., Bry. Banga | Banga | 500000 | 2019-03-16 | 2020-03-31 | 100% | 435324.84
2016 | Const. of Evacuation Ctr., Brgy. San Roque | San Roque | 500000 | 2017-06-16 | 2019-06-30 | 100% | 361521.48
2016 | Const. of Covered Court/Evacuation Ctr., Bry. Suba | Suba | 500000 | 2016-12-16 | 2017-05-31 | 100% | 454964.53
2016 | Const. of Multi-Purpose Bldg. for Evacuation Ctr., Brgy Villareal | Villareal | 500000 | 2019-01-05 | 2018-11-30 | 100% | 436829.46
2016 | Establishment of Youth Development Center | Bayawan City | 5000000 | 2017-06-15 | 2018-09-01 | 100% | 4000896.6
2016 | Rehabilitation of San Isidro Water Supply System | San Isidro | 350000 | 2017-02-01 | 2017-03-31 | 100% | 189138.38
2016 | Const. of Water Tank & Pipeline at Tabuan Brgy Proper | Tabuan | 500000 | 2017-05-01 | 2018-05-31 | 99.5% | 424113.31
2016 | Construction of Tayawan Water System | Tayawan | 300000 | 2017-01-06 | 2020-02-29 | 95% | 267009.23
2016 | Installation of Electrical System (Sitio Napit-an, Brgy Maninihon & Zamora Streets, Brgy. Suba) | Suba | 1500000 | 2016-11-15 | 2018-08-31 | 100% | 1439250.62
2016 | Purchase of Transforments & Primary Metering @ New Gov't. Center | Banga | 2545000 | 2016-11-24 | 2016-11-29 | 100% | 2540000
2016 | Installation of Secondary Line Feeder @ New Gov't. Center | Banga | 800000 | 2016-02-13 | 2018-07-15 | 100% | 669519.56
2016 | Establishment of Street Lighting Facilities - 2016 | Various Brgys. | 400000 | 2019-03-15 | 2020-04-15 | 100% | 314630
2016 | Installation of Street Lightings at Brgy Proper, Villasol | Villasol | 140000 | 2017-10-02 | 2017-10-30 | 100% | 133422.04
2017 | Establishment of Montessori-Type Early Child Care Development Centers | Various Brgys
2017 | a. Establishment of Montessori-Type Early Child Care Development Centers Phase 2 | Boyco | 2289000 | 2017-12-16 | 2020-02-10 | 100% | 1310863.71
2017 | b. Establishment of Montessori-Type Early Child Care Development Centers | Poblacion | 1211000 | 2018-01-01 | 2018-11-30 | 100% | 745005.92
2017 | Development of Tabuan People's Park | Tabuan | 2000000 | 2018-12-31 | 2020-04-20 | 100% | 1991861.08
2017 | Improvement of Barangay Health Center Lying-In Clinic, Brgy. Malabugas | Malabugas | 1678571.43 | 2019-01-10 | 2020-12-31 | 92% | 734631.51
2017 | Improvement of Barangay Health Center & Lying-in Clinic, Brgy. Manduao | Manduao | 100000 |  |  |  | 0
2017 | Construction of Covered Court and Evacuation Center, Brgy. Pagatban | Pagatban | 1728571.43 |  |  |  | 0
2017 | Improvement of Evacuation Center and Multi-Purpose Building, Brgy. Poblacion | Poblacion | 878571.43 |  |  |  | 0
2017 | Construction of New Day Care Center at Brgy. Poblacion | Poblacion | 800000 |  |  |  | 0
2017 | Construction of Lying-In Clinic, Brgy. San Isidro | San Isidro | 1178571.43 | 2019-02-24 | 2019-12-15 | 99.5% | 1177768.28
2017 | Improvemen of Health Center and Lying-in Clinic, Brgy.San Roque | San Roque | 1678571.43 |  |  |  | 0
2017 | Improvement of Barangay Health Center, Brgy. Tinago | Tinago | 600000 |  |  |  | 0
2017 | Construction of Multi-Purpose Center for Senior Citizens, Brgy. Villasol | Bayawan City | 50000 |  |  |  | 0
2017 | Improvement of Barangay Health Center, Brgy. San Jose | San Jose | 60000 |  |  |  | 0
2017 | Renovation of Barangay Health Center at Brgy. Tayawan | Tayawan | 150000 |  |  |  | 0
2017 | Renovation of Day Care Center, Brgy. Tayawan | Tayawan | 100000 |  |  |  | 0
2017 | Water System Development Project at Sitio Upper Camandagan, Brgy. Maninihon | Maninihon | 1000000 | 2019-05-01 | 2020-10-31 | 100% | 647344.67
2017 | Improvement of Multi-Purpose Gymnasium and Evacuation Center, Brgy. Maninihon | Maninihon | 678571.43 | 2019-01-25 | 2020-02-15 | 100% | 677054.7
2017 | Establishment of Barangay Water Refilling Station, Brgy. Nangka | Nangka | 678571.43 |  |  |  | 0
2017 | Improvement of Covered Court for Evacuation Center, Brgy Suba | Suba | 1678571.43 |  |  |  | 0
2017 | Improvement/Rehabilitation of Water Systems for Various Barangays | Various Brgys | 934500 | 2019-01-31 | 2020-05-31 | 100% | 626811.13
2017 | Installation of Water Refilling Stations at Various Barangays | Various Brgys | 2200000 | 2019-01-21 | 06/31/20 | 48% | 1054599.9
2017 | Construction of Multi-Purpose Pavement at Sitio Bolo, Brgy. Villasol | Villasol | 600000 | 2018-02-16 | 2018-06-30 | 100% | 563174.77
2017 | Construction of Multi-Purpose Building in Barangay Tayawan | Tayawan | 900000 |  |  |  | 0
2017 | Construction of Multi-Purpose Building in Barangay San Jose | San Jose | 900000 |  |  |  | 0
2017 | Construction of Drainage Canal at Cansumalig High School | Cansumalig | 150000 | 2017-12-16 | 2018-03-30 | 100% | 126833.17
2017 | Improvement of Water Systems of Guintanaan Tayawan | Tayawan | 100000 | 2018-01-31 | 2018-02-14 | 3% | 83473.61
2017 | Installation of Solar-Driven Water System for Catumbalan, Minaba | Minaba | 100000 |  |  |  | 0
2017 | Installation of Solar-Driven Water Systems for Napo, Brgy. Tayawan | Tayawan | 50000 |  |  |  | 0
2017 | Construction of Multi-Purpose Pavement at Sitio Upper Manlubid, Ali-is | Ali-is | 50000 |  |  |  | 0
2017 | Construction of Multi-Purpose Pavement at Inner Canabuan, Minaba | Minaba | 300000 | 2018-02-16 | 2018-06-30 | 100% | 286328.7
2017 | Improvement of Water System at Sitio Pag-awitan, Brgy. Ali-is | Ali-is | 500000 |  |  |  | 0
2017 | Installation of Electrical System in Sitio Buli-buli, Brgy. Banga | Banga | 60000 | 2019-01-02 | 2019-02-28 | 100% | 43514.9
2017 | Improvement of Water System, Brgy. Ubos | Ubos | 145000 | 2018-01-06 | 2018-06-15 | 100% | 136216.2
2017 | Improvement of Water System at Brgy. Villasol | Villasol | 70000 |  |  |  | 0
2017 | Construction of Multi-Purpose Pavement at Sitio Ponong, Brgy. Villasol | Villasol | 100000 | 2019-07-31 | 2020-05-31 | 100% | 90090.89
2017 | Installation of Electrical System at Sitio Malampa, Brgy. Pagatban | Pagatban | 50000 | 2018-01-06 | 2018-06-30 | 100% | 44857.31
2017 | Installation of Electrical System in Brgy. Malabugas | Malabugas | 50000 | 2018-03-16 | 2018-04-30 | 100% | 46024.73
2017 | Improvement of Canabuan Water System, Brgy. Minaba | Minaba | 200000 | 6/31/2018 | 2020-12-31 | 30% | 63749.99
2017 | Improvement of Barangay Multi-Purpose Hall, Brgy. Ali-is | Ali-is | 200000 |  |  |  | 0
2017 | Construction of Multi-Purpose Pavement at Purok 2, Brgy. Kalamtukan | Kalamtukan | 250000 | 2018-01-16 | 2018-06-30 | 100% | 224233.82
2017 | Installation of Street Lights at Purok 4, Cansilong, Brgy. Malabugas | Malabugas | 100000 | 2018-03-16 | 2018-05-31 | 100% | 90521.66
2017 | Installation of Electrical System for Purok Ipil-Ipil, Brgy. San Roque | San Roque | 200000 |  |  |  | 0
2017 | Electrification Project for Various Barangays | Various Brgys | 10000 | 2018-01-06 | 2018-06-15 | 100% | 9060.49
2017 | Installation of Deep Well at Atilano Cabangal High School, Brgy. Nangka | Nangka | 250000 | 2018-11-15 | 2020-12-31 | 4% | 10606.87
2017 | Installation of Water System at Brgy. Pagatban | Pagatban | 50000 | 2018-03-16 | 2019-06-30 | 100% | 41977.04
2017 | Installation of Water System at Brgy. Poblacion | Poblacion | 70000 | 2018-03-01 | 2018-03-15 | 100% | 28933.33
2017 | Improvement of Multi-Purpose Gym & Evacuation Center, Brgy. San Isidro | San Isidro | 495000 | 2019-01-25 | 2019-07-23 | 100% | 303934.68
2017 | Construction of Multi-Purpose Pavement, Brgy. Dawis | Dawis | 340000 | 2017-11-01 | 2018-02-28 | 100% | 327529.86
2017 | Construction of Multi-Purpose Building at Relocation Site, Brgy. San Miguel | San Miguel | 500000 |  |  |  | 0
2017 | Construction of CICL at BADC Magsulay, Barangay Narra | Narra | 1000000 |  |  |  | 0
2017 | Const. of Livelihood Center for Women at Brgy Villasol Proper | Villasol | 100000 |  |  |  | 0
2017 | Construction of Multi-purpose Pavement at Sitio Kaayahan (Phase 1) | Sitio Kaayahan | 100000 | 2017-07-31 | 2020-03-31 | 100% | 92984.26
2017 | Completion of Multi-purpose Pavement at Sitio Tangistangisan | Sitio Tangistangisan | 330000 | 2018-01-02 | 2018-06-30 | 100% | 306358.29
2017 | Improvement of Cabatangan-Tavera Water System | Nangka | 154784.58 | 2019-01-16 | 2019-03-31 | 100% | 133057.22
2017 | Establishment of Early Child Development Center | Bayawan City | 2300000 | 2018-03-31 | 2019-12-31 | 99.79% | 2107332.3
2017 | Construction of Multi-Purpose Pavement at Brgy. Ali-is | Ali-is | 580000 | 2017-12-16 | 2018-06-30 | 100% | 549090.35
2017 | Construction of Multi-Purpose Pavement at Sitio Guinhamogan, Brgy. Cansumalig | Cansumalig | 559523.81 | 2018-04-18 | 2018-07-31 | 100% | 519399.55
2017 | Construction of Multi-Purpose Pavement at Sitio Guintalasan, Brgy. Cansumalig | Cansumalig | 559523.81 | 2018-09-15 | 2020-09-15 | 100% | 299477.66
2017 | Improvement of Multi-Purpose Building at Brgy. Dawis | Dawis | 678571.43 |  |  |  | 0
2017 | Construction of Multi-Purpose Pavement at Sitio Cogon, Brgy. Kalamtukan | Kalamtukan | 500000 | 2018-01-16 | 2018-06-30 | 100% | 471707.68
2017 | Improvement of Multi-Purpose Building, Brgy. Tinago | Tinago | 1128571.43 |  |  |  | 0
2017 | Construction of Multi-Purpose Pavement at Sitio Manghakayhakay, Brgy. Villasol | Villasol | 600000 | 2017-12-16 | 2018-03-31 | 100% | 560025.05
2017 | Purchase of 50 KVA Transformer for BCTLDC |  | 500000 |  |  |  | 0
2017 | Construction of City Health Office Building |  | 1000000 |  |  |  | 0
2017 | Construction of Workshop Area for Bayawan City Technology & Livelihood Development Center (BCTLDC) |  | 3000000 | 2019-05-17 | 2019-10-31 | 100% | 2988556.83
2017 | Purchase of Workshop Tools and Equipment for BCTLDC:
Furniture & Fixtures
2017 | 3 units Exhaust Fan |  | 4500 |  |  |  | 0
2017 | 3 units Industrial Fan |  | 19656 |  |  |  | 0
2017 | 4 units White Board with Movable Stand |  | 11000 |  |  |  | 0
2017 | 3 units White Board (4x8x3/4) |  | 9900 |  |  |  | 0
Machinery
2017 | 18 units Arc Welding Machine AC/DC & Acc |  | 698040 |  |  |  | 0
Communication Equipment
2017 | 1 unit LCD projector |  | 26000 |  |  |  | 0
Disaster Response & Rescue Equipment
2017 | 4 units Fire Extinguishers |  | 12364 |  |  |  | 0
Military, Police & Security Equipment
2017 | 1 Set Security Equipment Access Control (CCTV) |  | 29845 |  |  |  | 0
Other Machinery & Equipment
2017 | 6 units Work Bench w/ Bench Vice on 4 Corners |  | 204000 |  |  |  | 0
2017 | 25 sets Combination Spanner (6mm to 24 mm) |  | 80000 |  |  |  | 0
2017 | 12 units Blow Torch |  | 18000 |  |  |  | 0
2017 | 12 units Clamp on Meter |  | 36000 |  |  |  | 0
2017 | 6 units Portable Electric Drill |  | 30000 |  |  |  | 0
2017 | 6 units Portable Planer |  | 51600 |  |  |  | 0
2017 | 6 units Portable Circular Saw |  | 47220 |  |  |  | 0
2017 | 25 pcs Welding Positioners |  | 96250 |  |  |  | 0
2017 | 6 units Electrode Oven |  | 24000 |  |  |  | 0
2017 | 25 units Portable Disc Grinder |  | 78750 |  |  |  | 0
2017 | 6 units Pipe Threader 1/2-2" |  | 343200 |  |  |  | 0
2017 | 6 units Pipe Bender |  | 26400 |  |  |  | 0
2017 | 6 units Heat Gun 1200 watts |  | 18900 |  |  |  | 0
2017 | 6 units Bolt Cutter |  | 7680 |  |  |  | 0
2017 | 12 pcs Box Wrench |  | 58800 |  |  |  | 0
2017 | 12 pcs Wire Splicer |  | 25320 |  |  |  | 0
2017 | 12 pcs Wire Stripper |  | 25320 |  |  |  | 0
2017 | 12 units Electric Drill |  | 58800 |  |  |  | 0
2017 | 12 units Portable Grinder |  | 52500 |  |  |  | 0
2017 | 6 units Pipe Cutter (1/2"-1") |  | 31590 |  |  |  | 0
2017 | 3 units Manual Pipe Threader (1/2", 3/4", 1") |  | 33705 |  |  |  | 0
2017 | 3 units Fusion Machine (20mm-32mm) |  | 34020 |  |  |  | 0
2017 | 4 units Electric Grinder (4") |  | 20520 |  |  |  | 0
2017 | 12 units Angle Grinder |  | 61560 |  |  |  | 0
2017 | 2 units Labelling Machine |  | 2200 |  |  |  | 0
2017 | 6 units Insulation Resistance Tester |  | 9900 |  |  |  | 0
2017 | 6 units Earth Resistance Tester |  | 13200 |  |  |  | 0
2017 | 4 units Pedestal/Bench Grinding Machine |  | 9400 |  |  |  | 0
2017 | 10 units Panel Board with 70 amp main & 4 |  | 34450 |  |  |  | 0
2017 | 25 pcs Electrician Pliers |  | 66250 |  |  |  | 0
2017 | Other Property, Plant & Equipment
2017 | 3 units Wheelbarrow |  | 6600 |  |  |  | 0
2017 | 6 sets Oxy-Acetylene/Oxy-LPG Cutting Outfit |  | 72000 |  |  |  | 0
2017 | 6 units Plastic Drum (200 liters) |  | 10560 |  |  |  | 0
2018 | Purchase of Lot for Multi-Purpose Hall at Sitio Cambulo. Banga | Banga | 600000 |  |  |  | 0
2018 | Water System Development at Bugay Proper | Bugay | 500000 | 2019-04-01 | 2020-12-31 | 100% | 148710.4
2018 | Development of Water System at Brgy. Villareal | Villareal | 1000000 | 2019-08-12 | 2020-11-30 | 100% | 327600
2018 | Installation of Street Lighting from Purok 1 to Purok IV, Brgy. Tayawan | Tayawan | 500000 | 2018-06-21 | 2020-12-31 | 100% | 389603.12
2018 | Improvement of Barangay Plaza and Children's Park, Tayawan | Tayawan | 500000 | 2018-06-21 | 2020-12-31 | 100% | 215789.75
2018 | Establishment of Early Child Care Dev't Centers: | Bayawan City
2018 | a. Brgy. Villareal | Villareal | 5000000 | 2018-06-21 | 2020-03-31 | 99% | 4870018 | On going
2018 | b. Brgy. Malabugas | Malabugas | 5000000 | 2018-06-21 | 2019-11-15 | 100% | 4874380.13
2018 | Construction of Day Care Center at Sitio Mantapi, Nangka | Nangka | 578571.43 | 2018-12-01 | 2020-12-01 | 56% | 373352.46
2018 | Improvement of Barangay Health Center & Lying-In Clinic, Brgy. Malabugas | Malabugas | 0 |  |  |  | 0
2018 | Construction of Health Center at Sitio Mantapi, Nangka | Nangka | 500000 | 2019-11-12 | 2020-11-12 | 22% | 110023.07
2018 | Construction of Bleachers at Barangay Evacuation Center, Ali-is | Ali-is | 678571.43 | 2018-01-04 | 2019-04-30 | 100% | 555739.56
2018 | Improvement of Barangay Multi-Purpose Building, Banaybanay | Banaybanay | 1000000 |  |  |  | 0
2018 | Improvement of Barangay Multi-Purpose Hall, Brgy. Boyco | Boyco | 1678571.43 |  |  |  | 0
2018 | Construction of Barangay Multi-Purpose Building, Cansumalig | Cansumalig | 1300000 | 2019-07-16 | 2020-11-30 | 100% | 1009687.4
2018 | Improvement of Barangay Multi-Purpose Building, Maninihon | Maninihon | 1000000 | 2019-11-01 | 2020-08-15 | 100% | 793802.54
2018 | Construction of Multi-Purpose Pavement at Sitio Mantapi, Nangka | Mantapi, Nangka | 600000 | 2018-01-07 | 2018-12-31 | 100% | 546309.58
2018 | Construction of Barangay Multi-Purpose Building, Narra | Narra | 1000000 |  |  |  | 0
2018 | Construction of Concrete Perimeter Fence of Covered Court & Evacuation Center, Brgy. Pagatban | Pagatban | 100000 | 2018-01-07 | 2018-08-31 | 100% | 86496.06
2018 | Construction of Multi-Purpose Building, Brgy. San Isidro (Phase 2) | San Isidro | 1078571.43 | 2019-01-08 | 2020-04-15 | 100% | 896146.5
2018 | Construction of Children and Women's Crisis Center, Brgy. Suba | Suba | 600000 | 2018-01-01 | 2018-03-17 |  | 219987.11
2018 | Improvement of Multi-Purpose Hall, Brgy. Suba | Suba | 578571.43 |  |  |  | 0
2018 | Construction of Multi-Purpose Hall, Brgy. Tinago | Tinago | 3957142.86 | 2019-07-01 | 2020-12-31 | 98% | 3660145.16 | On going
2018 | Improvement of Multi-Purpose Hall, Banga | Banga | 2078571.43 |  |  |  | 0
2019 | Construction of Multi-Purpose Pavement at Sitio -Upper Pinangimnan | San Jose | 839285.7 | 2020-04-15 | 2020-08-15 | 100% | 300623.45
2019 | Construction of Multi-Purpose Pavement at Sitio Pitogo 1 | San Jose | 839285.73 | 2020-06-15 | 2020-10-16 | 100% | 309875.17
2019 | Lot Acquisition for Dita Relocation | Tabuan | 5000000 |  |  |  | 0
2019 | Construction & Installation of Water Supply Systems for Barangays Malabugas, San Roque, Minaba, San Miguel and Tayawan | Various Brgys. | 11000000 |  |  |  | 0
2019 | Construction of Day Care Center, Brgy San Miguel | Bayawan City | 400000 | 2019-07-16 | 2019-09-30 | 100% | 281516.27
2019 | Construction of Concrete Fence of Minaba Elementary School | Minaba | 500000 | 2019-05-16 | 2020-03-31 | 90% | 253896.23
2019 | Construction of Concrete Fence of Canabuan Elementary School | Minaba | 500000 | 2019-01-06 | 2020-03-31 | 90% | 262890.06
2019 | Construction of Concrete Fence of Minaba High School | Minaba | 678571.43 | 2019-01-06 | 2020-03-31 | 90% | 256697.91
2019 | Construction of Concrete Fence of Bolirocon Elementary School, San Isidro | Bolirocon, San Isidro | 278571.43 | 2019-01-08 | 2020-03-31 | 100% | 215973.4
2019 | Construction of Perimeter Fence at San Roque Elementary School | San Roque | 578571.43 | 2019-01-06 | 2020-03-31 | 90% | 342555.5
2019 | Completion of Lapay Multi-Purpose Pavement | Dawis | 360000 | 2019-06-16 | 2019-08-31 | 100% | 274686.95
2019 | Construction of Barangay Multi-Purpose Building, Nangka | Nangka | 1678571.43 | 2019-06-30 | 2020-04-30 | 79% | 1229360.71 | On going
2019 | Construction of 2-Storey Multi-Purpose Building, Brgy. Poblacion | Poblacion | 1678571.43 | 2019-06-30 | 2020-06-30 | 35.44% | 1315771.87
2019 | Construction of Multi-Purpose Building, Barangay San Isidro (Phase 3) | San Roque | 1000000 | 2019-09-30 | 2020-07-31 | 95% | 409995.84 | On going
2020 | Water System Development for Sitio Balastro-Pulang Yuta-Tower, Brgy. Kalamtukan | Kalamtukan | 1678571.43 | 2020-07-01 | 2020-10-05 |  | 1232722.08
2020 | Water System Development at Sitio Calumpang, Kalumboyan | Kalumboyan | 500000 | 2020-07-01 | 2020-08-17 |  | 249553.4
2020 | Installation of Water Supply System at Sitios Bantolinao, Patag and Proper I, Brgy. Tabuan | Tabuan | 500000 | 2020-07-01 | 2020-10-05 |  | 2960.4
2020 | Improvement of Water Supply System at BCWMEC | Maninihon | 600000 |  |  |  | 0
2020 | Installation of Streetlighting System at Bulibuli, Banga | Banga | 500000 |  |  |  | 0
2020 | Barangay Electrification Project, San Jose | San Jose | 858571.43 |  |  |  | 0
2020 | Electrification Project at Purok Sambag, San Roque | San Roque | 600000 |  |  |  | 0
2020 | Construction of Bunker Silo | Bayawan City | 1000000 | 2020-08-01 | 2020-12-31 |  | 343510.56
2020 | Construction of Barangay Multi-Purpose Hall (Phase II), Cansumalig | Cansumalig | 1678571.43 | 2020-07-01 | 2020-12-20 | 62% | 657726.03 | On going
2020 | Construction of Multi-Purpose Hall at Niludhan, Dawis | Dawis | 700000 | 2020-07-01 | 2020-09-13 | 88% | 308608.66 | -do-
2020 | Construction of Barangay Nangka Multi-Purpose Hall (Phase II) | Bayawan City | 2478571.43 | 2020-10-01 | 2021-03-30 | 78% | 1393149.34 | -do-
2020 | Construction of Multi-Purpose Building (Phase II), Brgy. Poblacion | Poblacion | 1678571.43 | 2020-10-01 | 2021-02-12 |  | 924035.76
2020 | Construction of Multi-Purpose Building at Sitio Bia-as, San Miguel | San Miguel | 700000 | 2020-07-01 | 2020-09-25 | 77% | 570607.95
2020 | Construction of Multi-Purpose Hall, Brgy. San Miguel (Phase V) | San Miguel | 500000 | 2020-07-01 | 2020-08-29 | 100% | 595022.73
2020 | Improvement of Barangay Multi-Purpose Building, Suba | Suba | 1678571.43 | 2020-10-01 | 2021-01-30 |  | 530379.71
2020 | Construction of Barangay Multi-Purpose Hall, Tinago (Phase 4) | Tinago | 3878571.43 | 2020-10-01 | 2021-05-28 | 85% | 1912335.72 | On going
2020 | Construction of Multi-Purpose Hall, Brgy. Ubos (Phase 1) | Ubos | 2080000 | 101-1-20 | 2021-04-15 | 88% | 1063431.58 | -do-
| Total Projects for Social Development - Continuing Appropriation |  | 157307936.99 |  |  |  | 80085776.9
ECONOMIC DEVELOPMENT
2011 | Const. of Hanging Bridge at Sitio Tiki, Kalumboyan (Phase 3) | Kalumboyan | 700000 | 2011-07-01 | 2020-12-31 | 100% | 546410.34
2012 | Construction of Slaughterhouse | Suba | 10000000 | 2016-09-16 | 2018-03-31 | 100% | 7818835.46
2013 | Fabrication of Distillation Chamber for Essential Oil Production | Banga | 150000 |  |  |  | 0
2014 | Construction of Bayawan City Boulevard/Phase 2 | Bayawan City | 1000000 | 2014-08-16 | 2014-10-30 | 100% | 936750.81
2014 | Major Repair - Construction & Heavy Equipment | Motorpool Area | 10000000 | 2014-06-11 | 2020-12-31 | 22% | 2242763
2014 | Road Surfacing from Sitio Binanigan to Sitio Guintana-an, Brgy. Tayawan, Phase 1 | Tayawan | 500000 | 2016-03-16 | 2020-04-01 | 100% | 451875.74
2014 | Construction of Water System-Crusher Kalumboyan | Kalumboyan | 500000 | 2015-06-01 | 2016-06-30 | 100% | 182582.35
2015 | Const. of Motorpool Building, Phase 1, Cabcabon | Cabcabon, Banga | 8483700 | 2015-07-06 | 09/31/17 | 100% | 7893686.98
2015 | Purchase of Various Heavy Equipment |  | 3476406.99 |  |  |  | 0
2015 | Reblocking of Concrete Pavement at Villareal-Cansumalig-San Isidro FMR, Phase 2 | Bayawan City | 500000 | 2015-06-01 | 2015-06-30 | 100% | 457677.34
2015 | Construction of Gomez Street Extension | Bayawan City | 3000000 | 2016-03-16 | 2018-06-30 | 100% | 1148517.88
2015 | Construction of Access Road at Bayawan East, | Bayawan City | 2053659.56 | 2015-04-01 | 2016-03-15 | 100% | 1967337.73
2015 | Road Surfacing of Sitio Hag-um and Sitio Mambunot, Brgy. Tayawan, Phase 1 | Tayawan | 500000 | 2016-03-16 | 2020-02-15 | 100% | 463402.41
2015 | Rehabilitation of FMR at Sitio Tubod, Brgy. Tabuan | Tubod, Tabuan | 100000 | 2015-10-01 | 2016-03-15 | 100% | 56654.12
2015 | Rehabilitation of Pulangyuta-Lapay FMR | Bayawan City | 2014400 | 2015-09-16 | 2017-03-31 | 100% | 2008455.26
2015 | Improvement of Bayawan City Wet Public Market Building-1 (84 units) | Bayawan City | 104400 |  |  |  | 0
2015 | Road Opening Rizal St. from Zamora St. to River Bank | Bayawan City | 42000 |  |  |  | 0
2016 | Improvement of Agricultural Dev. Ctr. (ADC), Cansumalig, Phase 2 | Cansumalig | 400000 | 2017-06-01 | 2018-06-30 | 100% | 348687.17
2016 | Const. of Rain Collector at Brgy. San Isidro | San Isidro | 150000 | 2017-12-16 | 2018-05-31 | 100% | 137210.67
2016 | Fish Farm Development Program |  | 900000 |  |  |  | 0
2016 | Renovation of the Integrated Business Center(IBC) Building | Villareal | 8000000 | 2017-04-27 | 2020-02-15 | 100% | 7449981.63
2016 | Pilot Livestock Silage Stocking Project - Establishment of Stockroom |  | 560000 | 2017-05-16 | 2017-08-10 | 96% | 427042.2
2016 | Other Property, Plant and Equipment |  | 400000 |  |  |  | 0
2016 | Establishment of Bayawan Farmers' Market in Dumaguete |  | 5000000 | 2018-02-05 | 2018-10-31 | 100% | 4994489.13
2016 | Purchase of Agricultural & Forestry Equipment and Implements |  | 8800000 | 2018-01-02 | 2018-12-31 | 100% | 8400000
2016 | Purchase of Digital Weighing Scale |  | 250000 |  |  |  | 0
2016 | Reblocking of Concrete Pavement at Villareal-Cansumalig-San Isidro FMR, Phase 3 | Bayawan City | 500000 | 2017-03-01 | 2017-07-31 | 100% | 470136.11
2016 | Reblocking of Concrete Pavement Nangka- Narra FMR | Bayawan City | 500000 | 2017-02-16 | 2017-06-30 | 100% | 472475.09
2016 | Reblocking of Concrete Pavement with Slope Protection at Malabugas-San Roque Route | Bayawan City | 500000 | 2017-05-01 | 2017-10-31 | 100% | 463375.74
2016 | Reblocking of Concrete Pavement with Slope Protection at Tabuan-Banay-banay Route | Bayawan City | 500000 | 2017-05-01 | 2017-10-31 | 100% | 463537.29
2016 | Concreting of Road Approaching Cagayon Box Culvert with Slope Protection | Banaybanay | 1000000 | 2017-01-01 | 2017-10-31 | 100% | 922836.09
2016 | Concreting of Road Approaching Cabigohan Box Culvert with Slope Protection | Dawis | 1000000 | 2017-05-01 | 2017-10-15 | 100% | 947426.51
2016 | Installation of Guardrails at Kalumboyan Bridge Approaches | Kalumboyan | 2000000 | 2017-08-01 | 2018-06-30 | 100% | 1716619.15
2016 | Const. of Urban Roads (Gomez to Kabankalan Road) | City Proper | 8000000 | 2017-06-01 | 2018-12-31 | 100% | 5854241.79
2016 | Rehab of FMR at So. Pag-awitan, Ali-is | Ali-is | 500000 | 2018-05-16 | 2018-12-31 | 100% | 296371.2
2016 | Road Opening at Sitio Palasanon, Cansinacao, Guintalasan Mangharaw & Guinhamogan, Brgy Cansumalig | Cansumalig | 500000 | 2018-02-16 | 2020-06-30 | 100% | 152009.44
2016 | Road Rehabilitation at so. Camague, Brgy Dawis | Villareal | 500000 | 11/31/2019 | 2020-07-31 | 60% | 185715.6
2016 | Road surfacing at Manduao-Bucao, Brgy Manduao | Manduao | 500000 | 2016-03-11 | 2016-07-28 | 5% | 167283.93
2016 | Const. of Steel Bridge Connecting So. Malampa to So. Tab-ang, Brgy Pagatban | Pagatban | 500000 | 2017-06-16 | 2018-01-31 | 100% | 408032.04
2016 | Const. or Road from Gov't. Ctr. To sitio Buli-buli/Phase 2 | Banga | 2000000 | 2017-01-01 | 2017-11-30 | 100% | 1680955.01
2016 | Improvement of Road Along Bayawan CIP Main Canal | Bayawan City | 190000 | 2019-08-16 | 2020-05-15 | 100% | 90000
2016 | Const. of Footbridge at Sitio Lower Baican, Brgy Villasol | Baican, Villasol | 220000 | 2018-02-01 | 2018-06-30 | 100% | 221204.91
2016 | Rehabilitation of Bayawan Communal Irrigation System | Pagatban | 500000 | 2016-08-16 | 2016-12-31 | 100% | 458455.32
2016 | Const. of Small Scale Irrigation Project at Sitio Magsulay | Narra | 1000000 | 2016-08-16 | 2019-12-31 | 100% | 894843.52
2016 | Const. of Box Culvert in So. Candalaga, Brgy Nangka | Nangka | 500000 | 2017-03-16 | 2017-06-30 | 100% | 413628.17
2016 | Construction of Spring Box at Upper Talao, San Isidro | San Isidro | 500000 | 2018-04-15 | 2019-03-31 | 100% | 261148.49
2016 | Const. of 1 unit Single Box Culvert Phase 1 at So, Magsakang, brgy Tayawan | Tayawan | 500000 | 2018-01-16 | 2018-05-15 | 100% | 410379.87
2017 | Improvement of Barangay Public Market, Brgy. Malabugas | Malabugas | 50000 |  |  |  | 0
2017 | Construction of Pigpens |  | 400000 |  |  |  | 0
2017 | Construction of 2 Units Small Scale Rubber Processing Plant with Shed |  | 300000 |  |  |  | 0
2017 | Purchase of Breeding Stocks | Bayawan City | 1944000 |  |  |  | 0
2017 | Improvement of Brgy. Dawis Livestock Auction Market | Dawis | 150000 | 2019-09-01 | 2019-12-31 | 100% | 75042.98
2017 | Fabrication of Portable Batching Plant |  | 500000 | 2017-10-16 | 2018-05-31 | 100% | 325671.05
2017 | Construction of CEO Multi-Purpose Building | Cabcabon | 2000000 | 2017-04-16 | 2019-04-30 | 100% | 1744342.36
2017 | Construction of Motorpool Building at Cabcabon | Cabcabon | 8000000 | 2017-05-16 | 2019-12-15 | 99.5% | 6670246.05
2017 | Lot Acquisition |  | 500000 |  |  |  | 0
2017 | Improvement of Public Market Water System | Bayawan City | 500000 |  |  |  | 0
2017 | Construction of Slope Protection at Narra-Duyanduyan FMR, Sito Duyan-duyan, Brgy. Narra | Bayawan City | 1000000 | 2017-10-16 | 2018-05-31 | 100% | 895097.05
2017 | Purchase of Various Agricultural Equipment | Bayawan City | 4000000 |  |  |  | 0
2017 | Slope Protection at Barangay Proper, San Isidro | San Isidro | 50000 | 2017-11-16 | 2018-01-31 | 100% | 66281.74
2017 | Construction of Flat Slab Bridge at Brgy. Proper, Banaybanay | Banaybanay | 600000 | 2018-01-16 | 2018-09-30 | 100% | 583108.44
2017 | Improvement of FMR at Sitio Cangcawit, Banaybanay | Banaybanay | 1078571.43 | 2020-02-15 | 2020-08-31 | 100% | 888248.25
2017 | Improvement of Covered Court & Evacuation Center, Brgy. Banga | Banga | 500000 | 2019-03-16 | 2019-10-30 | 100% | 358699.53
2017 | Improvement of FMR at Sitio Cansig-id, Brgy. Banga | Banga | 500000 | 2017-12-01 | 2018-01-31 | 100% | 445034
2017 | Improvement of FMR from Brgy. Proper to Sitio Aya, Brgy. Bugay | Bugay | 839286.43 | 2020-04-20 | 2020-06-01 | 100% | 728752.38
2017 | Improvement of FMR from Brgy Proper to Sitio Canlantang,Brgy. Bugay | Bugay | 839285 | 2020-04-20 | 2020-06-01 | 100% | 612956.45
2017 | Construction of Satellite Farmers' Market, Brgy. Dawis | Dawis | 1000000 |  |  |  | 0
2017 | Improvement of FMR at Brgy. Dawis | Dawis | 150000 | 2018-06-01 | 2019-02-22 | 100% | 146687.65
2017 | Improvement of Road from Barangay Proper to Kalamtukan Elementary School, Brgy. Kalamtukan | Kalamtukan | 1178571.43 | 2017-10-16 | 2018-06-15 | 100% | 1083384.59
2017 | Improvement of FMR at Brgy. Proper, Manduao | Manduao | 500000 | 2019-01-13 | 2020-04-15 | 100% | 117245.47
2017 | Improvement of FMR at Brgy. Minaba | Minaba | 678571.43 | 2018-05-16 | 2019-01-31 | 100% | 532636.79
2017 | Improvement of FMR at Sitio Kasla, Brgy. Nangka | Nangka | 1000000 | 2017-12-01 | 2018-07-31 | 100% | 910370.06
2017 | Improvement of FMR at Sitios Terong, Palongpong, Canggabi and Cadal-ugan, Brgy. Narra | Narra | 1000000 | 2018-05-16 | 2020-08-01 | 99% | 418043.41
2017 | Road Opening at Brgy. Narra Proper | Narra | 678571.43 | 2018-06-16 | 2019-12-31 | 100% | 642563.45
2017 | Construction of Cloning Chamber at San Roque BADC | San Roque | 500000 |  |  |  | 0
2017 | Improvement of Binanigan-Guintanaan FMR, Tayawan | Tayawan | 678571.43 | 2019-10-15 | 2020-07-31 | 100% | 225203.65
2017 | Improvement of Binanigan-Napo FMR, Brgy. Tayawan | Tayawan | 500000 | 2019-01-10 | 2020-03-16 | 95% | 429480.42 | Road not passable
2017 | Construction of Flat Slab Bridge Connecting Barangay Proper to Purok Malinong, Brgy. Villasol | Villasol | 1078571.43 | 2018-02-15 | 2019-04-30 | 100% | 1023759.93
2017 | Improvement of FMR at Brgy. Banaybanay | Banaybanay | 100000 | 2020-06-01 | 2020-08-15 | 100% | 44042.5
2017 | Improvement of FMR at Sitio Napit-an, Brgy. Maninihon | Maninihon | 220000 | 2018-04-01 | 2018-07-31 | 100% | 189414.53
2017 | Improvement of FMR at Sitio Ondol, Brgy. Nangka | Nangka | 100000 | 2018-04-01 | 2018-08-31 | 100% | 95011
2017 | Road Improvement at Brgy. Ubos | Ubos | 170000 | 2018-01-01 | 2018-02-15 | 100% | 148954.81
2017 | Construction of Pathway to Banay-Banay Proper | Banay-Banay | 100000 | 2017-10-16 | 2018-02-28 | 100% | 90879.07
2017 | Road Opening from National Highway to Purok 1 Pasil, Brgy. Malabugas | Malabugas | 150000 | 2019-09-15 | 2020-09-16 | 50% | 70424.49
2017 | Improvement of FMR at Sitio San Ramon, Brgy. Poblacion | Poblacion | 150000 | 2018-04-01 | 2018-08-31 | 100% | 143423.48
2017 | Rehabilitation of Farm to Market Road from Sitio Bosque to Tavera, Barangay Nangka | Nangka | 1000000 | 2019-06-12 | 2020-06-10 | 90% | 447997.6 | Road not passable
2017 | Purchase of Lot (Road Right of Way for Various Road Projects) |  | 2980124.07 |  |  |  | 0
2017 | Development of Danapa Eco Park | Nangka | 18000000 | 2017-12-06 | 2020-02-29 | 100% | 16389043.68
2017 | Development of Narra Water Park | Narra | 16000000 | 2017-09-12 | 2018-09-30 | 100% | 15993892.48
2017 | Purchase of Livestock Breeding Stocks |  | 533460 | 2017-05-31 | 11/31/2019 | 100% | 515555.56
2018 | Loan Amortization |  | 9809031.89 |  |  |  | 0
2018 | Lot Acquisition for Development Projects |  | 1754285.71 |  |  |  | 0
2018 | Widening of Malabugas-San Roque Road | Bayawan City | 3500000 | 2019-01-09 | 2019-12-31 | 100% | 3046766.71
2018 | Concreting of Road Approaching Candalaga Box Culvert with Slope Protection, Nangka | Nangka | 1000000 | 2018-04-01 | 2018-11-30 | 100% | 872520.61
2018 | Concreting of Road Approaching Pusi-on Box Culvert with Slope Protection, Maninihon | Maninihon | 1000000 | 2018-04-01 | 2019-02-28 | 100% | 853979.33
2018 | Concreting of Road Approaching Balao Box Culvert with Slope Protection, San Miguel | San Miguel | 1000000 | 2018-04-01 | 2018-10-30 | 100% | 830492.78
2018 | Concreting of Road Approaching Magsakang Box Culvert with Slope Protection, Tayawan | Tayawan | 1000000 | 2018-04-01 | 2019-07-31 | 100% | 853320.52
2018 | Completion of Magsakang Flat Slab Bridge, Tayawan | Tayawan | 1000000 | 2018-04-01 | 2019-04-30 | 100% | 954259.8
2018 | Concreting of Road Approaching Pamuat Box Culvert with Slope Protection, San Isidro | San Isidro | 1000000 | 2018-04-01 | 2019-06-30 | 100% | 949641.59
2018 | Concreting of Dawis-Lapay FMR | Bayawan City | 5500000 | 2018-04-01 | 2019-07-31 | 100% | 4549805.09
2018 | Concreting of Banga-San Roque-Minaba-San Miguel-Tayawan FMR | Bayawan City | 5872000 | 2018-04-01 | 2019-06-30 | 100% | 5222289.97
2018 | Concreting of Nangka-Narra FMR | Bayawan City | 5500000 | 2018-04-01 | 2019-05-31 | 100% | 4598663.85
2018 | Concreting of Tabuan- Banaybanay-Lapay-Bugay-San Jose-Manduao FMR | Bayawan City | 28340000 | 2019-05-29 | 2019-09-08 | 100% | 28213392.75
2018 | Concreting of Road from Sitio Balastro to Sitio Candulion to Pulangyuta, Barangay Kalamtukan | Kalamtukan | 10500000 | 2018-01-08 | 2019-08-31 | 100% | 9135098.81
2018 | Concreting of Road with Drainage Canal at Upper Napit-an, Maninihon | Maninihon | 300000 | 2018-04-01 | 2018-07-31 | 100% | 175615.88
2018 | Construction of Flat Slab Bridge at Sitio Terong, Narra | Narra | 600000 | 2018-04-01 | 2019-06-30 | 100% | 521679.69
2018 | Road Concreting from Proper Narra to Purok III, Brgy. Narra | Narra | 500000 | 2018-04-01 | 2018-10-16 | 100% | 394845.27
2018 | Concreting of Road at Sitio Upper Pamu-at, San Isidro | San Isidro | 500000 | 2018-04-01 | 2020-03-16 | 100% | 266836.87
2018 | Concreting of Road at Upper Talao, San Isidro | San Isidro | 600000 | 2018-10-01 | 2019-03-31 | 100% | 515539.32
2018 | Road Shouldering Along Zamora St., Brgy. Ubos | Ubos | 500000 | 2018-06-16 | 2018-11-30 | 100% | 428565.85
2018 | Road Surfacing from Barangay Proper to Sitio Gawgaw to Sitio Aya, Brgy. Bugay | Bugay | 839286.43 | 2019-03-01 | 2020-12-31 | 100% | 719892.01
2018 | Road Surfacing from Barangay Proper to Sitio Mambuy-og to Sitio Canlantang, Brgy. Bugay | Bugay | 839285 | 2019-01-04 | 2019-12-31 | 100% | 767136.18
2018 | Road Surfacing at Barangay Cansumalig | Cansumalig | 1078571.43 | 2018-04-01 | 2018-05-31 | 96.97% | 951669.79
2018 | Installation of Cylindrical Culvert with Riprap at Proper Narra | Narra | 578571.43 | 2018-06-16 | 2019-08-31 | 100% | 505318.65
2018 | Construction of Small Scale Irrigation Projects (SSIP): | Bayawan City
2018 | a. Purok Mangga, Brgy. Manduao | Manduao | 800000 | 2018-06-01 | 2020-04-30 | 74% | 634546.45
2018 | c. Upper Canlinte, Brgy Ali-is | Ali-is | 800000 | 2018-06-01 | 2020-04-30 | 100% | 578453.13
2018 | Rehabilitation of Irrigation Canal at Brgy. Tabuan | Tabuan | 915000 | 2019-03-01 | 2020-03-10 | 100% | 773915.66
2018 | Construction of Barangay Public Market, Ali-is (Phase 1) | Bayawan City | 1000000 |  |  |  | 0
2018 | Construction of Rainwater Harvesting Systems for Nurseries:
2018 | a. Brgy. San Miguel | San Miguel | 250000 | 2018-10-01 | 2018-11-30 | 100% | 194742.5
2018 | b. Brgy. Tayawan | Tayawan | 250000 | 2018-10-16 | 2019-05-31 | 100% | 191604.82
2018 | c. Brgy. Cansumalig | Cansumalig | 250000 | 2018-10-16 | 2019-06-30 | 100% | 191100.28
2018 | d. Brgy. Manduao | Manduao | 250000 | 2018-10-16 | 2020-05-31 | 100% | 159644.74
2018 | e. Brgy. Kalamtukan | Kalamtukan | 250000 | 2018-10-16 | 2020-05-31 | 100% | 183871.5
2018 | Construction of Fish Processing Center @ Brgy. Suba | Suba | 2500000 | 2019-04-01 | 2019-12-31 | 95% | 2184728.63
2018 | Major Repair of Narra Barangay Agricultural Development Center (BADC) | Narra | 520000 | 2018-09-30 | 2020-03-31 | 100% | 449602.67
2018 | Major Repair of Manduao Barangay Agricultural Development Center (BADC) | Manduao | 290000 | 2018-09-30 | 2020-03-31 | 100% | 227443.68
2018 | Purchase of Boom Truck | Bayawan City | 1600000 |  |  |  | 0
2018 | Purchase of Lot for Agricultural Research Center | Maninihon | 16000000 | 2018-12-01 | 2019-12-31 | 100% | 15710989
2018 | Establishment of Agricultural Research Center | Maninihon | 6895568.71 |  |  |  | 0
2018 | Improvement of Bugay-San Jose-Manduao FMR | Bayawan City | 3000000 | 2018-10-15 | 2019-01-06 | 100% | 2959185.3
2018 | Concreting of Urban Roads with Drainage System (Gomez St.) | Poblacion | 12885436.16 | 2019-01-16 | 2020-02-29 | 100% | 10611305.74
2019 | Supply & Installation of Hog & Cattle Slaughterhouse Equipment for Bayawan City AA Slaughterhouse Plant | Bayawan City | 16478571.43 |  |  |  | 0
2019 | Construction of Dawis Public Market (Phase 2) | Dawis | 2000000 | 2020-09-01 | 2021-01-16 | 47.91% | 1298823.57
2019 | Loan Amortization |  | 4338835.57 |  |  |  | 0
2019 | Lot Acquisition for Road Right of Way | Villareal | 500000 |  |  |  | 0
2019 | Lot Acquisition for Agricultural Development Center (Tan-ayan) | Tan-ayan | 2500000 |  |  |  | 0
2019 | Wayang Access Road Development | Nangka | 20000000 | 2019-02-16 | 2020-04-30 | 99% | 17521736.65 | On going
2019 | Construction of Ondol-Napit-an FMR | Bayawan City | 20000000 | 2019-03-15 | 2020-08-31 | 84% | 15242902.86 | -do-
2019 | Concreting of Access Road from National Highway to Palongpong Agricultural Development Center | Bayawan City | 9000000 | 2019-01-04 | 2020-03-31 | 100% | 7288949.69
2019 | Improvement of Road Leading to Danapa Inland Aquaculture Facility | Nangka | 2000000 | 2019-03-16 | 2019-12-31 | 100% | 1659691.3
2019 | Concreting of Perimeter Road at BCWMEC | Maninihon | 2000000 | 2019-01-06 | 2020-02-15 | 100% | 1630309.7
2019 | Concreting of Urban Roads with Drainage System (Gomez St.) | Poblacion | 3000000 | 2019-07-16 | 2020-03-31 | 100% | 2288790.17
2019 | Improvement of Maninihon-Cansumalig-San Isidro FMR |  | 2387650.49 | 2020-01-06 | 2020-06-30 | 100% | 2098167.93
2019 | Construction of Public Market Stalls in Omod, Maninihon (Phase 1) | Maninihon | 1678571.43 | 2019-06-16 | 2020-05-31 | 100% | 1351998.01
2019 | Establishment of Agricultural Research Center |  | 10877134.99 |  |  |  | 0
Purchase of Construction & Heavy Equipment:
| 1 unit Bulldozer |  | 15000000 |  |  |  | 14988000
| 1 unit Backhoe |  | 12000000 |  |  |  | 11988000
| 1 unit Trailer Mounted DW100-T Drilling Rig with Accessories |  | 3594500 |  |  |  | 0
| 2 units 6-Wheeler Dump Truck |  | 4400000 |  |  |  | 0
2019 | Purchase of Livestock Breeding Stocks |  | 2000000 |  |  |  | 1530000
2020 | Loan Amortization | Bayawan City | 5526165.42 |  |  |  | 0
2020 | Purchase of Lot for Relocation Site, Brgy. Manduao | Manduao | 1000000 |  |  |  | 0
2020 | Purchase of Lot for Barangay Multi-Purpose Hall Extension, Banga | Banga | 1678571.43 |  |  |  | 0
2020 | Lot Acquisition for Informal Settlers | Bayawan City | 1574365.84 |  |  |  | 0
2020 | Completion of Urban Road (Gomez Ext.) | Bayawan City | 6000000 | 2020-01-02 | 2021-04-30 | 95% | 4043536.46
2020 | Concreting of Inland Aquaculture Road Network | Bayawan City | 7500000 | 2020-10-01 | 2021-04-19 | 97% | 2178108.72 | On going
2020 | Improvement of Farm to Market Road at Sitio Dita, Ali-is | Ali-is | 1078571.43 | 2020-07-01 | 2021-10-21 | 45% | 347279.41 | -do-
2020 | Concreting of Tower-Baong Road, Kalamtukan | Kalamtukan | 500000 | 2020-10-01 | 2020-11-05 |  | 48803.47
2020 | Concreting of Manduao-Bucao Farm to Market Road | Manduao | 1000000 | 2020-10-01 | 2020-12-30 |  | 224458.79
2020 | Road Concreting at Sitio Ondol, Nangka | Nangka | 500000 | 2020-10-01 | 2020-06-30 | 100% | 150595.82
2020 | Road Concreting at Talaptap-Narra Proper | Narra | 500000 | 2020-08-03 | 2020-11-25 | 93% | 323815.19
2020 | Road Concreting at Purok Pagkakaisa, Villareal | Villareal | 800000 | 2020-12-01 | 2020-12-30 | 100% | 278691.21
2020 | Improvement of Maninihon-Cansumalig-San Isidro Farm to Market Road | Bayawan City | 2612349.51 |  |  |  | 0
2020 | Construction of Small Scale Irrigation Project in Sitio Bolo, Tabuan | Tabuan | 459855 |  |  |  | 0
2020 | Construction of Barangay Public Market, Banaybanay | Banaybanay | 500000 | 2020-07-01 | 2020-08-12 | 100% | 158035.5
2020 | Construction of Dawis Public Market (add'l fund) | Dawis | 825000 |  |  |  | 0
2020 | Construction of Public Market Building, Maninihon | Maninihon | 2378571.43 | 2020-10-01 | 2021-03-30 | 34% | 751582 | On going
2020 | Construction of Perimeter & Divisional Fences for Cattle at Sitio Cabcabon, Brgy. Banga | Banga | 800000 | 2020-07-01 | 2020-12-31 |  | 370660.9
2020 | Construction of Cattle Shed at Sitio Cabcabon, Barangay Banga | Banga | 1200000 | 2020-07-01 | 2020-12-31 |  | 619322.84
2020 | Construction of Piggery |  | 1000000 |  |  |  | 0
2020 | Construction of Flat Slab Bridge at Magtangis Creek in Sitio Guintana-an, Brgy. Tayawan | Tayawan | 1678571.43 | 2020-10-01 | 2020-12-29 |  | 11866.6
2020 | Construction & Heavy Equipment
2020 | 6 Units Dump Truck |  | 30000000 |  |  |  | 29988000
2020 | 1 Unit Motor Grader |  | 14000000 |  |  |  | 11400000
2020 | 1 Unit Backhoe (1 cu.m) |  | 10000000 |  |  |  | 9876543.21
2020 | 2 Units Payloader |  | 23000000 |  |  |  | 22997530
2020 | 2 Units Vibratory Roller |  | 12000000 |  |  |  | 11976000
2020 | 1 Unit Transit Mixer (5 cu.m) |  | 4000000 |  |  |  | 0
2020 | 1 Unit Water Tanker |  | 4000000 |  |  |  | 0
2020 | 1 Unit Backhoe (0.5 cu.m) |  | 3000000 |  |  |  | 0
2020 | 1 Unit Mini-Dumptruck - DA |  | 1500000 |  |  |  | 0
2020 | Purchase of 1 unit Mini Dump Truck |  | 1678571.43 |  |  |  | 0
2020 | Purchase of Mini-Dumptruck for Barangay Boyco |  | 1678571.43 |  |  |  | 0
2020 | Purchase of Mini-Dumptruck for Barangay Minaba |  | 1200000 |  |  |  | 0
2020 | Purchase of 1 Unit Dump Truck for Barangay Tabuan |  | 1000000 |  |  |  | 0
| Total Projects for Economic Development - Continuing Appropriation |  | 573183615.65 |  |  |  | 392945195.81
ENVIRONMENTAL MANAGEMENT
2004 | Sanitary Landfill (Land Acquisition) 2004 | Maninihon | 1000000 |  |  |  | 8311
2013 | Construction of Drainage Canal with Cover Along City Streets | Bayawan City | 606779.6 | 2014-06-02 | 2014-11-30 | 100% | 544360.59
2016 | Construction of Drainage City Streets - Zamora, Teologio Sts, Subd Area | Zamora, Teologio & Subd Area | 3000000 | 2017-01-01 | 2017-09-15 | 100% | 2641029.39
2016 | Rehabilitation of River Bank Protection at Sitio Ebuan | Nangka | 2000000 | 2017-03-16 | 2018-12-31 | 100% | 1451778.7
2016 | Const. of Drainage Canal at along Burgos St. & AlongBollos St. Brgy Ubos | Ubos | 500000 | 2017-02-01 | 2017-06-30 | 100% | 442668.24
2016 | Rehabilitation of Riverbank @ Brgy. Nangka | Nangka | 1000000 | 2018-05-16 | 2018-12-31 | 100% | 1013905.35
2017 | Concreting of Drainage Canal Cover Along National Highway, Brgy. Villareal | Villareal | 678571.43 | 2017-11-16 | 2019-12-31 | 90% | 491510.65
2017 | Construction of Drainage at Cabugcabugan Creek, Brgy. Poblacion, Phase 4 | Poblacion | 1356746.77 | 2017-11-16 | 2020-08-31 | 97% | 1197855.77
2017 | Construction of Concrete Canal Cover Along Rizat St. Brgy Tinago | Tinago | 1000000 | 2017-11-16 | 2018-03-31 | 100% | 862393.25
2017 | Construction of Riverbank Protection at Camayaan Creek,Brgy. Malabugas | Malabugas | 1000000 | 2018-01-16 | 2018-10-16 | 100% | 898258.82
2017 | Flood Control Project at Brgy. Malabugas, Phase 2 | Malabugas | 1500000 | 2017-09-01 | 2018-06-30 | 100% | 1331896.08
2018 | Construction of Drainage Canal from Upper Napit-an to Lower Napit-an, Brgy. Maninihon | Maninihon | 650000 | 2018-06-01 | 2018-09-30 | 100% | 546606.01
2018 | Covering of Drainage Canals along Gomez St., Brgy. Ubos | Ubos | 1078571.43 | 2018-08-12 | 2020-03-31 | 100% | 1033885.73
2018 | Purchase of Garbage Compactor Truck | Bayawan City | 1500000 |  |  |  | 0
2019 | Construction of Drainage Canal at Magsulay Agricultural Development Center | Narra | 400000 | 2019-07-16 | 2020-03-31 | 100% | 328396.65
2019 | Concreting of Drainage Canals at Barangay Proper, San Isidro | Bayawan City | 400000 | 2019-01-06 | 2019-08-31 | 100% | 335921.21
2019 | Purchase of Garbage Compactor Truck |  | 5000000 |  |  |  | 0
2019 | Purchase of Vacuum Declogger Truck |  | 2000000 |  |  |  | 0
2020 | Construction of Foot Bridge at Sitio Omod, Maninihon | Maninihon | 500000 | 2020-10-01 | 2020-12-20 | 87% | 373056.99 | On going
2020 | Construction of Foot Bridge at Purok Ipil-ipil, San Roque | San Roque | 500000 | 2020-07-01 | 2020-12-20 | 56.2% | 419119.17 | Road not passable
2020 | Construction of Concrete Canal Cover at Barangay Suba | Suba | 500000 | 2020-10-01 | 2020-12-20 | 100% | 430222.74
2020 | Construction of New Central Materials Recovery Facility | Bayawan City | 2500000 | 2020-07-01 | 2020-12-20 | 83% | 2083061.62 | On going
2020 | Construction of Toxic and Hazardous Waste Vault Phase 2 | Bayawan City | 800000 | 2020-09-01 | 2020-12-01 | 97% | 471033.6 | -do-
2020 | Fabrication of 32 Units Residual Waste Containment Faciltiy for Upland Barangays | Bayawan City | 2000000 | 2021-07-01 | 2022-04-20 |  | 1384824.51 | -do-
| Total Projects for Environmental Management - Continuing Appropriation |  | 31470669.23 |  |  |  | 18290096.07
| TOTAL DF - CONTINUING APPROPRIATION |  | 761962221.87 |  |  |  | 491321068.78
TOTAL EDF - CURRENT & CONTINUING APPROPRIATION |  |  | 1005159518.27 |  |  |  | 564753861.04
| CORAZON P. LIRAZAN, CPA, MBA |  |  |  | HON. PRYDE HENRY A. TEVES
| City Accountant |  |  |  | City Mayor