## Form 6a -TFU
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
REGION: REGION VII - CENTRAL VISAYAS |  | CALENDAR YEAR: 2023 | 2024
PROVINCE NEGROS ORIENTAL |  | QUARTER: 4 | 2
CITY/MUNICIPALITY CITY OF BAYAWAN (TULONG)
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of | Remarks
[5 empty] | % of | Total Cost Incurred | Extensions, if
[5 empty] | Completion | to Date | any
Sta. Bayabas - Common Health Fund | Bayawan City | 4048535.04 |  |  |  | 1382057.24 |  | on going
DA for Construction of Briefing Area, Stockroom and Other Facilities | Sitio Napit-an, Maninihon | 300000 | 2022-07-04 | 2022-12-16 | 100% | 262342.2 |  | Physically Completed
DA for Retention Fee for 2019 Rubber (Seedling Production: Site Preparation |  | 494250 |  |  |  | 0 |  | on going
DA for Rice Extension Service Program (RESP) Scholarship Grant and TESDA 7 TVET Program | Bayawan City | 16346692.95 |  |  |  | 26962.5 |  | on going
CSWD for Social Pension for Indigent Senior Citizen (DSWD RO7) | Bayawan City | 17658000 |  |  |  | 17442000 |  | on going
DENR to Enhance National Greening Program - Seedling Production & Seedling Maintenance activities of its Rubber (2018) | Bayawan City | 283728 |  |  |  | 0 |  | for implementation by City Agriculture
DENR to Enhance National Greening Program 2018 (DENR) - Green Rubber Budding, Care and Maintenance of Budded Seedlings | Bayawan City | 763920 |  |  |  | 71700 |  | on going
Page 1 of 3
DENR to Enhance National Greening Program 2019 (DENR) - Site Preparation and Planting, and 1st Year Maintenance and Protection activities of its Rubber | Bayawan City | 747485.6 |  |  |  | 0 |  | for implementation by City Agriculture
DENR to Enhance National Greening Program 2019 Rubber - Year III 1st Maintenance and Protection | Bayawan City | 423155.25 |  |  |  | 0 |  | for implementation by City Agriculture
DENR to Enhance National Greening Program 2019 Rubber- 2nd Year Maintenance and Protection | Bayawan City | 398356.87 |  |  |  | 0 |  | for implementation by City Agriculture
DENR to Enhance National Greening Program 2020 Rubber- Maintenance and Protection |  | 16532.25 |  |  |  | 0 |  | for implementation by City Agriculture
DENR to Enhance National Greening Program 2020 Rubber- Maintenance and Protection Year II |  | 41330.62 |  |  |  | 0 |  | for implementation by City Agriculture
DOH to Completion of Tabuan Barangay Health Station | Barangay Tabuan | 500000 |  |  |  | 0 |  | per CEO: no site location; no POW
DOH to Construction/Completion/ Expansion of Villasol Birthing Facility (BHS) | Barangay Villasol | 500000 |  |  |  | 0 |  | per CEO: Procurement process
DOLE Integrated Livelihood Project (Kabuhayan Program) | Bayawan City | 3742694 |  |  |  | 0 |  | on going
NORSU & LGU Equity to "Bayawan LGU-NORSU" Joint Venture for Sports Complex Project | Bayawan City - NORSU | 280000000 | 2020-09-09 |  | 93.28% | 269998999.2 |  | on going
DBM to Construction of Sen. Lorenzo G. Teves Memorial Circle (Rotunda) | Bayawan City | 16826393 | 2022-05-02 |  | 86.85% | 5811587.82 |  | per CEO: Pending no tiles deliver; no electrical & pluming materials for the fountain delever
NHA-LGU Equity to Development of Enzo Town House, Phase I | Bayawan City | 20032192.5 |  |  |  | 8326842.7 |  | on going
Page 2 of 3
DILG Fire Code Fees Collection (20% LGU Share) |  | 843995.07 |  |  |  | 0 |  | on going
KOICA - COVID-19 Isolation Facility and Diagnostic Laboratory (medical, laboratory and Other MOOE) | Bayawan City | 22212625.4 |  |  |  | 1504000 |  | per CEO: Procurement process
KOICA - Construction of RT-PCR Molecular Laboratory | Barangay Poblacion | 3914795 | 2022-07-04 |  | 100% | 3803110.74 |  | Physically Completed
KOICA - Construction of COVID-19 Isolation Facility | Barangay Poblacion | 23742579.6 | 2022-07-04 |  | 100% | 23314500.07 |  | Physically Completed
DBM - Construction of Bugay Bridge | Bayawan City | 20000000 | 2023-06-26 |  | 25.02% | 5003467.57 |  | on going
DBM -Barangay Tabuan- Concreting of Farm to Market Road |  | 2500000 |  |  |  | 0 |  | Funds received 6/26/24
TOTAL |  | 436337261.15 |  |  |  | 336947570.04
872674522.3
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
OPHELIA URIKA R. TRINIDAD |  | DONALD B. TUBIO, CPA, MPM |  |  |  | JOHN T. RAYMOND, JR
Local Budget Officer |  | Local Accountant |  |  |  | Local Chief Executive
Page 3 of 3
.

## Form 6b - TFU (hidden)
LOCAL GOVERNMENT SUPPORT FUND (Report on Fund Utilization and Status of Program/Project Implementation)
REGION: |  |  | CALENDAR YEAR:
PROVINCE: |  |  | QUARTER:
CITY/MUNICIPALITY: |  |  | OFFICE:
Amount
Fund Source | Date of Notice of Authority to Debit Account Issued | Type of Program/Project | Name Title of Program/Project | Specific Location | Mechanism/Mode of Implementation | Estimated Number of Beneficiaries | Received | Obligation | Disbursement | Estimated Completion (Month and Year) | Remarks on Program/Project Status
Certified Correct by: |  |  |  |  | Attested by:
The Local Finance Committee:
Local Chief Executive
City Budget Officer
City Treasurer
City Planning and Development Coordinator
Instructions:
1 | The report shall prepared by the LFC, in coordination with the other local officials concerned (local accountant on the allotment, obligation and disbursements;
local engineers in the status of infrastructure projects, as may be applicable.
2 | The fund source shall be based on the NADAI issued to the cities.
3 | The type of program/project shall be identified, consistent with the projects that may be implemented under the Circular.
4 | Amount received refers to the amount received by the city as its location. It is the amount the NADAI. Obligation refers to the total amount obligated by the
city as of reporting period. Disbursement refers to the total amount paid as of reporting period.
5 | The status of programs/projects refers to the percentage of physical completion or delivery of service as of reporting period.

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2