## 3rd
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
REGION: REGION VII - CENTRAL VISAYAS |  | CALENDAR YEAR: 2023 | 2024
PROVINCE NEGROS ORIENTAL |  | QUARTER: 4 | 3
CITY/MUNICIPALITY CITY OF BAYAWAN (TULONG)
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of | Remarks
[5 empty] | % of | Total Cost Incurred | Extensions, if
[5 empty] | Completion | to Date | any
Sta. Bayabas - Common Health Fund | Bayawan City | 4932946.87 |  |  |  | 2902367.33 |  | on going
DA for Retention Fee for 2019 Rubber (Seedling Production: Site Preparation |  | 494250 |  |  |  | 0 |  | on going
DA for Rice Extension Service Program (RESP) Scholarship Grant and TESDA 7 TVET Program | Bayawan City | 19486746.99 |  |  |  | 3545288.29 |  | for implementation by City Agriculture
DENR to Enhance National Greening Program - Seedling Production & Seedling Maintenance activities of its Rubber (2018) | Bayawan City | 283728 |  |  |  | 0 |  | for implementation by City Agriculture
DENR to Enhance National Greening Program 2018 (DENR) - Green Rubber Budding, Care and Maintenance of Budded Seedlings | Bayawan City | 763920 |  |  |  | 71700 |  | on going
DENR to Enhance National Greening Program 2019 (DENR) - Site Preparation and Planting, and 1st Year Maintenance and Protection activities of its Rubber | Bayawan City | 747485.6 |  |  |  | 0 |  | for implementation by City Agriculture
DENR to Enhance National Greening Program 2019 Rubber - Year III 1st Maintenance and Protection | Bayawan City | 423155.25 |  |  |  | 0 |  | for implementation by City Agriculture
DENR to Enhance National Greening Program 2019 Rubber- 2nd Year Maintenance and Protection | Bayawan City | 398356.87 |  |  |  | 0 |  | for implementation by City Agriculture
DENR to Enhance National Greening Program 2020 Rubber- Maintenance and Protection |  | 16532.25 |  |  |  | 0 |  | for implementation by City Agriculture
DENR to Enhance National Greening Program 2020 Rubber- Maintenance and Protection Year II |  | 41330.62 |  |  |  | 0 |  | for implementation by City Agriculture
DOH to Completion of Minaba Barangay Health Station | Barangay Tabuan | 500000 |  |  |  | 133399.39 |  | For Re-POW
DOH to Construction/Completion/ Expansion of Villasol Birthing Facility (BHS) | Barangay Villasol | 500000 |  |  |  | 0 |  | per CEO: Procurement process
DOLE Integrated Livelihood Project (Kabuhayan Program) | Bayawan City | 3742694 |  |  |  | 0 |  | on going
NORSU & LGU Equity to "Bayawan LGU-NORSU" Joint Venture for Sports Complex Project | Bayawan City - NORSU | 280000000 | 2020-09-09 |  | 93.28% | 269998999.2 |  | on going
DBM to Construction of Sen. Lorenzo G. Teves Memorial Circle (Rotunda) | Bayawan City | 16826393 | 2022-05-02 |  | 86.85% | 6092087.82 |  | per CEO: Pending no tiles deliver; no electrical & pluming materials for the fountain delever
NHA-LGU Equity to Development of Enzo Town House, Phase I | Bayawan City | 20032192.5 |  |  |  | 11091904.25 |  | Procurement Process
DILG Fire Code Fees Collection (20% LGU Share) | Bayawan City | 1142346.49 |  |  |  | 0 |  | on going
KOICA - COVID-19 Isolation Facility and Diagnostic Laboratory (medical, laboratory and Other MOOE) | Bayawan City | 22212625.4 |  |  |  | 1504000 |  | per CEO: Procurement process
KOICA - Construction of RT-PCR Molecular Laboratory | Barangay Poblacion | 3914795 | 2022-07-04 |  | 100% | 3803110.74 |  | Physically Completed
Page 2 of 3
KOICA - Construction of COVID-19 Isolation Facility | Barangay Poblacion | 23742579.6 | 2022-07-04 |  | 100% | 23314500.07 |  | Physically Completed
DBM - Construction of Bugay Bridge | Bayawan City | 20000000 | 2023-06-26 |  | 63.72% | 11710753.84 |  | on going
DBM -Barangay Tabuan- Concreting of Farm to Market Road |  | 2500000 |  |  |  | 0 |  | not yet implemented
TOTAL |  | 422702078.44 |  |  |  | 334168110.93
845404156.88
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
OPHELIA URIKA R. TRINIDAD |  | DONALD B. TUBIO, CPA, MPM |  |  |  | JOHN T. RAYMOND, JR
Local Budget Officer |  | Local Accountant |  |  |  | Local Chief Executive
Page 3 of 3
.