## Form 7 - DFU
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
Region: REGION VII - CENTRAL VISAYAS |  | CALENDAR YEAR: |  | 2024
Province: NEGROS ORIENTAL |  | QUARTER: |  | 3rd Quarter
City/Municipality: CITY GOVERNMENT OF BAYAWAN
Program or Project | Location | Total Cost (per Budget Approp) | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Obligation (per Budget)
CURRENT APPROPRIATION
SOCIAL DEVELOPMENT
Installation of Water System for Sitio Malubog, Brgy. San Isidro | San Isidro | 3000000 |  |  | 100% | 3000000 | None | To be implemented by BAWAD
Development of Barangay Plaza, Brgy. Tabuan | Tabuan | 2400000 |  |  | 0% | 0 | -do- | Not yet started; Procurement in progress
Development of Public Plaza, Brgy. Kalumboyan | Kalumboyan | 5000000 |  |  | 0% | 0 | -do- | Not yet started; Procurement in progress
Improvement of Bayawan City AA Slaughterhouse | Banga | 10000000 |  |  | 0% | 0 | -do- | Not yet started; Procurement in progress
Improvement of Niludhan Falls | Dawis | 5000000 |  |  | 0% | 0 | -do- | Not yet started; Procurement in progress
Total Projects for Social Development - Current Appropriation |  | 25400000 |  |  | 11.81% | 3000000
ECONOMIC DEVELOPMENT
Loan Amortization | Various Brgys. | 83401498.4 |  |  | 97.6% | 81400620.25 | None | Loan availed to finance various developmental projects
Land Acquisition for Barangay Public Market, Brgy. Nangka | Nangka | 5000000 |  |  | 0% | 0 | -do- | Not yet started; Procurement in progress
Improvement of FMR from Barangay Proper to Cansi-ang, Brgy. Villasol | Villasol | 3000000 |  |  | 0% | 0 | -do- | Not yet started; Procurement in progress
Improvement of FMR from Malinong to Tangistangisan, Brgy. Villasol | Villasol | 3000000 |  |  | 0% | 0 | -do- | Not yet started; Procurement in progress
Construction of Access Road from National Highway to Boulevard, Brgy. Villareal | Villareal | 25000000 |  |  | 0% | 0 | -do- | Not yet started; Procurement in progress
Concreting of Access Road at Government Center, Cabcabon | Banga | 5000000 | 2024-04-01 | 2024-07-05 | 49.76% | 2487773.91 | -do- | On-going
Concreting of Kalumboyan-Tabuan FMR | Tabuan | 10000000 |  |  | 0% | 0 | -do- | Not yet started; Procurement in progress
Concreting of Tabuan-Banaybanay FMR | Banaybanay | 10000000 |  |  | 0% | 0 | -do- | Not yet started; Procurement in progress
Concreting of Urban Road (T. Diao Street Extension to Brgy. Hall, Poblacion) | Poblacion | 10000000 |  |  | 0% | 0 | -do- | Not yet started; Procurement in progress
Road Concreting at Purok Sampaguita, Barangay Villareal | Villareal | 4000000 | 2024-07-01 | 2024-09-13 | 63.22% | 2528962.82 | -do- | On-going
Concreting of Manduao-Bucao FMR | Manduao | 7700000 | 2024-04-01 | 2024-05-06 | 66.32% | 5106560.98 | -do- | On-going
Construction of Bantolinao Creek Double Flat Slab Bridge Connecting to Sitio Malon, Brgy. Tabuan | Tabuan | 2600000 |  |  | 0% | 0 | -do- | Not yet started; Procurement in progress
Construction of Barangay Public Market Building, Brgy. Tayawan | Tayawan | 5000000 | 2024-07-01 | 2024-12-18 | 0.206% | 10300 | -do- | On-going
Construction of Wet Market @ Omod Proper, Brgy. Maninihon | Maninihon | 5000000 | 2024-07-01 | 2024-12-18 | 14.7% | 734882.5 | -do- | On-going
1 Unit Mini-Hydraulic Excavator | Banga | 3000000 |  |  | 99.9% | 2997000 | -do- | Physically Completed
5 Units Dump Truck | Banga | 35000000 |  |  | 99.98% | 34991815 | -do- | Physically Completed
1 Unit Motor Grader with Ripper | Banga | 12000000 |  |  | 99.96% | 11995000 | None | Physically Completed
Concreting of GK Village Road | Villareal | 5000000 |  |  | 0% | 0 | -do- | Not yet started; Procurement in progress
Acquisition of Lot for LGU Development Projects | Bayawan City | 45053982.57 |  |  | 100% | 45053982.57 | -do- | Completed
Total Projects for Economic Development - Current Appropriation |  | 278755480.97 |  |  | 67.19% | 187306898.03
ENVIRONMENTAL MANAGEMENT
Improvement of Drainage Canals in Brgys. Tinago, Suba and Boyco | Boyco | 7500000 | 04/01/24 | 08/29/24 | 3.38% | 253508 | None | On-going
Total Projects for Environmental Management - Current Appropriation |  | 7500000 |  |  | 3.38% | 253508
TOTAL DF - CURRENT APPROPRIATION |  | 311655480.97 |  |  | 61.14% | 190560406.03
CONTINUING APPROPRIATION
SOCIAL DEVELOPMENT
Installation of Solar-Driven Water Systems for Napo, Brgy. Tayawan | Tayawan | 50000 |  |  | 0% | 0 | None | To be implemented by BAWAD
Purchase of 50 KVA Transformer for BCTLDC | Banga | 500000 |  |  | 0% | 0 | -do- | Not purchased yet
Water System Development at Bugay Proper | Bugay | 500000 | 2019-04-01 | 2020-12-31 | 35.04% | 175180.8 | -do- | Physically Completed
Development of Water System at Brgy. Villareal | Villareal | 1000000 | 2019-08-12 | 2020-11-30 | 39.38% | 393844 | -do- | Physically Completed
Construction & Installation of Water Supply Systems for Barangays Malabugas, San Roque, Minaba, San Miguel and Tayawan | Malabugas | 11000000 |  |  | 99.8% | 10977815 | -do- | Physically Completed
Construction of Day Care Center at Sitio Mantapi, Nangka | Nangka | 578571.43 | 2018-12-01 | 2020-12-01 | 50.85% | 294184.16 | -do- | Pending: Waiting for Deed of Donation
Improvement of Barangay Health Center & Lying-In Clinic, Brgy. Malabugas | Malabugas | 1000000 | 2019-07-05 | 2019-12-30 | 86.43% | 864307.07 | -do- | Physically Completed
Construction of Health Center at Sitio Mantapi, Nangka | Nangka | 500000 | 2019-11-12 | 2020-11-12 | 95.78% | 478921.94 | -do- | for abandonment, No site available, DOD issue
Improvement of Barangay Multi-Purpose Building, Banaybanay | Banaybanay | 1000000 | 2018-01-01 | 2018-06-30 | 65.91% | 659082 | -do- | Not yet started: Procurement Process
Construction of Children and Women's Crisis Center, Brgy. Suba | Suba | 600000 | 2018-01-01 | 2018-03-17 | 50.38% | 302300.77 | -do- | Not yet started: Procurement Process: For Abandonment
Improvement of Multi-Purpose Hall, Brgy. Suba | Suba | 578571.43 |  |  | 36.86% | 213278.94 | -do- | Subject for discontinuance
Major Repair of Manduao Barangay Agricultural Development Center (BADC) | Manduao | 290000 | 2018-09-30 | 2020-03-31 | 79.65% | 230987.73 | -do- | Physically Completed
Construction of Concrete Fence of Minaba Elementary School | Minaba | 500000 | 2019-05-16 | 2020-03-31 | 76.25% | 381251.98 | -do- | Physically Completed
Construction of Concrete Fence of Canabuan Elementary School | Minaba | 500000 | 2019-01-06 | 2020-03-31 | 93.22% | 466122.28 | -do- | On-going; PAINTING
Construction of Concrete Fence of Minaba High School | Minaba | 678571.43 | 2019-01-06 | 2020-03-31 | 71.05% | 482122 | None | Physically Completed
Construction of Perimeter Fence at San Roque Elementary School | San Roque | 578571.43 | 2019-01-06 | 2020-03-31 | 91.53% | 529538.13 | -do- | PENDING; G.I. PIPE "for re-ad" STATUS
Construction of Multi-Purpose Pavement at Sitio -Upper Pinangimnan | San Jose | 839285.7 | 2020-04-15 | 2020-08-15 | 86.3% | 724306.73 | -do- | Physically Completed
Construction of Multi-Purpose Pavement at Sitio Pitigo 1 | San Jose | 839285.73 | 2020-06-15 | 2020-10-16 | 81.42% | 683380.4 | -do- | Physically Completed
Supply & Installation of Hog & Cattle Slaughterhouse Equipment for Bayawan City AA Slaughterhouse Plant | Banga | 16478571.43 | 2022-02-01 | 2022-07-15 | 98.55% | 16239929.35 | -do- | On-going; PLUMBING AND PAINTING
Purchase of Lot for Barangay Multi-Purpose Hall Extension, Banga | Banga | 1678571.43 |  |  | 0% | 0 | -do- | Not purchased yet
Installation of Water Supply System at Sitios Bantolinao, Patag and Proper I, Brgy. Tabuan | Tabuan | 500000 | 2020-07-01 | 2020-10-05 | 0.594% | 2970 | -do- | Implemented by BAWAD
Construction of Small Scale Irrigation Project in Sitio Bolo, Tabuan | Tabuan | 459855 | 2022-03-01 | 2022-05-30 | 90.96% | 418266 | -do- | Implemented by Agri Engineering
Improvement of Water Supply System at BCWMEC | Maninihon | 600000 |  |  | 81.84% | 491055 | -do- | Implemented by BAWAD
Construction of Barangay Multi-Purpose Hall (Phase II), Cansumalig | Cansumalig | 1678571.43 | 2020-07-01 | 2020-12-20 | 70.71% | 1186868.45 | -do- | Pending: Materials not Delivered (Doors, Windows, and Floor Tiles)
Construction of Barangay Nangka Multi-Purpose Hall (Phase II) | Bayawan City | 2478571.43 | 2020-10-01 | 2021-03-30 | 84.72% | 2099788.9 | -do- | Pending: Painting Materials Not Available
Improvement of Barangay Multi-Purpose Building, Suba | Suba | 1678571.43 | 2020-10-01 | 2021-01-30 | 36.84% | 618431 | -do- | for abandonment
Construction of Barangay Multi-Purpose Hall, Tinago (Phase 4) | Tinago | 3878571.43 | 2020-10-01 | 2021-05-28 | 90.14% | 3496152.07 | -do- | Pending: Materials Not Completely Delivered
Construction of Multi-Purpose Hall, Brgy. Ubos (Phase 1) | Ubos | 2080000 | 2020-10-11 | 2021-04-15 | 90.16% | 1875296.21 | -do- | Pending: Materials Not Completely Delivered
Development of Water Supply System for Bayawan City "AA" Slaughterhouse & Poultry Dressing Plant | Bayawan City | 11700000 | 2022-02-01 | 2022-07-15 | 61.27% | 7169065.21 | -do- | On-going; PLUMBING AND PAINTING
Streetlighting Project at Sitio Cansig-id to Buli-buli, Barangay Banga | Banga | 700000 |  |  | 87.22% | 610558.15 | -do- | Physically Completed
Solar Streetlighting Project in Purok 1-Lower, Purok 2-Lower and Purok 4-Upper and Lower Cansilong, Brgy. Malabugas | Malabugas | 500000 | 2022-04-12 | 2022-04-12 | 84.32% | 421610.05 | -do- | On-going
Installation of Solar-Powered Streetlighting System at Dayhagan to Proper Minaba | Minaba | 300000 | 2021-11-16 | 2021-12-30 | 84.61% | 253815.36 | -do- | On-going
Installation of Solar Streetlighting System at Purok Falcata, Barangay San Roque | San Roque | 200000 | 2022-02-01 | 2022-03-06 | 3.956% | 7911.96 | -do- | On-going
Establishment of Special Care Isolation/Quarantine Faciltiy | Bayawan City | 2200000 | 2021-01-16 | 2021-03-31 | 0% | 0 | -do- | On-going
Improvement of Barangay Health Center, Tinago | Tinago | 600000 |  |  | 0% | 0 | -do- | Not yet started: Procurement Process
Construction of Barangay Evacuation Center, Dawis (Phase 2) | Dawis | 1678571.43 | 2021-07-01 | 2021-08-31 | 70.55% | 1184293.6 | -do- | On-going
Construction of Multi-Purpose Building, Brgy. Minaba | Minaba | 4800000 | 2021-09-22 | 2022-03-20 | 84.94% | 4077262.13 | -do- | Terminated as of December 21, 2022
Construction of Barangay Multi-Purpose Building, San Jose | San Jose | 1000000 | 2021-05-01 | 2021-06-15 | 48.62% | 486201.44 | None | Pending: Materials not available (doors and windows)
Improvement of Barangay Multi-Purpose Hall (Phase 1), San Roque | San Roque | 1000000 | 2023-05-01 | 2023-07-30 | 58.39% | 583912 | -do- | Not yet started: Procurement Process
Construction of Barangay Multi-Purpose Hall (Phase III), Cansumalig | Casumalig | 1678571.43 | 2021-07-01 | 2021-10-29 | 35.13% | 589695.47 | -do- | Pending: Remaining materials not yet delivered
Construction of Multi-Purpose Hall at Niludhan, Dawis | Dawis | 500000 | 2021-07-01 | 2021-08-15 | 38% | 189975.4 | -do- | Physically Completed
Construction of Multi-Purpose Building (Phase III), Brgy. Poblacion | Poblacion | 1678571.43 | 2021-12-15 | 2022-02-15 | 76.31% | 1280901.33 | -do- | Pending: Insufficient Materials Delivered
Construction of Water Filtration Tank at Barangay Narra | Narra | 1100000 | 2023-01-13 | 2023-04-13 | 77.44% | 851886.95 | -do- | Pending, remaining works; Installation of Roofing materials and Plumbing Works
Road Improvement at Bugay Proper to National High School, BADC and Sitio Gaw-gaw | Bugay | 1678571.43 | 2022-04-18 | 2022-06-15 | 34.61% | 581035.16 | -do- | Pending: Physically Completed but no PR
Improvement of Barangay Road Going to Proper B and High School, Brgy. Banaybanay | Banaybanay | 178571.43 | 2022-01-03 | 2022-02-15 | 85.8% | 153221.28 | -do- | Pending: Waiting for heavy equipment schedule
Development of Water System at Agricultural Development Center (ADC), Brgy. San Miguel | San Migue | 200000 |  |  | 0.535% | 1070 | -do- | Not started; Subject for discontinuance
Construction of Tayawan-Minaba Water System | Tayawan | 25000000 | 2023-12-29 | 2024-05-31 | 65.03% | 16256420 | -do- | On-going
Installation of Solar-Powered Streetlighting System at Sitio Dayhagan to Proper Minaba (Phase 2) | Minaba | 500000 | 2022-01-03 | 2022-02-20 | 24.25% | 121246.45 | -do- | Subject For Discontinuance
Construction of Senior Citizen and PWD Building, Brgy. Malabugas | Malabugas | 1300000 | 2022-04-01 | 2022-06-10 | 85.97% | 1117576.9 | -do- | On-Going
Construction of Socio-Cultural Services Center | Bayawan City | 3357142.86 |  |  | 0% | 0 | -do- | Not yet started; Procurement in progress
Renovation of Cayaocao Health Center, Brgy. Narra | Narra | 150000 | 2022-04-18 | 2022-05-15 | 65.1% | 97643.9 | -do- | Pending, no delivery of remaining material. Remaining works Installation of Ceiling (interior).
Rehabilitation of Barangay Health Center, San Roque | San Roque | 1678571.43 | 2022-05-01 | 2022-09-30 | 100% | 1678571.43 | -do- | No Vital Materials, Subject for Cancellation
Improvement of Lying-in Clinic, Manduao | Manduao | 650000 |  |  | 32.71% | 212611.49 | -do- | Subject For Discontinuance
Construction of Barangay Evacuation Center, Dawis (Phase 3) | Dawis | 1678571.43 | 2022-10-12 | 2022-12-15 | 85.14% | 1429195.15 | -do- | Physically Completed
Improvement of Multi-Purpose Hall, Barangay Pagatban | Pagatban | 1678571.43 |  |  | 0% | 0 | -do- | Subject For Discontinuance
Construction of Multi-Purpose Hall at Niludhan, Dawis (Phase II) | Dawis | 1200000 | 2022-01-04 | 2022-10-06 | 68.52% | 822287.5 | -do- | Subject For Discontinuance
Construction of Multi-Purpose Building (Phase IV), Brgy. Poblacion | Poblacion | 550000 | 2022-07-01 | 2022-09-15 | 4.575% | 25163.26 | -do- | Pending: Materials not delivered yet
Construction of Multi-Purpose Building at Sitio Bia-as, San Miguel (Phase II) | San Migue | 2250000 | 2022-09-03 | 2023-01-10 | 62.2% | 1399492.22 | -do- | Pending; No trusses and roof materials available
Improvement of Barangay Multi-Purpose Building, Suba (Phase II) | Suba | 1678571.43 |  |  | 0% | 0 | -do- | Subject for discontinuance
Installation of Solar-Powered Streetlighting System along T. Diao Street from National Highway to Gomez Street Rotunda | Bayawan City | 400000 | 2023-04-03 | 2023-05-03 | 62.96% | 251823.46 | None | On-going
Construction of Socio-Cultural Services Center, Boyco (Phase 2) | Boyco | 5000000 |  |  | 0% | 0 | -do- | Not yet started; Procurement in progress
Construction of 2-Storey Multi-Purpose Building, Suba | Suba | 5000000 | 2023-04-04 | 2023-09-17 | 99.79% | 4989671.52 | -do- | Not yet started; Procurement in progress
Construction of Multi-Purpose Hall and Evacuation Center @ Sitio Cabcabon, Banga (Phase 1) | Banga | 26000000 | 07/01/22 | 08/31/22 | 0.1562% | 40600 | -do- | In progress
Improvement of Barangay Multi-Purpose Hall, Banga | Banga | 2500000 |  |  | 0% | 0 | -do- | Not yet started; Procurement in progress
Improvement of Barangay Multi-Purpose Building, San Isidro | San Isidro | 1500000 | 2023-10-02 | 2023-11-16 | 0% | 0 | -do- | On-going
Total Projects for Social Development - Continuing Appropriation |  | 166808426.46 |  |  | 54.66% | 91170099.68
ECONOMIC DEVELOPMENT
Purchase of Various Heavy Equipment | Banga | 50260406.99 |  |  | 93.08% | 46784000 | None | Purchased for the construction of developmental projs
Road Rehabilitation at So. Camague, Brgy Dawis | Dawis | 500000 | 11/31/2019 | 2020-07-31 | 87.14% | 435724.2 | -do- | On-going
Road surfacing at Manduao-Bucao, Brgy Manduao | Manduao | 500000 | 2016-03-11 | 2016-07-28 | 98.95% | 494731 | -do- | Pending: Heavy Equipment Available
Improvement of Brgy. Dawis Livestock Auction Market | Dawis | 150000 | 2019-09-01 | 2019-12-31 | 0% | 0 | -do- | Physically Completed
Road Surfacing at Barangay Cansumalig | Cansumalig | 1078571.43 | 2018-04-01 | 2018-05-31 | 91.89% | 991106.86 | -do- | Physically Completed
Construction of Fish Processing Center @ Brgy. Suba | Suba | 2500000 | 2019-04-01 | 2019-12-31 | 91.56% | 2288877.33 | -do- | pending: no glassworks
Establishment of Agricultural Research Center | Bayawan City | 6895568.71 | 2022-10-10 | 2023-04-30 | 87.57% | 6038727.64 | -do- | On-going
Wayang Access Road Development | Nangka | 20000000 | 2019-02-16 | 2021-11-30 | 92.47% | 18493484.13 | -do- | Physically Completed
Construction of Ondol-Napit-an FMR | Maninihon | 20000000 | 2019-03-15 | 2020-08-31 | 98.93% | 19785191.55 | -do- | Physically Completed
Concreting of Urban Roads with Drainage System (Gomez St.) | Poblacion | 3000000 | 2019-07-16 | 2020-03-31 | 85.05% | 2551641.43 | -do- | Physically Completed
Construction of Dawis Public Market (Phase 2) | Dawis | 2000000 | 2020-09-01 | 2021-01-16 | 76.26% | 1525227.5 | -do- | Pending : Due to Materials availability
Completion of Urban Road (Gomez Ext.) | Poblacion | 6000000 | 2020-01-02 | 2021-04-30 | 84.26% | 5055572.25 | -do- | Physically Completed
Concreting of Inland Aquaculture Road Network | Nangka | 7500000 | 2020-10-01 | 2021-04-19 | 78.3% | 5872530.85 | -do- | Physically Completed
Improvement of Farm to Market Road at Sitio Dita, Ali-is | Ali-is | 1078571.43 | 2020-07-01 | 2021-10-21 | 76.06% | 820316.12 | -do- | Physically Completed
Concreting of Tower-Baong Road, Kalamtukan | Kalamtukan | 500000 | 2020-10-01 | 2020-11-05 | 62.79% | 313925.8 | -do- | Pending: Materials not fully delivered
Concreting of Manduao-Bucao Farm to Market Road | Manduao | 1000000 | 2020-10-01 | 2020-12-30 | 59.4% | 594030.1 | -do- | Pending: No Billboard available
Construction of Flat Slab Bridge at Magtangis Creek in Sitio Guintana-an, Brgy. Tayawan | Tayawan | 1678571.43 | 2020-10-01 | 2020-12-29 | 73.44% | 1232742.93 | -do- | PENDING DUE TO DOWNSTREAM APRON USED AS TEMPORARY DETOUR
Barangay Electrification Project, San Jose | San Jose | 858571.43 |  |  | 0% | 0 | -do- | Not yet started: Procurement Process
Electrification Project at Purok Sambag, San Roque | San Roque | 600000 |  |  | 0% | 0 | -do- | Not yet started: Procurement Process
Construction of Public Market Building, Maninihon | Maninihon | 2378571.43 | 2020-10-01 | 2021-03-30 | 68.59% | 1631450.99 | None | Pending, no delivery of windows,roll up doors, plumbing and electrical fixtures.
Construction of Dawis Public Market (add'l fund) | Dawis | 825000 |  |  | 9.719% | 80178.75 | -do- | Pending: Due to materials availability
Construction of Bunker Silo | Bayawan City | 1000000 | 2020-08-01 | 2020-12-31 | 82.04% | 820364 | -do- | For Implementation: Material Delivered:83.89% For Delivery 0.29% Re-Add 15.82%
Concreting of Tabuan-Ali-is FMR | Tabuan | 10000000 | 2021-05-01 | 2021-12-15 | 79.72% | 7971725.05 | -do- | Pending: No delivery of chevron signs
Concreting of Minaba-Tayawan-Kalumboyan FMR | Minaba | 10000000 | 2021-04-01 | 2022-01-15 | 71.85% | 7184963.97 | -do- | pending: no chevron signs and billboard materials
Concreting of San Roque-San Miguel FMR | San Roque | 11284948.4 | 2021-10-01 | 2022-05-30 | 46.79% | 5280203.45 | -do- | PENDING; BILLBOARD AND CHEVRON SIGN MATERIALS NOT YET AVAILABLE
Rehabilitation of Farm to Market Roads in Various Sitios, Brgy. Kalumboyan | Kalumboyan | 1678571.43 | 2021-10-01 | 2022-04-01 | 79.17% | 1328949.96 | -do- | Pending: Waiting for materials fully delivered
Road Concreting along Refilling Station at Gomez St., Brgy. Ubos | Ubos | 500000 | 2021-10-01 | 2021-10-31 | 84.74% | 423700.35 | -do- | Physically Completed
Road Improvement from National Highway to Purok Balatong I and Purok Balatong II, Manduao | Manduao | 1900000 | 2021-04-01 | 2021-12-15 | 91.6% | 1740346.5 | -do- | Pending
Concreting of Dawis-Lapay FMR | Dawis | 10000000 | 2021-07-01 | 2022-02-15 | 58.03% | 5803378.75 | -do- | Pending( No chevron signages delivered due to bidding failed)
Concreting of Nangka-Narra FMR | Nangka | 10000000 | 2021-10-01 | 2022-05-31 | 83.33% | 8333258.54 | -do- | Pending: No available materials for Chevron signs, no delivery of primary materials (sand & gravel, aggregates and boulders)
Concreting of Circumferential Road at Brgy Proper 1, Brgy Tabuan | Tabuan | 2800000 | 2022-11-15 | 2023-04-15 | 22.22% | 622035.35 | -do- | On-going
De-silting of Pagtigaon Creek at Barangay Maninihon | Maninihon | 500000 | 2021-07-01 | 2021-08-15 | 77.3% | 386495.45 | -do- | Physically Completed
Improvement of Communal Irrigation Systems | Nangka | 10305205.13 | 2023-10-31 | 2024-01-31 | 68.67% | 7076104.44 | -do- | Project is under DA
Sitio Electrification Project, Brgy. San Jose | San Jose | 2778571.43 |  |  | 0% | 0 | -do- | Not yet started: Procurement Process
Construction of Barangay Public Market Stalls (Phase 1), Brgy. Banaybanay | Banaybanay | 1000000 | 2021-07-01 | 2021-07-16 | 60.38% | 603819.6 | -do- | On-going
Fabrication of Steel Scaffolding and Home Building System | Bayawan City | 5000000 | 2021-07-01 | 2022-02-15 | 55.11% | 2755499.5 | -do- | PENDING; NO TUBULAR MATERIALS
Construction of New Materials Recovery Facility | Bayawan City | 3500000 |  |  | 26.53% | 928546.55 | -do- | PENDING; NO TUBULAR MATERIALS
Construction of Cattle Shed at Napit-an, Brgy Maninihon | Maninihon | 1200000 | 2020-07-01 | 2020-12-31 | 79.68% | 956185.8 | -do- | Physically Completed
Construction of Perimeter & Divisional Fences for Cattle at Napit-an, Barangay Maninihon | Maninihon | 800000 | 2020-07-01 | 2020-12-31 | 90.03% | 720236 | -do- | Physically Completed
Fabrication of 4 Units Flatbed Dryer with Shed | Dawis, Narra, Kalumboyan, Tayawan | 4800000 | 2023-11-20 | 2023-12-19 | 99.17% | 4760000 | -do- | Physically Completed
Concreting of Maninihon-Cansumalig FMR | Maninihon | 5000000 | 2022-08-22 | 2023-01-15 | 97.18% | 4859169.48 | None | Physically Completed
Concreting of Minaba-Tayawan FMR | Minaba | 10000000 | 2022-10-01 | 2023-04-04 | 78.81% | 7880874.41 | -do- | Physically Completed
Improvement of Tabuan-Banaybanay-Lapay-Bugay FMR | Tabuan | 5000000 | 2022-04-01 | 2022-10-10 | 87.21% | 4360334.86 | -do- | Pending: Materials Not Completely Delivered
Concreting of Barangay Roads with Drainage Canal at Manduao Proper | Manduao | 1150000 | 2022-10-01 | 2022-11-21 | 79.73% | 916942.66 | -do- | Pending : Due to Materials availability
Concreting of Urban Road (T. Diao Street to Brgy. Hall, Poblacion) | Poblacion | 10000000 | 2022-04-01 | 2022-09-22 | 39.5% | 3949971.81 | -do- | Pending: Materials Not Completely Delivered
Road Concreting along Bollos St., Ubos | Ubos | 2740000 | 2022-01-03 | 2022-04-10 | 64.62% | 1770663.1 | -do- | Physically Completed
Road Shoulder Concreting Along Zamora to Gomez Street | Bayawan City | 2000000 | 2022-04-01 | 2022-07-10 | 97.22% | 1944377.2 | -do- | Physically Completed
Road Concreting Going to Barangay Agricultural Development Center, Ali-is | Ali-is | 1178571.43 | 2022-10-01 | 2022-12-10 | 86.45% | 1018836.11 | -do- | Physically Completed
Road Concreting with Drainage Canal from National Highway to Kalamtukan National High School | Kalamtukan | 1678571.43 | 2022-04-01 | 2022-07-10 | 58.26% | 977891.95 | -do- | Pending, No delivery of Remaining materials. Actual accomplishment: Physically completed
Road Concreting at Sitio Gamao, Brgy. Narra | Narra | 700000 | 2022-01-01 | 2023-02-10 | 80.77% | 565388.4 | -do- | Physically Completed
Road Rehabilitation and Concreting at Sitio Cabcabon, Banga | Banga | 600000 | 2022-01-03 | 2022-02-10 | 70.46% | 422757.75 | -do- | Pending: Materials Not Completely Delivered
Construction of Farm to Market Road at Sitio Upper Pamu-at, Brgy. San Isidro (Phase II) | San Isidro | 500000 | 2022-05-01 | 2022-08-10 | 36.85% | 184236.97 | -do- | Pending ; Accom.: Physically completed Materials del.: 19.22%
Road Concreting at Barangay Proper Going to Box Culvert at Sitio Upper Pamu-at, Brgy. San Isidro | San Isidro | 1678571.43 | 2022-01-01 | 2023-01-10 | 61.3% | 1028971.27 | -do- | Pending, No delivery of Remaining materials. Actual accomplishment: Physically completed
Improvement of Dawis-Lapay FMR | Dawis | 5000000 | 2022-10-01 | 2023-04-10 | 57.5% | 2875131.22 | -do- | Pending
Improvement of Nangka-Narra FMR | Nangka | 5000000 | 2022-01-01 | 2022-07-10 | 68.15% | 3407679.24 | -do- | Pending; Accom.: Physically completed Materials del.: 34.36%
Improvement of Banga-Tayawan FMR | Banga | 5000000 | 2022-04-01 | 2022-10-10 | 91.08% | 4553754.52 | -do- | PENDING; NO BILLBOARD MATERIALS AVAILABLE
Improvement of Gamao-Cadal-ugan FMR | Narra | 5000000 | 2022-01-03 | 2022-07-10 | 89.19% | 4459415.27 | -do- | Physically Completed
Improvement of Barangay Road with Concrete Canal at Proper I, Tabuan | Tabuan | 1300000 | 2022-01-03 | 2022-02-15 | 64.71% | 841181.02 | -do- | Pending: materials not fully delivered
Improvement of Farm to Market Road at Sitios Baong, Bocao and Cangcawit, Brgy. Banaybanay | Banaybanay | 1500000 | 2022-01-03 | 2022-04-20 | 87.91% | 1318676 | -do- | On-going
Improvement of Farm to Market Road at Purok Ipil-Ipil, San Roque | San Roque | 500000 | 2022-04-01 | 2022-08-20 | 90.7% | 453502 | -do- | Pending: Road not passable
Improvement of Farm to Market Road at Sitio Bantolinao, Malon to Proper, Brgy. Tabuan | Tabuan | 300000 | 2022-07-01 | 2022-09-10 | 1.127% | 3380 | -do- | Pending: Waiting for heavy equipment schedule
Improvement of Farm to Market Roads at Sitios Cansolomon, Upper Baco and Manggopo, Brgy. Tayawan | Tayawan | 500000 | 2022-10-01 | 2022-11-20 | 88.58% | 442919.75 | None | Pending: Waiting for heavy equipment schedule
Improvement of Sitio Road with Drainage Canal and Flat Slab Bridge at Purok Sampaguita, Brgy. Villareal | Villareal | 2000000 | 2022-01-01 | 2023-01-10 | 55.25% | 1104920.71 | -do- | Pending: Materials Not Delivered
Improvement of Drainage Canals at Barangay Proper, Kalumboyan | Kalumboyan | 1678571.43 | 2022-04-12 | 2022-04-12 | 72.33% | 1214028.79 | -do- | Pending: materials not fully delivered
Improvement of Drainage Canal Alongside Barangay Hall, Poblacion | Poblacion | 900000 | 2022-10-03 | 2022-12-10 | 88.47% | 796218.66 | -do- | Pending: Materials Not Completely Delivered
Construction of Flat Slab Bridge at Purok II, Brgy. Narra | Narra | 600000 | 2022-01-03 | 2022-03-10 | 20.89% | 125323.83 | -do- | PENDING, NO AREA/SITE AVAILABLE, ROW ISSUES AND DOD
Construction of Flat Slab Bridge at Purok III, Brgy. Narra | Narra | 500000 | 2022-04-01 | 2022-06-10 | 43.92% | 219578.9 | -do- | Pending, No delivery of remaining materials. Actual accomplishment: Physically Completed
Construction of Barangay Public Market Stalls (Phase 2), Brgy. Banaybanay | Banaybanay | 500000 | 2022-04-01 | 2022-05-10 | 47.18% | 235880 | -do- | Subject For Discontinuance
Rehabilitation of Solar Drying Pavement, Brgy. Kalumboyan | Kalumboyan | 1000000 | 2022-04-12 | 2022-04-12 | 76.71% | 767122.38 | -do- | On-going
Completion of Farrowing Pens | Bayawan City | 450000 |  |  | 0% | 0 | -do- | Not started yet
Loan Amortization | Banga | 54000000 |  |  | 99.82% | 53902201.15 | -do- | Loan availed to finance various developmental projects
Purchase of Lor for Barangay Facilities, Minaba | Minaba | 3000000 |  |  | 0% | 0 | -do- | Not yet purchased
Concreting of Urban Road (P. Gamo Extension to Brgy. Hall, Poblacion) | Poblacion | 15428574 | 2023-04-01 | 2023-11-10 | 79.74% | 12302481.6 | -do- | On-Going; Materials Not Completely Delivered
Road Concreting at Purok 2, San Jose | San Jose | 3000000 | 2023-04-03 | 2023-10-15 | 84.12% | 2523524.79 | -do- | On-going
Road Shoulder Concreting and Drainage Construction along Gomez Street, Ubos | Ubos | 4620000 | 2023-04-03 | 2023-11-15 | 83.69% | 3866418.92 | -do- | Pending: Materials Not Completely Delivered
Road Shoulder Concreting along J.P. Rizal Street | Bayawan City | 6300000 | 2023-04-03 | 2023-03-17 | 85.34% | 5376376.8 | -do- | On-going
Road Shoulder Concreting at Maninihon-Cansumalig-San Isidro FMR | Maninihon | 5000000 | 2023-01-02 | 2023-06-30 | 82.6% | 4130185.75 | -do- | On-going
Road Concreting with Drainage Canal and Slope Protection from Proper going to Kalamtukan Elementary School | Kalamtukan | 2500000 | 2023-04-03 | 2023-07-15 | 77.74% | 1943526.71 | -do- | On-going
Road Concreting at Barangay Proper, San Miguel | San Miguel | 3200000 | 2023-04-01 | 2023-06-16 | 90.57% | 2898316.8 | -do- | PENDING; NO BILLBOARD MATERIALS
Road Concreting going to Public Market and Banaybanay National High School | Banaybanay | 4000000 | 2023-04-03 | 2023-07-15 | 75.33% | 3013336.52 | -do- | Pending: Materials not fully delivered
Road Concreting going to Banaybanay Health Center | Banaybanay | 1000000 | 2023-04-03 | 2023-05-31 | 52.44% | 524449.4 | -do- | Pending: Materials not fully delivered
Road Rehabilitation at Purok Dol-dol and Ipil-ipil, San Roque | San Roque | 3000000 | 2023-04-01 | 2023-07-12 | 91.94% | 2758290.8 | None | PENDING; NO BILLBOARD MATERIALS
Construction of Ondol-Wayang-Napit-an Road (Phase 3) | Maninihon | 14185000 | 2023-04-01 | 2023-12-19 | 88.93% | 12615247.19 | -do- | On-Going
Road Concreting at Purok Pagkakaisa, Villareal | Villareal | 1500000 | 2023-04-01 | 2023-05-31 | 78.62% | 1179354.46 | -do- | Pending: Materials not fully delivered
Improvement of Farm to Market Road at Sitio Naga, Minaba | Minaba | 2000000 | 2023-01-01 | 2023-04-25 | 95.24% | 1904730.85 | -do- | PENDING; NO BILLBOARD MATERIALS AVAILABLE
Development of Dayhagan-Guintanaan Sitio Road | Minaba | 10000000 |  |  | 0% | 0 | -do- | No. POW
Rehabilitation of Farm to Market Roads in Various Rural Barangays | Various Brgys. | 4000000 |  |  | 100% | 4000000 | -do- | Physically Completed
1 units Motor Grader | Banga | 12000000 |  |  | 99.98% | 11997000 | -do- | Physically Completed
1 unit Road Roller | Banga | 6000000 |  |  | 99.97% | 5998000 | -do- | Physically Completed
1 unit Transit Mixer | Banga | 5000000 |  |  | 99.9% | 4995000 | -do- | Physically Completed
1 unit Mini Dump Truck | Banga | 2000000 |  |  | 99.75% | 1995000 | -do- | Physically Completed
1 unit Fuel Tanker | Banga | 3000000 |  |  | 99.83% | 2995000 | -do- | Physically Completed
1 unit Forklift | Banga | 2000000 |  |  | 99.75% | 1995000 | -do- | Physically Completed
2 Units Hydraulic Excavator Wheel Type | Banga | 11320000 |  |  | 0% | 0 | -do- | Not yet purchased
1 Unit Self-Loading Truck | Banga | 8430000 |  |  | 99.94% | 8425000 | -do- | Physically Completed
1 Unit Skid Steer Loader | Banga | 3000000 |  |  | 99.9% | 2997000 | -do- | Physically Completed
1 Unit Tri-axle Low Bed Trailer | Banga | 1965000 |  |  | 99.75% | 1960000 | -do- | Physically Completed
Acquisition of Lot for LGU Development Projects | Various Brgys. | 107834479.21 |  |  | 100% | 107834479.21 | -do- | Physically Completed
Total Projects for Economic Development - Continuing Appropriation |  | 591588468.17 |  |  | 82.75% | 489514321.9
ENVIRONMENTAL MANAGEMENT
Construction of Toxic and Hazardous Waste Vault Phase 2 | Bayawan City | 800000 | 2020-09-01 | 2020-12-01 | 89.8% | 718368.7 | None | Physically Completed
Construction of Foot Bridge at Sitio Kaayahan, San Jose | San Jose | 2000000 | 2020-10-01 | 2020-12-20 | 85.36% | 1707275 | -do- | Physically Completed
1 Unit Brand New Garbage Compactor Truck ( Additional Fund) | Bayawan City | 1500000 |  |  | 99.27% | 1489000 | -do- | Physically Completed
Total Projects for Environmental Management - Continuing Appropriation |  | 4300000 |  |  | 91.04% | 3914643.7
GRAND TOTAL DF - CURRENT & CONTINUING APPROPRIATION |  | 762696894.63 |  |  | 76.65% | 584599065.28
TOTAL Appropriation |  | 1074352375.6 |  |  | 72.15% | 775159471.31
We hereby certify that we have reviewed the contents and hereby attest to the veracity and corretness of the data or infromation contained in this document.
OPHELIA URIKA R. TRINIDAD |  |  |  | JOHN T. RAYMOND, JR.
City Budget Officer |  |  |  | Local Chief Executive

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2
43