## 1
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES | [8 empty] | Note: - Printed -For signature by Donals & CMO dated 10/16/24
REGION: REGION VII - CENTRAL VISAYAS |  | CALENDAR YEAR: 2023 | 2025
PROVINCE NEGROS ORIENTAL |  | QUARTER: 4 | 1
CITY/MUNICIPALITY CITY OF BAYAWAN (TULONG)
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of | Remarks
[5 empty] | % of | Total Cost Incurred | Extensions, if
[5 empty] | Completion | to Date | any
Sta. Bayabas - Common Health Fund | Bayawan City | 3611053.63 |  |  |  | 727323.7 |  | on going
DA for Retention Fee for 2019 Rubber (Seedling Production: Site Preparation | Bayawan City | 494250 |  |  |  | 0 |  | on going
DA for Rice Extension Service Program (RESP) Scholarship Grant and TESDA 7 TVET Program | Bayawan City | 16361739.45 |  |  |  | 599987.5 |  | for implementation by City Agriculture
DA for Shielded Metal Arc Welding (SMAW) NC I & NC II from TESDA 7 Negros Oriental | Bayawan City | 554700 |  |  |  | 111488 |  | on going
DENR to Enhance National Greening Program - Seedling Production & Seedling Maintenance activities of its Rubber (2018) | Bayawan City | 283728 |  |  |  | 0 |  | for implementation by City Agriculture | 20201050-004-000058
DENR to Enhance National Greening Program 2018 (DENR) - Green Rubber Budding, Care and Maintenance of Budded Seedlings | Bayawan City | 692220 |  |  |  | 0 |  | on going | 20201050-004-000059
DENR to Enhance National Greening Program 2019 (DENR) - Site Preparation and Planting, and 1st Year Maintenance and Protection activities of its Rubber | Bayawan City | 747485.6 |  |  |  | 0 |  | for implementation by City Agriculture | 20201050-004-000074
Page 1 of 3
DENR to Enhance National Greening Program 2019 Rubber - Year III 1st Maintenance and Protection | Bayawan City | 423155.25 |  |  |  | 0 |  | for implementation by City Agriculture | 20201050-004-000081
DENR to Enhance National Greening Program 2019 Rubber- 2nd Year Maintenance and Protection | Bayawan City | 398356.87 |  |  |  | 0 |  | for implementation by City Agriculture | 20201050-004-000080
DENR to Enhance National Greening Program 2020 Rubber- Maintenance and Protection |  | 16532.25 |  |  |  | 0 |  | for implementation by City Agriculture
DENR to Enhance National Greening Program 2020 Rubber- Maintenance and Protection Year II |  | 41330.62 |  |  |  | 0 |  | for implementation by City Agriculture
DOH to Completion of Minaba Barangay Health Station | Barangay Tabuan | 500000 |  |  |  | 133399.39 |  | For Re-POW | 20201050-004-000061
DOH to Construction/Completion/ Expansion of Villasol Birthing Facility (BHS) | Barangay Villasol | 500000 |  |  |  | 0 |  | per CEO: Procurement process | 20201050-004-000086
CSWD Social Pension Progrtam from Indigent Senior Citizen | Bayawan City | 35316000 |  |  |  | 0 |  | on going
DOLE Integrated Livelihood Project (Kabuhayan Program) | Bayawan City | 3742694 |  |  |  | 0 |  | on going | 20201050-004-000088
NORSU & LGU Equity to "Bayawan LGU-NORSU" Joint Venture for Sports Complex Project | Bayawan City - NORSU | 280000000 | 2020-09-09 |  | 93.28% | 269998999.2 |  | on going | 20401010-001 | 10710030-030-0257
LGU Equity to Construction of BAYAWAN-NORSU Sports Complex | Bayawan City - NORSU | 37499269.15 |  |  |  | 37499269.15 |  | on going | 20201070-005-078 | 10710030-030-0260
DBM to Construction of Sen. Lorenzo G. Teves Memorial Circle (Rotunda) | Bayawan City | 16826393 | 2022-05-02 |  | 86.85% | 6402717.12 |  | per CEO: Pending no tiles deliver; no electrical & pluming materials for the fountain delever | 10710020-001-0222
NHA-LGU Equity to Development of Enzo Town House, Phase I | Bayawan City | 20032192.5 |  |  |  | 11248657.23 |  | on going | 20201050 & 20201070 10710020-030-0012 | 10 CIP -710020-030-0012)
Page 2 of 3
DILG Fire Code Fees Collection (20% LGU Share) | Bayawan City | 1110446.49 |  |  |  | 222454 |  | on going
KOICA - COVID-19 Isolation Facility and Diagnostic Laboratory (medical, laboratory and Other MOOE) | Bayawan City | 21214261.19 |  |  |  | 100930 |  | per CEO: Procurement process
DBM - Construction of Bugay Bridge | Bayawan City | 20000000 | 2023-06-26 |  | 63.72% | 15008402.94 |  | on going
DBM Concreting of Farm to Market Road from Proper Tabuan going Sitio Bunga-bunga Brgy. Tabuan | Bayawan City | 5000000 |  |  |  | 0 |  | not yet implemented
DBM -Barangay Tabuan- Concreting of Farm to Market Road | Bayawan City | 2500000 |  |  |  | 580550 |  | not yet implemented
TOTAL |  | 467865808 |  |  |  | 342634178.23
935731616
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
OPHELIA URIKA R. TRINIDAD |  | DONALD B. TUBIO, CPA, MPM |  |  |  | JOHN T. RAYMOND, JR
Local Budget Officer |  | Local Accountant |  |  |  | Local Chief Executive
Page 3 of 3
.